## 1. All Data
| 2021-22 Corporate Plan Reporting Spreadsheet |  |  |  | QUARTER 1: April - June 2021 |  |  |  | QUARTER 2: July - September 2021 |  |  |  |  | QUARTER 3: October - December 2021 |  |  |  |  | QUARTER 4: January - March 2022
Reporting Officer | Corporate Plan Ref Number | Measures | Target 2020/21 | Target Date | Quarter 1 (April - June 2021) | End of year forecast as at end of Q1 (NUMERICAL INDICATORS ONLY) | Quarter 1 On Track? (R/A/G) | Comments / Further action (Q1) (IF APPLICABLE) | Quarter 2 (July - September 2021) | Year to date (April - Sept 2021) (NUMERICAL INDICATORS ONLY) | End of year forecast as at end of Q2 (NUMERICAL INDICATORS ONLY) | Quarter 2 On Track? (R/A/G) | Comments / Further action (Q2) (IF APPLICABLE) | Quarter 3 (October - December 2021) | Year to date (April - Dec 2021) (NUMERICAL INDICATORS ONLY) | End of year forecast as at end of Q3 (NUMERICAL INDICATORS ONLY) | Quarter 3 On Track? (R/A/G) | Comments / Further action (Q3) (IF APPLICABLE) | Quarter 4 (January - March 2022) | Cumulative Annual Outturn (NUMERICAL INDICATORS ONLY) | End of Year Achieved? (R/A/G) | Comments / Further action (Q4) (IF APPLICABLE) | Qtr | Service | Team | Corporate Priority | Portfolio | Statement Reference Number | CP order
James Abbott | VFM 01 | Successful Delivery of Elections | Successfully Deliver Staffordshire County Council Elections | 2021-05-01 | Staffordshire County Council elections were successfully undertaken in May 2021. |  | Fully Achieved | [15 empty] | 1 | Andy O'Brien | Corporate & Commercial | Value for Money | Leader | L01 | 01
Nicola Gilligan | VFM 02 | Successful Delivery of Elections | Successfully Deliver PFCC Election as PARO with all constituent authorities submitting returns by 11 May | 2021-05-01 | The PFCC Election was delivered successfully. |  | Fully Achieved | [15 empty] | 1 | Andy O'Brien | Elections | Value for Money | Leader | L02 | 02
Nicola Gilligan | VFM 03 | Implementation of Boundary Review Outcomes | Prepare for amended boundaries and complete Polling Place Review | 2022-03-01 | Waiting for the order to be laid in Parliament before commencing the Polling Place Review. |  | On Track to be Achieved | [15 empty] | 4 | Andy O'Brien | Elections | Value for Money | Leader | L03 | 03
James Abbott | VFM 04 | Embracing Digital Opportunities | Maintain GeoPlaces Gold Standard in ESBC related categories | 2022-03-01 | Work is ongoing towards maintaining gold standard LLPG data. A resync of the Council's data with Geoplace, scheduled for later this year, will further improve the quality of our data. |  | On Track to be Achieved | [15 empty] | 4 | Sal Khan | Programmes & Transformation | Value for Money | Leader | L04 | 04
James Abbott | VFM 05 | Embracing Digital Opportunities | Establish a process for reviewing digital services that begins by identifying the intended outcome, designing the process and considering the technology most suitable to deliver that outcome | 2021-09-01 | A process for reviewing digital services is due to be presented to the Strategic Digital Group for consideration. |  | On Track to be Achieved | [15 empty] | 2 | Sal Khan | Programmes & Transformation | Value for Money | Leader | L05 | 05
James Abbott | VFM 06 | Embracing Digital Opportunities | Implement Phase 1 of the UPRN project | 2022-03-01 | First task to be completed is a resync of the LLPG against the NLPG. Resync requested waiting for guidance from Geoplace on the file format. |  | On Track to be Achieved | [15 empty] | 4 | Sal Khan | Programmes & Transformation | Value for Money | Leader | L06 | 06
James Abbott | VFM 07 | Embracing Digital Opportunities | Complete Feasibility Study investigating the possibility of introducing online customer accounts | 2021-09-01 | A feasibility report is due to be presented to the Strategic Digital group in August for consideration. |  | On Track to be Achieved | [15 empty] | 2 | Sal Khan | Programmes & Transformation | Value for Money | Leader | L07 | 07
James Abbott | VFM 08 | Continue to Develop Effective Communications | Implement Corporate E-Newsletter solution | 2021-07-01 | Corporate E-Newsletter designed and implemented. Content of the first edition approved and issued w/c 26th July. |  | Fully Achieved | [15 empty] | 2 | Sal Khan | Programmes & Transformation | Value for Money | Leader | L08 | 08
James Abbott | VFM 09 | Continue to Develop Effective Communications | Leader’s Blog live on the Council Website | 2021-05-01 | Leaders blog live on the website in May 2021 with an introductory post. |  | Fully Achieved | [15 empty] | 1 | Sal Khan | Programmes & Transformation | Value for Money | Leader | L09 | 09
James Abbott | VFM 10 | Continue to Develop Effective Communications | New Targeted Cabinet Video Messaging commences | 2021-05-01 | Videos of Councillors Ray Faulkner and George Allen were published in April 21. Video messaging will continue on an ad hoc basis. |  | Fully Achieved | [15 empty] | 1 | Sal Khan | Programmes & Transformation | Value for Money | Leader | L10 | 10
James Abbott | VFM 11 | Continue to Develop Effective Communications | Develop New Communications Strategy | 2021-12-01 |  |  | Not Yet Due | [15 empty] | 3 | Sal Khan | Programmes & Transformation | Value for Money | Leader | L11 | 11
James Abbott | VFM 12 | LGA Peer Review | Work with the LGA to deliver a peer review to another council/s to build up to hosting one in East Staffordshire | 2022-03-01 |  |  | Not Yet Due | [15 empty] | 4 | Andy O'Brien | Corporate & Commercial | Value for Money | Leader | L12 | 12
James Abbott | VFM 13 | Improved Resilience Planning | Complete a Review of our Emergency and Business Continuity Planning approach | 2021-09-01 | Review has commenced, drawing in feedback from recent experiences. |  | On Track to be Achieved | [15 empty] | 2 | Sal Khan | Corporate & Commercial | Value for Money | Leader | L13 | 13
Guy Thornhill | VFM 14 | Investigate Cloud Services | Provide report looking at the benefits/issues with Cloud Computing for ESBC | 2021-12-01 |  |  | Not Yet Due | [15 empty] | 3 | Sal Khan | ICT | Value for Money | Leader | L14 | 14
Guy Thornhill | VFM 15 | ICT Business Support | Continue with strategic support to OWBC – Two update reports | 2022-03-01 | Project is progressing well from ESBC perspective |  | On Track to be Achieved | [15 empty] | 4 | Sal Khan | ICT | Value for Money | Leader | L15 | 15
Guy Thornhill | VFM 16 | ICT Business Support | Complete Desktop refresh | 2022-03-01 | Rollout currently 30% complete |  | On Track to be Achieved | [15 empty] | 4 | Sal Khan | ICT | Value for Money | Leader | L16 | 16
James Abbott | VFM 17 | Review of Council Committees | Complete a Review of Council Committee Functions | 2021-12-01 | Scoping paper and programme of milestones is being collated to ensure a robust review is undertaken considering all relevant opportunities. |  | On Track to be Achieved | [15 empty] | 3 | Sal Khan | Corporate & Commercial | Value for Money | Leader | L17 | 17
Lisa Turner | VFM 18 | Responding to Significant Local Government Finance Changes and Assessing the Impact on the Council’s Financial Position | Activities Throughout the Year Reported in Line with the Timed Responses | 2022-03-01 | Awaiting further developments / consultations from Central Government | n/a | On Track to be Achieved | [15 empty] | 4 | Sal Khan | FMU | Value for Money | Leader | L18 | 18
Lisa Turner | VFM 19 | Set the MTFS for 2022/23 onwards | Set Budget for Council Approval | 2022-02-01 |  |  | Not Yet Due | [15 empty] | 4 | Sal Khan | FMU | Value for Money | Leader | L19 | 19
Lisa Turner | VFM 20 | Having an approved Statement of Accounts | Submit Statement of Accounts to Audit Committee by the earlier Statutory Deadline | (By the statutory deadline) | Accounts submitted to external auditors and the audit is currently underway. | n/a | On Track to be Achieved | [16 empty] | Sal Khan | FMU | Value for Money | Leader | L20 | 20
Lisa Turner | VFM 21 | Continue to Improve Financial Resilience | Review and Refresh Financial Regulations | 2022-03-01 |  |  | Not Yet Due | [15 empty] | 4 | Sal Khan | FMU | Value for Money | Leader | L21 | 21
Lisa Turner | VFM 22 | Continue to Improve Financial Resilience | Review and Refresh Contract Procedure Rules | 2022-03-01 |  |  | Not Yet Due | [15 empty] | 4 | Sal Khan | FMU | Value for Money | Leader | L22 | 22
Linda McDonald | VFM 23 | Increasing Staffing Availability Through Reduced Sickness | Short Term Sickness Days Average: 2.7 days |  | 0.48 days | 2.7 | On Track to be Achieved | [16 empty] | Andy O'Brien | HR, Payroll & Payments | Value for Money | Leader | L23 | 23
Linda McDonald | VFM 24 | Maintain Timely Payment of Creditors | Average Time To Pay Creditors: Within 10 days of receipt of invoice |  | average 8 days | av 10 days | On Track to be Achieved | [16 empty] | Andy O'Brien | HR, Payroll & Payments | Value for Money | Leader | L24 | 24
James Abbott | VFM 25 | Maintain Robust Mechanisms for Contract Managing the Leisure Service Arrangements | Report on the performance of the Leisure Operator on a quarterly basis | 2022-03-01 | Quarterly Performance Report presented to Corporate Management Team, Leader and Deputy Leaders, LAG / LOAG / IAAG and AVFM Scrutiny Committee during May and June 2021. |  | On Track to be Achieved | [15 empty] | 4 | Mark Rizk | Corporate & Commercial | Value for Money | Leisure, Amenities & Tourism | LAT01 | 25
James Abbott | VFM 26 | Work with Leisure Operator to Continue to Provide High Quality Sports Facilities | Replace the Artificial Turf Pitch at Shobnall Leisure Complex* | 2021-08-01 | Contractor has been appointed and the artificial turf has been manufactured. There have been delays beyond the Council's or Contractor's control in the delivery of the turf from overseas with shipment delayed due to the current container crisis. The artificial turf will be replaced as planned, however, anticipated completion is now early September. |  | In Danger of Falling Behind Target | Works to upgrade floodlighting of the pitch to increase performance and energy efficiency as a separate element for the project have been agreed. | [14 empty] | 2 | Mark Rizk | Corporate & Commercial | Value for Money | Leisure, Amenities & Tourism | LAT02 | 26
Michael Hovers | VFM 27 | Procurement of Grounds Maintenance Contractor | Complete the procurement of the Grounds Maintenance contract | 2022-03-01 | Grounds Maintenance has been issued and provider returns are presently being evaluated with a view to awarding in qtr 2 |  | On Track to be Achieved | [15 empty] | 4 | Mark Rizk | Community & Open Spaces | Value for Money | Leisure, Amenities & Tourism | LAT03 | 27
Michael Hovers | VFM 28 | Developing Tourism within the Borough | Provide a first year update on the progress of the Tourism Plan including the investigation of options for a showcase event for local tourism businesses in a post Covid-19 environment | 2021-11-01 |  |  | Not Yet Due | [15 empty] | 3 | Mark Rizk | Community & Open Spaces | Value for Money | Leisure, Amenities & Tourism | LAT04 | 28
Nathan Gallagher | VFM 29 | Improve Awareness of Council Services, Venues and Initiatives | Develop marketing plans for each service area and achieve 85% completion of 21/22 marketing targets | 2022-03-01 | A specific Marketing Plan has been develop for each service area. |  | On Track to be Achieved | [15 empty] | 4 | Mark Rizk | Marketing | Value for Money | Leisure, Amenities & Tourism | LAT05 | 29
Nathan Gallagher | VFM 30 | Improve Awareness of Council Services, Venues and Initiatives | Deliver a minimum of 5 events to promote East Staffordshire and ESBC services and report performance to councillors each quarter* | 2022-03-01 | In this quarter we delivered a Young Trader Market, in support of the National Market Trader Federation Young Traders campaign. The event promote the Market Hall as a destination for developing small and start up businesses. |  | On Track to be Achieved | [15 empty] | 4 | Mark Rizk | Marketing | Value for Money | Leisure, Amenities & Tourism | LAT06 | 30
Nathan Gallagher | VFM 31 | Improve Awareness of Council Services, Venues and Initiatives | Provide marketing support across ESBC departments and develop a minimum of 6 marketing campaigns around key events and projects across the council | 2022-03-01 | In this quarter we delivered a Stay Local campaign aimed at encouraging local residents to support local businesses across East Staffordshire. Also in this period we began rolling our a Be Your Own Boss campaign to encourage small and start up business to trader on our Markets. |  | On Track to be Achieved | [15 empty] | 4 | Mark Rizk | Marketing | Value for Money | Leisure, Amenities & Tourism | LAT07 | 31
Naomi Perry | VFM 32 | Continue to develop SMARTER working practices for Planning | Prepare the ‘Assure’ Migration Project Plan | 2021-06-01 | Report completed in June and considered by CMT on 15th July |  | Fully Achieved | [15 empty] | 1 | Sal Khan | Planning | Value for Money | Regeneration & Planning Policy | RPP01 | 32
Naomi Perry | VFM 33 | Continue to develop SMARTER working practices for Planning | Implement new Online Mapping System Improvements | 2022-03-01 | Progress has been made and on target to be implemented by March 2022 |  | On Track to be Achieved | [15 empty] | 4 | Sal Khan | Planning | Value for Money | Regeneration & Planning Policy | RPP02 | 33
Naomi Perry | VFM 34 | Continuing to inform and improve Planning awareness with Members | At least 2 briefings delivered to elected members during the year | March 2022 | No briefings have been undertaken since March however likely to take place Autumn 2021 and spring 2022 |  | On Track to be Achieved | [15 empty] | 4 | Sal Khan | Planning | Value for Money | Regeneration & Planning Policy | RPP03 | 34
Naomi Perry | VFM 35 | Continuing to inform and improve Planning awareness with Members | Targeted Planning Committee Briefings - 10 throughout the year | March 2022 | 4 provided so far (April, May, June, July) |  | On Track to be Achieved | [15 empty] | 4 | Sal Khan | Planning | Value for Money | Regeneration & Planning Policy | RPP04 | 35
Naomi Perry | VFM 36 | Monitor Local Plan Performance | Authority Monitoring Report Prepared | 2021-12-01 |  |  | On Track to be Achieved | [15 empty] | 3 | Sal Khan | Planning | Value for Money | Regeneration & Planning Policy | RPP05 | 36
Naomi Perry | VFM 37 | Monitor Local Plan Performance | SHLAA completed | 2021-09-01 |  |  | On Track to be Achieved | [15 empty] | 2 | Sal Khan | Planning | Value for Money | Regeneration & Planning Policy | RPP06 | 37
Naomi Perry | VFM 38 | Monitor Local Plan Performance | Consider review of the Local Plan | 2021-10-01 |  |  | On Track to be Achieved | [15 empty] | 3 | Sal Khan | Planning | Value for Money | Regeneration & Planning Policy | RPP07 | 38
Naomi Perry | VFM 39 | New and Refreshed Planning Policies | Publish Infrastructure Funding Statement | 2022-01-01 |  |  | On Track to be Achieved | [15 empty] | 4 | Sal Khan | Planning | Value for Money | Regeneration & Planning Policy | RPP08 | 39
Naomi Perry | VFM 40 | New and Refreshed Planning Policies | S106 Prioritisation Report Approved | 2021-08-01 | Report considered by LDL 26th July 2021 |  | On Track to be Achieved | [15 empty] | 2 | Sal Khan | Planning | Value for Money | Regeneration & Planning Policy | RPP09 | 40
Naomi Perry | VFM 41 | New and Refreshed Planning Policies | S106 Monitoring Fee Report Approved | 2021-08-01 | Report considered by LDL 26th July 2021 |  | On Track to be Achieved | [15 empty] | 2 | Sal Khan | Planning | Value for Money | Regeneration & Planning Policy | RPP10 | 41
Sarah Richardson | VFM 42 | Continue to Maximise Income Through Effective Collection Processes | Collection Rates of Council Tax: 98% (Previously BVPI 9) |  | 29.65% | 98 | On Track to be Achieved | Target is annual | [15 empty] | Sal Khan | Revenues, Benefits & Customer Contacts | Value for Money | Environment & Housing | EH01 | 42
Sarah Richardson | VFM 43 | Continue to Maximise Income Through Effective Collection Processes | Collection Rates of NNDR: 99% (Previously BVPI 10) |  | 33.36% | 99 | On Track to be Achieved | Target is annual. | [15 empty] | Sal Khan | Revenues, Benefits & Customer Contacts | Value for Money | Environment & Housing | EH02 | 43
Sarah Richardson | VFM 44 | Continue to Maximise Income Through Effective Collection Processes: Reduce Former Years Arrears | Former Years Arrears for Council Tax; £2,500,000 |  | 2262619.96 | 2500000 | On Track to be Achieved | Target is annual. | [15 empty] | Sal Khan | Revenues, Benefits & Customer Contacts | Value for Money | Environment & Housing | EH03 | 44
Sarah Richardson | VFM 45 | Continue to Maximise Income Through Effective Collection Processes: Reduce Former Years Arrears | Former Years Arrears for NNDR; £1,500,000 |  | 2088266.62 | 1500000 | On Track to be Achieved | Target is annual. Previous year charges raised since 1 April total £1.3m. Any charges raised for previous years during the current year will impact on the arrears balance outstanding. | [15 empty] | Sal Khan | Revenues, Benefits & Customer Contacts | Value for Money | Environment & Housing | EH04 | 45
Sarah Richardson | VFM 46 | Continue to Maximise Income Through Effective Collection Processes: Reduce Former Years Arrears | Former Years Arrears for Sundry Debts; £80,000 |  | 0 | 80000 | On Track to be Achieved | Target is annual. | [15 empty] | Sal Khan | Revenues, Benefits & Customer Contacts | Value for Money | Environment & Housing | EH05 | 46
Sarah Richardson | VFM 47 | Maintaining excellent customer access to services with face-to-face and telephony enquiries | 99% of CSC and Telephony Team Enquiries Resolved at First Point of Contact |  | 0% | 0 | Not Yet Due | The CSCs have been closed since October 2020. A date for re-opening has not yet been set. | [15 empty] | Sal Khan | Revenues, Benefits & Customer Contacts | Value for Money | Environment & Housing | EH06 | 47
Sarah Richardson | VFM 48 | Maintaining excellent customer access to services with face-to-face and telephony enquiries | Minimum 75% Telephony Team Calls Answered Within 10 Seconds |  | 81% | 75 | On Track to be Achieved | [16 empty] | Sal Khan | Revenues, Benefits & Customer Contacts | Value for Money | Environment & Housing | EH07 | 48
Sarah Richardson | VFM 49 | Continue to Improve the Ways We Provide Benefits to Those Most in Need: | Time Taken to Process Benefit New Claims and Change Events (Previously NI 181) 4.5 days |  | 4.07 days | 4.5 | On Track to be Achieved | [16 empty] | Sal Khan | Revenues, Benefits & Customer Contacts | Value for Money | Environment & Housing | EH08 | 49
Sarah Richardson | VFM 50a | Working Towards the Reduction of Claimant Error Housing Benefit Overpayments (HBOPs): | % of HBOPs Overpayments Recovered During the Year; 90% |  | 125% | 90 | On Track to be Achieved | This is all HBOP payments received (all years) compared to the HBOPs raised during the current year | [15 empty] | Sal Khan | Revenues, Benefits & Customer Contacts | Value for Money | Environment & Housing | EH09 | 50
Sarah Richardson | VFM 50b | Working Towards the Reduction of Claimant Error Housing Benefit Overpayments (HBOPs): | % In Year HBOPs Overpayments Recovered During the Year; 70% |  | 33% | 0.7 | In Danger of Falling Behind Target | This is in-year HBOP payments received for in-year HBOPs raised during the current year. | [15 empty] | Sal Khan | Revenues, Benefits & Customer Contacts | Value for Money | Environment & Housing | EH09 | 51
Sarah Richardson | VFM 50c | Working Towards the Reduction of Claimant Error Housing Benefit Overpayments (HBOPs): | % of HBOPS Processed and on Payment Arrangement; 90% |  | 89% | 0.9 | On Track to be Achieved | [16 empty] | Sal Khan | Revenues, Benefits & Customer Contacts | Value for Money | Environment & Housing | EH09 | 52
Sarah Richardson | VFM 51 | Implement the new Recovery and Write-Off Policy Changes | Revised Policy changes implemented | 2021-04-01 | Implemented 01/04/2021 |  | Fully Achieved | [15 empty] | 1 | Sal Khan | Revenues, Benefits & Customer Contacts | Value for Money | Environment & Housing | EH10 | 53
Sarah Richardson | VFM 52 | Review and develop a new Local Council Tax Reduction Scheme | Local Council Tax Reduction Scheme approved | 2021-12-01 | Not yet due |  | Not Yet Due | [15 empty] | 3 | Sal Khan | Revenues, Benefits & Customer Contacts | Value for Money | Environment & Housing | EH11 | 54
Sarah Richardson | VFM 53 | SMARTER Working in RBCC | Report on automation opportunities within RBCC software | 2021-12-01 | Not yet due |  | Not Yet Due | [15 empty] | 3 | Sal Khan | Revenues, Benefits & Customer Contacts | Value for Money | Environment & Housing | EH12 | 55
Sarah Richardson | VFM 54 | SMARTER Working in RBCC | Report on Operations of the Council’s CSCs | 2021-09-01 | Not yet due |  | Not Yet Due | [15 empty] | 2 | Sal Khan | Revenues, Benefits & Customer Contacts | Value for Money | Environment & Housing | EH13 | 56
Paul Farrer | VFM 55a | Strategic Procurement Activities | Dry Recycling Treatment Procurement concluded | 2022-06-01 | This procurement process was concluded ahead of a report being considered by Cabinet in June 2021. At the meeting it was subsequently decided to postpone the contract award pending the outcome of negotiations with the County Council. Delegated authority granted to Leader/Deputy Leader to finalise the decision by EDR, anticipated in July. |  | Fully Achieved | [15 empty] | 4 | Sal Khan | Environment | Value for Money | Environment & Housing | EH14 | 57
Paul Farrer | VFM 55b | Strategic Procurement Activities | Waste Transfer Station Procurement concluded | February 2022 |  |  | Not Yet Due | [15 empty] | 4 | Sal Khan | Environment | Value for Money | Environment & Housing | EH14 | 58
Paul Farrer | VFM 55c | Strategic Procurement Activities | Garden Waste Treatment Procurement concluded | February 2022 |  |  | Not Yet Due | [15 empty] | 4 | Sal Khan | Environment | Value for Money | Environment & Housing | EH14 | 59
Paul Farrer | VFM 56 | Strategic Procurement Activities | Implementation of new operational fleet | Commencing November 2021 | Orders have been placed for all vehicles and pre-contract/mobilisation meetings are continuing with the Council's new maintenance provider, Specialist Fleet Services.. |  | On Track to be Achieved | [15 empty] | 3 | Sal Khan | Environment | Value for Money | Environment & Housing | EH15 | 60
Paul Farrer | VFM 57 | Strategic Procurement Activities | Installation of new electric charging points for electric fleet | TBA post award | Quotations for charging points have been obtained and will be installed so as to coincide with role out of new fleet. |  | On Track to be Achieved | [16 empty] | Sal Khan | Environment | Value for Money | Environment & Housing | EH16 | 61
Paul Farrer | VFM 58 | Further Development of SMARTER working (Waste Collection) | 90% milestones achieved on the revised Project Plan focusing on Shared Service delivery | 2022-03-01 | SWOT analysis of existing and proposed depot arrangements undertaken by consultant. This will help to identify risks, constraints and next steps. |  | On Track to be Achieved | [15 empty] | 4 | Sal Khan | Environment | Value for Money | Environment & Housing | EH17 | 62
Paul Farrer | VFM 59 | Further Development of SMARTER working (Waste Collection) | Initiate new recycling communication campaign post Scrutiny Review | TBA Post Scrutiny Review | Awaiting full outcome from scrutiny review |  | Not Yet Due | [16 empty] | Sal Khan | Environment | Value for Money | Environment & Housing | EH18 | 63
Paul Farrer | VFM 60 | Further Development of SMARTER working (Street Cleaning) | New Street Cleaning Policies | 2022-03-01 |  |  | Not Yet Due | [15 empty] | 4 | Sal Khan | Environment | Value for Money | Environment & Housing | EH19 | 64
Paul Farrer | VFM 61 | Further Development of SMARTER working (Street Cleaning) | 90% milestones achieved on the revised Project Plan | 2022-03-01 | The software has been installed and the in-cab units are in place. Work is continuing on integrating these with the system provider to ensure performance can be accurately recorded. |  | On Track to be Achieved | [15 empty] | 4 | Sal Khan | Environment | Value for Money | Environment & Housing | EH20 | 65
Paul Farrer | VFM 62 | Respond to Government (Waste) Policy Announcements | Complete responses to Government consultations in line with consultation deadlines |  | Responses submitted for Deposit Return Scheme, Extended Producer Responsibility and Consistency |  | Fully Achieved | [16 empty] | Sal Khan | Environment | Value for Money | Environment & Housing | EH21 | 66
Brett Atkinson | VFM 63 | Delivering Better Services to Support Homelessness | Project to maximise VFM and improve pathways out of supported housing - Project Initiation and approval of approach | Project Initiation by June 2021 | Project approved by Cabinet on 14 June 2021 and initiated shortly thereafter. |  | Fully Achieved | [15 empty] | 1 | Sal Khan | Housing Options | Value for Money | Environment & Housing | EH22 | 67
Rachel Liddle | VFM 64 | Development of the Selective Licensing Scheme | Selective Licensing Fourth Year Review Complete | 2021-11-01 | Report in progress |  | On Track to be Achieved | [15 empty] | 3 | Mark Rizk | Environmental Health | Value for Money | Community & Regulatory Services | CRS01 | 68
Rachel Liddle | VFM 65 | Development of the Selective Licensing Scheme | New Selective Licensing Designation completed | March 2022* | On hold until Covid restrictions are removed to enable final consultation meetings to be undertaken |  | Not Yet Due | [15 empty] | 4 | Mark Rizk | Environmental Health | Value for Money | Community & Regulatory Services | CRS02 | 69
Margaret Woolley | VFM 66 | Review of the Council’s CCTV Provision | Undertake a review of CCTV provision, including a survey of the existing fixed camera provision | 2021-07-01 | Report presented to CMT and groups following survey by SGW Consultancy. Due before Cabinet on 12th July. |  | On Track to be Achieved | [15 empty] | 2 | Mark Rizk | Licensing & Enforcement | Value for Money | Community & Regulatory Services | CRS03 | 70
Margaret Woolley | VFM 67 | Review of the Council’s CCTV Provision | Implement new contract for monitoring and maintenance of fixed CCTV cameras | 2022-02-01 | An extended contract has been implemented until March 2022. |  | On Track to be Achieved | [15 empty] | 4 | Mark Rizk | Licensing & Enforcement | Value for Money | Community & Regulatory Services | CRS04 | 71
Margaret Woolley | VFM 68 | Licensing and Enforcement Activities | Undertake a full review of the licensing fees and charges in accordance with the appropriate legislation | 2021-12-01 | A review will commence shortly. |  | Not Yet Due | [15 empty] | 3 | Mark Rizk | Licensing & Enforcement | Value for Money | Community & Regulatory Services | CRS05 | 72
Margaret Woolley | VFM 69 | Licensing and Enforcement Activities | Undertake a review of the Gambling Act Policy | 2022-02-01 | Not started |  | On Track to be Achieved | [15 empty] | 4 | Mark Rizk | Licensing & Enforcement | Value for Money | Community & Regulatory Services | CRS06 | 73
Margaret Woolley | VFM 70 | Licensing and Enforcement Activities | Update the Taxi License and Private Hire Policy | 2022-03-01 | A review has commenced and changes made to include the DfT Standards. A trade meeting was held to discuss the policy and any other matters the trade had. |  | On Track to be Achieved | [15 empty] | 4 | Mark Rizk | Licensing & Enforcement | Value for Money | Community & Regulatory Services | CRS07 | 74
Margaret Woolley | VFM 71 | Licensing and Enforcement Activities | Conclude the review of taxi ranks in Burton and Uttoxeter | 2022-03-01 | A rank review has been conducted. We are now waiting on the County Council for feedback on our proposals. |  | Not Yet Due | [15 empty] | 4 | Mark Rizk | Licensing & Enforcement | Value for Money | Community & Regulatory Services | CRS08 | 75
Margaret Woolley | VFM 72 | Licensing and Enforcement Activities | Review and update the Councils ‘A’ board policy | 2022-03-01 | A review and update of the Councils policy has begun. We need to establish the route it needs to go down to approve |  | On Track to be Achieved | [15 empty] | 4 | Mark Rizk | Licensing & Enforcement | Value for Money | Community & Regulatory Services | CRS09 | 76
Michael Hovers | VFM 73 | Community & Civil Enforcement (CCE) | Complete a first year review of the use of the Parking App and consider proposals for further development | 2021-08-01 | Report has been written and is due to be received by Cabinet et al in Qtr 2 |  | On Track to be Achieved | [15 empty] | 2 | Mark Rizk | Community & Open Spaces | Value for Money | Community & Regulatory Services | CRS10 | 77
Michael Hovers | CR 01 | Market Hall Development Initiatives | Use targeted events and campaigns to raise the profile of the Market Hall-complete 6 events and initiatives* | 2022-03-01 | Young Traders market has taken place in qtr 1 and a Craft Fair. Events for later in the year have been pencilled at prominent times such as Christmas and negotiations are taking place with providers on the potential delivery of more events. |  | On Track to be Achieved | [15 empty] | 4 | Mark Rizk | Markets | Community Regeneration | Leisure, Amenities & Tourism | LAT08 | 78
Michael Hovers | CR 02 | Market Hall Development Initiatives | Continue to support Market Hall Traders through the post-Covid-19 recovery period and the outcome of the Stronger Towns bid | 2022-03-01 |  |  | Not Yet Due | [15 empty] | 4 | Mark Rizk | Markets | Community Regeneration | Leisure, Amenities & Tourism | LAT09 | 79
Michael Hovers | CR 03 | Market Hall Development Initiatives | Provide an enhanced ‘Christmas offer’ to increase footfall to the town centre and Market Place area of Burton upon Trent during this annual peak period* | 2021-12-01 |  |  | Not Yet Due | [15 empty] | 3 | Mark Rizk | Markets | Community Regeneration | Leisure, Amenities & Tourism | LAT10 | 80
Michael Hovers | CR 04 | Market Hall Development Initiatives | Continue to benchmark Market Hall performance through APSE membership | 2022-03-01 |  |  | Not Yet Due | [15 empty] | 4 | Mark Rizk | Markets | Community Regeneration | Leisure, Amenities & Tourism | LAT11 | 81
Michael Hovers | CR 05 | Increase Capacity at Stapenhill Cemetery | Progress the Cemetery expansion plans including further groundwork investigations | 2022-03-01 | Consultants have produced a Tier 2 report setting out the topography and soil conditions of the proposed extension site. The Environment Agency have been engaged with to review the environmental impact of site |  | Not Yet Due | [15 empty] | 4 | Mark Rizk | Community & Open Spaces | Community Regeneration | Leisure, Amenities & Tourism | LAT12 | 82
James Abbott | CR 06 | Supporting Sports and Leisure Delivery Partners | Identify and respond to appropriate opportunities to support the Birmingham 2022 Commonwealth Games-including the Queen’s Baton Relay and supporting cultural activities | 2022-03-01 | Council officers continue to attend a lead officer group, in relation to the Games. The Council has supported various communications opportunities such as the recruitment of Games volunteers and advertisement of the West Midlands ticket ballot through its website and social media channels. |  | On Track to be Achieved | [15 empty] | 4 | Mark Rizk | Corporate & Commercial | Community Regeneration | Leisure, Amenities & Tourism | LAT13 | 83
James Abbott | CR 07 | Supporting Sports and Leisure Delivery Partners | Support partners in progressing the Uttoxeter Sports Hub aspiration including receipt of six-monthly progress report from partners | 2022-03-01 |  |  | Not Yet Due | [15 empty] | 4 | Mark Rizk | Corporate & Commercial | Community Regeneration | Leisure, Amenities & Tourism | LAT14 | 84
Andrea Smith | CR 08 | Major Planning Applications Determined Within 13 Weeks | Top Quartile as measured against relevant MHCLG figures |  | 10 Applications all within time = 100% |  | On Track to be Achieved | [16 empty] | Sal Khan | Planning | Community Regeneration | Regeneration & Planning Policy | RPP11 | 85
Andrea Smith | CR 09 | Minor Planning Applications Determined Within 8 Weeks | Top Quartile as measured against relevant MHCLG figures |  | 59 Applications of which 54 were within time = 92% |  | On Track to be Achieved | [16 empty] | Sal Khan | Planning | Community Regeneration | Regeneration & Planning Policy | RPP12 | 86
Andrea Smith | CR 10 | Other Planning Applications Determined in 8 Weeks | Top Quartile as measured against relevant MHCLG figures |  | 155 Applications of which 151 were within time - 97% |  | On Track to be Achieved | [16 empty] | Sal Khan | Planning | Community Regeneration | Regeneration & Planning Policy | RPP13 | 87
Naomi Perry | CR 11 | Supporting Neighbourhood Plans | Rolleston Neighbourhood Plan Made | May 2021 (unless Elections are postponed) | Rolleston Neighbourhood Plan Made in May following referendum |  | Fully Achieved | [15 empty] | 1 | Sal Khan | Planning | Community Regeneration | Regeneration & Planning Policy | RPP14 | 88
Naomi Perry | CR 12 | New and Refreshed Planning Policies | Tourism Technical Guide Finalised | 2021-12-01 |  |  | Not Yet Due | [15 empty] | 3 | Sal Khan | Planning | Community Regeneration | Regeneration & Planning Policy | RPP15 | 89
Thomas Deery | CR 13 | Deliver transformative regeneration for Burton upon Trent working in partnership with the Burton Towns Fund board | Agree the Heads of Terms with MHCLG for Burton’s Towns Fund bid | 2021-04-01 | The Heads of Terms for the Towns Fund have been agreed with MHCLG, confirming the allocation and acceptance of £22.8m. |  | Fully Achieved | [15 empty] | 1 | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP16 | 90
Thomas Deery | CR 14 | Deliver transformative regeneration for Burton upon Trent working in partnership with the Burton Towns Fund board | Submit project confirmations and up to 2 shovel ready proposals to MHCLG | 2021-06-01 | Project confirmations were submitted in May 2021 and have been accepted by Government, these identify shovel ready proposals however no proposals will be implemented before April 2022 in order to enable the full completion of the business case and consultation process. |  | Fully Achieved | [15 empty] | 1 | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP17 | 91
Thomas Deery | CR 15 | Deliver transformative regeneration for Burton upon Trent working in partnership with the Burton Towns Fund board | Develop a business case for the High Street Property Intervention project and support strategic partners in developing business cases for the remaining Towns Fund projects | 2021-12-01 | The development of the Project D (High Street) business case is underway with consultation activity taking place during Q2. An approach to programme assurance has also been established whereby other Officers will lead on the co-ordination and support of other partners in developing their business cases. |  | On Track to be Achieved | [15 empty] | 3 | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP18 | 92
James Abbott | CR 16 | Deliver transformative regeneration for Burton upon Trent working in partnership with the Burton Towns Fund board | Submit the Summary Documents for all the Burton Towns Fund projects to MHCLG | 2022-03-01 | Business Case Summary Documents to be submitted following the potential approval of full Business Cases, anticipated to be considered in Quarter 4. |  | Not Yet Due | [15 empty] | 4 | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP19 | 93
Thomas Deery | CR 17 | Support the regeneration of Uttoxeter through the Uttoxeter Masterplan | Following consultation brought forward, review progress against the implementation of the Uttoxeter Masterplan – explore and bid for monies from the levelling up fund | 2021-10-01 | The further stakeholder engagement and public consultation launches in July/August and runs until September, with a minimum consultation period of 6 weeks. The outcome of this process will feed into this update and establish the initial work for a future funding bid. |  | On Track to be Achieved | [15 empty] | 3 | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP20 | 94
Thomas Deery | CR 18 | Support the regeneration of Uttoxeter through the Uttoxeter Masterplan | Work with Staffordshire County Council to develop a sustainable bus and parking strategy for Uttoxeter | 2022-03-01 |  |  | Not Yet Due | [15 empty] | 4 | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP21 | 95
Thomas Deery | CR 19 | Support the delivery of affordable housing on brownfield land through the utilisation of S106 commuted sums | Review and update the Brownfield and Infill Regeneration Strategy in line with new Government guidance and policy | 2022-03-01 |  |  | Not Yet Due | [15 empty] | 4 | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP22 | 96
Thomas Deery | CR 20 | Improve the Washlands as a regional attraction | Undertake a feasibility study to inform the development of a Washlands Visitor Centre | 2021-12-01 | Depending upon the outcome of the consultation process for Towns Fund Project D in Q2, this work could be captured by the feasibility work for Project D. In the meantime, initial conversations have taken place with Staffordshire Wildlife Trust regarding this possible facility. |  | On Track to be Achieved | [15 empty] | 3 | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP23 | 97
Thomas Deery | CR 21 | Improve the Washlands as a regional attraction | Complete the delivery of the Washlands Enhancement Project | 2022-03-01 | The planning permission for the Washlands project was granted in June 2021, which was slightly later than anticipated. Whilst a tender exercise will now be undertaken to commission contractors later in the summer/autumn, some of the works are likely to be at risk during the winter months, particularly between November-February. Therefore, there is a good likelihood that the works will be underway before March 2022, but not completed until the summer of 2022. |  | In Danger of Falling Behind Target | [15 empty] | 4 | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP24 | 98
Thomas Deery | CR 22 | Support economic growth in East Staffordshire | Working with the Worklessness Action Group and local MP, as appropriate, support the delivery of three physical or virtual job fairs | 2022-03-01 | A co-ordinated approach with the local MP has not yet been explored, but this will likely be looked at later in the year once enough time has passed after the easing of COVID-19 restrictions. In the meantime, we continue to work with WAG partners to support virtual job fair activities, more of which will take place later in the year. None have taken place in Q1. |  | On Track to be Achieved | [15 empty] | 4 | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP25 | 99
Thomas Deery | CR 23 | Support economic growth in East Staffordshire | Administer the Small Business Fund grant scheme to support the growth of small businesses and start-ups | 2022-03-01 | There have now been 3 panel meetings where 11 funding applications have been considered and 8 businesses have been approved for funding with £57k committed. |  | On Track to be Achieved | [15 empty] | 4 | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP26 | 100
Thomas Deery | CR 24 | Support economic growth in East Staffordshire | Hold 4 engagement events with Town Centre retailers | 2022-03-01 |  |  | Not Yet Due | [15 empty] | 4 | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP27 | 101
Thomas Deery | CR 25 | Support economic growth in East Staffordshire | Consider creating a Business Improvement District in Uttoxeter | 2022-03-01 |  |  | Not Yet Due | [15 empty] | 4 | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP28 | 102
Thomas Deery | CR 26 | Support economic growth in East Staffordshire | Commission inward investment consultants to drive private investment in Burton | 2021-07-01 | A possible partnership with SCC to support inward investment has been explored and could be taken forward in advance of this target date, however interesting, alternative options have recently presented themselves and so in order to consider these appropriately and afford them enough time, it is recommended that this target date is postponed by one quarter (to October 2021) |  | Not Yet Due | [15 empty] | 2 | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP29 | 103
Naomi Perry | CR 27 | New and Refreshed Planning Policies | Produce Guidance on achieving Biodiversity net gains through Planning | 2022-03-01 |  |  | Not Yet Due | [15 empty] | 4 | Sal Khan | Planning | Community Regeneration | Regeneration & Planning Policy | RPP30 | 104
Naomi Perry | CR 28 | New and Refreshed Planning Policies | Draft Local Sustainable Development (Climate Change SPD) | 2022-03-01 |  |  | Not Yet Due | [15 empty] | 4 | Sal Khan | Planning | Community Regeneration | Regeneration & Planning Policy | RPP31 | 105
Michael Hovers | CR 29 | Partnership Working | Review the Council’s internal procedures and training in support of the Prevent Agenda | 2022-03-01 |  |  | Not Yet Due | [15 empty] | 4 | Mark Rizk | Community & Open Spaces | Community Regeneration | Community & Regulatory Services | CRS11 | 106
Michael Hovers | CR 30 | Partnership Working | Consider the introduction of a Parish Council Forum/other communication channels | 2021-07-01 | Terms of reference for the Parish Council Forum has been agreed and a first virtual meeting is scheduled for early August |  | Fully Achieved | [15 empty] | 2 | Mark Rizk | Community & Open Spaces | Community Regeneration | Community & Regulatory Services | CRS12 | 107
Michael Hovers | EHB 01 | Open Spaces Initiatives | Achieve a minimum of 2 In Bloom gold awards for our In Bloom entries across the Borough* | 2021-09-01 | There is no judging visits in 2021 due COVID. Subsequently, entrants have been preparing portfolios for submission to the Heart of England. |  | On Track to be Achieved | [15 empty] | 2 | Mark Rizk | Community & Open Spaces | Environment and Health & Wellbeing | Leisure, Amenities & Tourism | LAT15 | 108
Michael Hovers | EHB 02 | Open Spaces Initiatives | Provide a first year update report on progress with the Parks Development Plan | 2021-12-01 |  |  | Not Yet Due | [15 empty] | 3 | Mark Rizk | Community & Open Spaces | Environment and Health & Wellbeing | Leisure, Amenities & Tourism | LAT16 | 109
Michael Hovers | EHB 03 | Open Spaces Initiatives | Enter at least 5 of our parks into the ‘It’s Your Neighbourhood Awards’ scheme and achieve a minimum of Bronze Award* | 2021-09-01 | Parks judging took place in Qtr 1 results are expected early September |  | Not Yet Due | [15 empty] | 2 | Mark Rizk | Community & Open Spaces | Environment and Health & Wellbeing | Leisure, Amenities & Tourism | LAT17 | 110
James Abbott | EHB 04 | Supporting Sports and Leisure Delivery Partners | Investigate opportunities to establish and enhanced Play Day event in conjunction with Everyone Active* | 2021-08-01 | The Play Day event was unable to be organised this year due to the ongoing uncertainty around Step 4 guidance, plus the time and resource that would be required to organise such an event. The Council will continue to work with Everyone Active on opportunities for future events. |  | Deferred | There may be further opportunities that could be investigated for the Play Day in 2022 with the Commonwealth games being held within the region. | [14 empty] | 2 | Mark Rizk | Corporate & Commercial | Environment and Health & Wellbeing | Leisure, Amenities & Tourism | LAT18 | 111
James Abbott | EHB 05 | Supporting Sports and Leisure Delivery Partners | Complete a Review of Health & Activity Strategy and Delivery in the Borough | 2022-01-01 | The review has commenced with an initial review of other applicable strategies i.e. Together Active, Sport England and Everyone Active strategies. |  | On Track to be Achieved | [15 empty] | 4 | Mark Rizk | Corporate & Commercial | Environment and Health & Wellbeing | Leisure, Amenities & Tourism | LAT19 | 112
Paul Farrer | EHB 06 | Maintain Performance For Street Cleansing | Litter Detritus Graffiti Fly-posting 0% |  | Not yet due - surveys run April - July |  | Not Yet Due | [16 empty] | Sal Khan | Environment | Environment and Health & Wellbeing | Environment & Housing | EH23 | 113
Paul Farrer | EHB 07 | Maintain Performance On Recycling | Household Waste Recycled and Composted: Upper quartile |  | 46.32% estimated as not al data received | 44 | On Track to be Achieved | [16 empty] | Sal Khan | Environment | Environment and Health & Wellbeing | Environment & Housing | EH24 | 114
Paul Farrer | EHB 08 | Maintain Performance On Waste Reduction | Residual Household Waste Per Household: Upper Quartile |  | 133kg estimated as not all data received | 525kg | On Track to be Achieved | [16 empty] | Sal Khan | Environment | Environment and Health & Wellbeing | Environment & Housing | EH25 | 115
Paul Farrer | EHB 09 | Minimise The Number Of Missed Bin Collections | Number Of Missed Bin Collections: Achieve 99.97% successful bin collections across the Borough | 2022-03-01 | 99.97% |  | On Track to be Achieved | [15 empty] | 4 | Sal Khan | Environment | Environment and Health & Wellbeing | Environment & Housing | EH26 | 116
Brett Atkinson | EHB 10 | Housing Strategy Initiatives: Review the Housing Strategy | Strategy review completed | 2021-12-01 | The strategy continues to be implemented in its current form. |  | Not Yet Due | [15 empty] | 3 | Sal Khan | Housing Options | Environment and Health & Wellbeing | Environment & Housing | EH27 | 117
Brett Atkinson | EHB 11 | Housing Strategy Initiatives: Refresh the Housing Allocations Policy | Approve refreshed Allocations Policy | 2021-12-01 | Initial discussions have taken place with the delivery partner to identify potential improvements. |  | On Track to be Achieved | [15 empty] | 3 | Sal Khan | Housing Options | Environment and Health & Wellbeing | Environment & Housing | EH28 | 118
Brett Atkinson | EHB 12 | Housing Strategy Initiatives: Proactively reducing the number of empty homes in the borough | Produce two performance reports during the year | 2022-03-01 | Work on the contract delivered by Grafton is onging, assisted by a verification exercise to ensure the owners of empty homes understand that Grafton are acting on behalf of the Council. Initial enquiries have been undertaken to identify empty homes which may be suitable for enforced sale. |  | On Track to be Achieved | [15 empty] | 4 | Sal Khan | Housing Options | Environment and Health & Wellbeing | Environment & Housing | EH29 | 119
Brett Atkinson | EHB 13 | Delivering Better Services to Support Homelessness | Average time from appointment to initial decision for homeless applicants of 3 days |  | There were 63 initial decisions taken in the quarter, with an avergae of 0.22 days from appointment to initial decision. | 1 day | On Track to be Achieved | [16 empty] | Sal Khan | Housing Options | Environment and Health & Wellbeing | Environment & Housing | EH30 | 120
Brett Atkinson | EHB 14 | Continue to Maximise Utilisation of Self Contained Temporary Accommodation for Homeless Applicants | Maintain ‘Key to Key’ Void Turnaround to an average of 6 working days |  | Over 5 'key to key' instances, there was a void turnaroound of 31 working days, or 6.2 days on average. | 5.8 days | On Track to be Achieved | [16 empty] | Sal Khan | Housing Options | Environment and Health & Wellbeing | Environment & Housing | EH31 | 121
Rachel Liddle | EHB 15 | Climate Change | Provide a 1st year review of progress made on the Climate Change Action Plan | 2022-02-01 | Action plan is being progressed which will be reflected in the report in due course |  | On Track to be Achieved | [15 empty] | 4 | Mark Rizk | Environmental Health | Environment and Health & Wellbeing | Community & Regulatory Services | CRS13 | 122
Rachel Liddle | EHB 16 | Disabled Facilities Grant Review | Complete Annual Review of Disabled Facilities Grant Service | 2021-12-01 | Report currently in progress |  | On Track to be Achieved | [15 empty] | 3 | Mark Rizk | Environmental Health | Environment and Health & Wellbeing | Community & Regulatory Services | CRS14 | 123
Rachel Liddle | EHB 17 | Partnership working with Trading Standards | To continue to work with Trading Standards on Covid-19 compliance and undertake a focused initiative on tenant fee compliance* | 2022-03-01 | Ongoing Covid Compliance work with Trading Standards. All outbreaks are investigated and enforcement action taken where appropriate. Monthly compliance checks undertaken in businesses during food hygiene inspections and targeted compliance checks in areas of concern such as pubs during Euro matches |  | On Track to be Achieved | [15 empty] | 4 | Mark Rizk | Environmental Health | Environment and Health & Wellbeing | Community & Regulatory Services | CRS15 | 124
Michael Hovers | EHB 18 | Community & Civil Enforcement (CCE) | Launch digitally based content (embracing digital technology) to reach a wider audience, educating residents on issues relating to the main issues reported i.e. fly tipping, dog fouling, littering | 2021-09-01 | Concept art and designs have been prepared. Following feedback from officers the content is to be edited before launching digitally in September |  | On Track to be Achieved | [15 empty] | 2 | Mark Rizk | Community & Open Spaces | Environment and Health & Wellbeing | Community & Regulatory Services | CRS16 | 125
Chloe Brown | EHB 19 | Brewhouse and Civic Function Suite | A minimum programme of 8 events and activities will be scheduled throughout the year to mark the 30th anniversary of the Brewhouse* | March 2022* | 3 Anniversary event/projects taken place so far. 30th Anniversary Artist commission awarded. Online 30 in 30 Campaign launched. First Live performance returned to Brewhouse to mark re-opening and celebrate 30th anniversary with 70% tickets sold. | 8 | On Track to be Achieved | [15 empty] | 4 | Mark Rizk | Brewhouse | Environment and Health & Wellbeing | Community & Regulatory Services | CRS17 | 126
Chloe Brown | EHB 20 | Brewhouse and Civic Function Suite | A programme of outdoor events and associated Arts Development work will be delivered across the Borough as part of 30th anniversary celebrations including a Public Art Trail* | March 2022* | First outdoor pilot event taken place in Stapenhill Gardens on 5 June with over 200 people in attendance over the day. 6 further outdoor events planned July - August 2021. |  | On Track to be Achieved | [15 empty] | 4 | Mark Rizk | Brewhouse | Environment and Health & Wellbeing | Community & Regulatory Services | CRS18 | 127
Chloe Brown | EHB 21 | Brewhouse and Civic Function Suite | Deliver a minimum of 6 online engagement opportunities as part of the digital development of the Brewhouse service | 2022-03-01 | 3 online engagement opportunities currently being delivered: Superspies Online Family Show and Spy related crafty activities for May Half Term. 20 families took part. Weekly Once Upon a Wednesday storytelling sessions taking place. Weekly Wellness workshops taking place - offering artistic skills development - sessions have been fully subscribed with 25 participants each week. | 6 | On Track to be Achieved | [15 empty] | 4 | Mark Rizk | Brewhouse | Environment and Health & Wellbeing | Community & Regulatory Services | CRS19 | 128
Chloe Brown | EHB 22 | Brewhouse and Civic Function Suite | Proposals for implementing a new model for the delivery of the Brewhouse, Arts and Town Hall (BATH) service that responds to Local and National initiatives such as the Stronger Towns Fund and Arts Council England will be delivered | 2022-03-01 | Initial work has begun. Awaiting update from Stronger Towns Fund next stage. Engaged Bob Rushton via grant funding from Arts Council to develop Programming Strategy and a Vision Statement for the Service. |  | On Track to be Achieved | [15 empty] | 4 | Mark Rizk | Brewhouse | Environment and Health & Wellbeing | Community & Regulatory Services | CRS20 | 129
Update not provided
Fully Achieved
Numerical Outturn Within 5% Tolerance
Numerical Outturn Within 10% Tolerance
Target Partially Met
Off Target
Completed Significantly After Target Deadline
Completion Date Within Reasonable Tolerance
Deferred
Deleted
Fully Achieved
On Track to be Achieved
In Danger of Falling Behind Target
Off Target
Completed Behind Schedule
Deleted
Not Yet Due
Update Not Provided
Deferred

## Q1 Summary
Click here to return to index page
Quarter One (2021/22) | Green |  | Amber |  | Red
| Number of Indicators | Percentage | Number of Indicators | Percentage | Number of Indicators | Percentage
Overall Performance
All due targets | 88 | 96.7% | 3 | 3.297% | 0 | 0%
Corporate Priority
Value for Money Council | 57 | 96.61% | 2 | 3.39% | 0 | 0%
Environment and Health & Well Being | 0 | 0% | 0 | 0% | 0 | 0%
Community Regeneration | 0 | 0% | 0 | 0% | 0 | 0%
Portfolio
Leader | 18 | 100% | 0 | 0% | 0 | 0%
Environment & Housing | 24 | 96% | 1 | 4% | 0 | 0%
Leisure, Amenities & Tourism | 9 | 90% | 1 | 10% | 0 | 0%
Regeneration & Planning Policy | 21 | 95.45% | 1 | 4.545% | 0 | 0%
Community and Regulatory Services | 16 | 100% | 0 | 0% | 0 | 0%

## Q2 Summary (hidden)
Click here to return to index page
Quarter Two (2020/21) | Green |  | Amber |  | Red
| Number of Indicators | Percentage | Number of Indicators | Percentage | Number of Indicators | Percentage
Overall Performance
All due targets | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Corporate Priority
Value for Money Council | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Environment and Health & Well Being | 0 | 0% | 0 | 0% | 0 | 0%
Community Regeneration | 0 | 0% | 0 | 0% | 0 | 0%
Portfolio
Leader | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Environment & Housing | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Leisure, Culture & Tourism | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Regeneration & Planning Policy | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Regulatory & Community Support | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!

## Q3 Summary (hidden)
Click here to return to index page
Quarter Three (2020/21) | Green |  | Amber |  | Red
| Number of Indicators | Percentage | Number of Indicators | Percentage | Number of Indicators | Percentage
Overall Performance
All due targets | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Corporate Priority
Value for Money Council | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Environment and Health & Well Being | 0 | 0% | 0 | 0% | 0 | 0%
Community Regeneration | 0 | 0% | 0 | 0% | 0 | 0%
Portfolio
Leader | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Environment & Housing | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Leisure, Amenities & Tourism | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Regeneration & Planning Policy | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Community & Regulatory Services | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!

## Q4 Summary (hidden)
Click here to return to index page
End of Year 2020/21 | Green |  | Amber |  | Red
| Number of Indicators | Percentage | Number of Indicators | Percentage | Number of Indicators | Percentage
Overall Performance
All due targets | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Corporate Priority
Value for Money Council | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Environment and Health & Well Being | 0 | 0% | 0 | 0% | 0 | 0%
Community Regeneration | 0 | 0% | 0 | 0% | 0 | 0%
Portfolio
Leader | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Environment & Housing | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Leisure, Amenities & Tourism | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Regeneration & Planning Policy | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Community & Regulatory Services | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!

## 2a. % By Priority
QUARTER ONE (April - June 2021) | [5 empty] | QUARTER TWO (July - Sept 2021) | [5 empty] | QUARTER THREE (Oct - Dec 2021) | [5 empty] | QUARTER FOUR (Jan - Mar 2022)
ALL TARGETS | [5 empty] | ALL TARGETS | [5 empty] | ALL TARGETS | [5 empty] | ALL TARGETS
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | 14 | 10.85% | 68.22% | 15.38% | 96.7% | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
On Track to be Achieved | 74 | 57.36% |  | 81.32% |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | Numerical Outturn Within 5% Tolerance | 0 | #DIV/0! |  | #DIV/0!
In Danger of Falling Behind Target | 3 | 2.326% | 2.326% | 3.297% | 3.297% | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Numerical Outturn Within 10% Tolerance | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[18 empty] | Target Partially Met | 0 | #DIV/0! |  | #DIV/0!
[18 empty] | Completion Date Within Reasonable Tolerance | 0 | #DIV/0! |  | #DIV/0!
Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Significantly After Target Deadline | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0!
Not yet due to be reported | 37 | 28.68% | 28.68% |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0!
Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0!
Deferred | 1 | 0.7752% | 0.7752% |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0!
Deleted | 0 | 0% | 0% |  |  | Deleted | 0 | #DIV/0! | #DIV/0! |  |  | Deleted | 0 | #DIV/0! | #DIV/0! |  |  | Deleted | 0 | #DIV/0! | #DIV/0!
Totals | 129 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0
Due to be Reported | 91 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0
VALUE FOR MONEY | [5 empty] | VALUE FOR MONEY | [5 empty] | VALUE FOR MONEY | [5 empty] | VALUE FOR MONEY COUNCIL
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | 10 | 12.99% | 74.03% | 16.95% | 96.61% | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
On Track to be Achieved | 47 | 61.04% |  | 79.66% |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | Numerical Outturn Within 5% Tolerance | 0 | #DIV/0! |  | #DIV/0!
In Danger of Falling Behind Target | 2 | 2.597% | 2.597% | 3.39% | 3.39% | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Numerical Outturn Within 10% Tolerance | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[18 empty] | Target Partially Met | 0 | #DIV/0! |  | #DIV/0!
[18 empty] | Completion Date Within Reasonable Tolerance | 0 | #DIV/0! |  | #DIV/0!
Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Significantly After Target Deadline | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0!
Not yet due to be reported | 18 | 23.38% | 23.38% |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0!
Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0!
Deferred | 0 | 0% | 0% |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0!
Deleted | 0 | 0% | 0% |  |  | Deleted | 0 | #DIV/0! | #DIV/0! |  |  | Deleted | 0 | #DIV/0! | #DIV/0! |  |  | Deleted | 0 | #DIV/0! | #DIV/0!
Totals | 77 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0
Due to be Reported | 59 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0

## 2b. Charts by Priority (hidden)
Charts by Corporate Priority | Please note that all charts shown below can be amended to be displayed in alternative styles. Please right click on the relevant chart, select "change chart type" and choose your preferred chart option.
Back to index
|  | Back to index | Back to index | Back to index | Back to index
OVERALL PERFORMANCE
[8 empty] | Q1 | Q2 | Q3 | Q4
[7 empty] | Green | 96.7% | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | Amber | 3.297% | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | Red | 0% | #DIV/0! | #DIV/0! | #DIV/0!
|  | Back to index | Back to index | Back to index | Back to index
VALUE FOR MONEY COUNCIL
[8 empty] | Q1 | Q2 | Q3 | Q4
[7 empty] | Green | 96.61% | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | Amber | 3.39% | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | Red | 0% | #DIV/0! | #DIV/0! | #DIV/0!
|  | Back to index | Back to index | Back to index | Back to index
ENVIRONMENT AND HEALTH & WELL BEING
[8 empty] | Q1 | Q2 | Q3 | Q4
[7 empty] | Green | 0% | 0% | 0% | 0%
[7 empty] | Amber | 0% | 0% | 0% | 0%
[7 empty] | Red | 0% | 0% | 0% | 0%
|  | Back to index | Back to index | Back to index |  | Back to index
COMMUNITY REGENERATION
[8 empty] | Q1 | Q2 | Q3 | Q4
[7 empty] | Green | 0% | 0% | 0% | 0%
[7 empty] | Amber | 0% | 0% | 0% | 0%
[7 empty] | Red | 0% | 0% | 0% | 0%

## 3a. % by Portfolio (hidden)
QUARTER ONE (April - June 2021) | [5 empty] | QUARTER TWO (July - Sept 2021) | [5 empty] | QUARTER THREE (Oct - Dec 2021) | [5 empty] | QUARTER FOUR (Jan - Mar 2022)
LEADER | [5 empty] | LEADER | [5 empty] | LEADER | [5 empty] | LEADER
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | 5 | 20.83% | 75% | 27.78% | 100% | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
On Track to be Achieved | 13 | 54.17% |  | 72.22% |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | Numerical Outturn Within 5% Tolerance | 0 | #DIV/0! |  | #DIV/0!
In Danger of Falling Behind Target | 0 | 0% | 0% | 0% | 0% | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Numerical Outturn Within 10% Tolerance | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[18 empty] | Target Partially Met | 0 | #DIV/0! |  | #DIV/0!
[18 empty] | Completion Date Within Reasonable Tolerance | 0 | #DIV/0! |  | #DIV/0!
Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Significantly After Target Deadline | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0!
Not yet due to be reported | 6 | 25% | 25% |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0!
Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0!
Deferred | 0 | 0% | 0% |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0!
Deleted | 0 | 0% | 0% |  |  | Deleted | 0 | #DIV/0! | #DIV/0! |  |  | Deleted | 0 | #DIV/0! | #DIV/0! |  |  | Deleted | 0 | #DIV/0! | #DIV/0!
Totals | 24 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0
Due to be Reported | 18 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0
ENVIRONMENT & HOUSING | [5 empty] | ENVIRONMENT & HOUSING | [5 empty] | ENVIRONMENT & HOUSING | [5 empty] | ENVIRONMENT & HOUSING
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | 4 | 11.43% | 68.57% | 16% | 96% | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
On Track to be Achieved | 20 | 57.14% |  | 80% |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | Numerical Outturn Within 5% Tolerance | 0 | #DIV/0! |  | #DIV/0!
In Danger of Falling Behind Target | 1 | 2.857% | 2.857% | 4% | 4% | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Numerical Outturn Within 10% Tolerance | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[18 empty] | Target Partially Met | 0 | #DIV/0! |  | #DIV/0!
[18 empty] | Completion Date Within Reasonable Tolerance | 0 | #DIV/0! |  | #DIV/0!
Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Significantly After Target Deadline | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0!
Not yet due to be reported | 10 | 28.57% | 28.57% |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0!
Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0!
Deferred | 0 | 0% | 0% |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0!
Deleted | 0 | 0% | 0% |  |  | Deleted | 0 | #DIV/0! | #DIV/0! |  |  | Deleted | 0 | #DIV/0! | #DIV/0! |  |  | Deleted | 0 | #DIV/0! | #DIV/0!
Totals | 35 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0
Due to be Reported | 25 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0
LEISURE, AMENITIES & TOURISM | [5 empty] | LEISURE, AMENITIES & TOURISM | [5 empty] | LEISURE, AMENITIES & TOURISM | [5 empty] | LEISURE, AMENITIES & TOURISM
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | 0 | 0% | 47.37% | 0% | 90% | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
On Track to be Achieved | 9 | 47.37% |  | 90% |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | Numerical Outturn Within 5% Tolerance | 0 | #DIV/0! |  | #DIV/0!
In Danger of Falling Behind Target | 1 | 5.263% | 5.263% | 10% | 10% | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Numerical Outturn Within 10% Tolerance | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[18 empty] | Target Partially Met | 0 | #DIV/0! |  | #DIV/0!
[18 empty] | Completion Date Within Reasonable Tolerance | 0 | #DIV/0! |  | #DIV/0!
Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Significantly After Target Deadline | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0!
Not yet due to be reported | 8 | 42.11% | 42.11% |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0!
Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0!
Deferred | 1 | 5.263% | 5.263% |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0!
Deleted | 0 | 0% | 0% |  |  | Deleted | 0 | #DIV/0! | #DIV/0! |  |  | Deleted | 0 | #DIV/0! | #DIV/0! |  |  | Deleted | 0 | #DIV/0! | #DIV/0!
Totals | 19 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0
Due to be Reported | 10 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0
REGENERATION & PLANNING POLICY | [5 empty] | REGENERATION & PLANNING POLICY | [5 empty] | REGENERATION & PLANNING POLICY | [5 empty] | REGENERATION & PLANNING POLICY
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | 4 | 12.9% | 67.74% | 18.18% | 95.45% | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
On Track to be Achieved | 17 | 54.84% |  | 77.27% |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | Numerical Outturn Within 5% Tolerance | 0 | #DIV/0! |  | #DIV/0!
In Danger of Falling Behind Target | 1 | 3.226% | 3.226% | 4.545% | 4.545% | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Numerical Outturn Within 10% Tolerance | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[18 empty] | Target Partially Met | 0 | #DIV/0! |  | #DIV/0!
[18 empty] | Completion Date Within Reasonable Tolerance | 0 | #DIV/0! |  | #DIV/0!
Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Significantly After Target Deadline | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0!
Not yet due to be reported | 9 | 29.03% | 29.03% |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0!
Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0!
Deferred | 0 | 0% | 0% |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0!
Deleted | 0 | 0% | 0% |  |  | Deleted | 0 | #DIV/0! | #DIV/0! |  |  | Deleted | 0 | #DIV/0! | #DIV/0! |  |  | Deleted | 0 | #DIV/0! | #DIV/0!
Totals | 31 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0
Due to be Reported | 22 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0
COMMUNITY & REGULATORY SERVICES | [5 empty] | COMMUNITY & REGULATORY SERVICES | [5 empty] | COMMUNITY & REGULATORY SERVICES | [5 empty] | COMMUNITY & REGULATORY SERVICES
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | 1 | 5% | 80% | 6.25% | 100% | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
On Track to be Achieved | 15 | 75% |  | 93.75% |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | Numerical Outturn Within 5% Tolerance | 0 | #DIV/0! |  | #DIV/0!
In Danger of Falling Behind Target | 0 | 0% | 0% | 0% | 0% | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Numerical Outturn Within 10% Tolerance | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[18 empty] | Target Partially Met | 0 | #DIV/0! |  | #DIV/0!
[18 empty] | Completion Date Within Reasonable Tolerance | 0 | #DIV/0! |  | #DIV/0!
Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Significantly After Target Deadline | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0!
Not yet due to be reported | 4 | 20% | 20% |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0!
Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0!
Deferred | 0 | 0% | 0% |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0!
Deleted | 0 | 0% | 0% |  |  | Deleted | 0 | #DIV/0! | #DIV/0! |  |  | Deleted | 0 | #DIV/0! | #DIV/0! |  |  | Deleted | 0 | #DIV/0! | #DIV/0!
Totals | 20 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0
Due to be Reported | 16 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0

## 3b. Charts by Portfolio (hidden)
Charts by Portfolio | Please note that all charts shown below can be amended to be displayed in alternative styles. Please right click on the relevant chart, select "change chart type" and choose your preferred chart option.
|  | Back to index | Back to index | Back to index | Back to index
LEADER OF THE COUNCIL
[7 empty] | Q1 | Q2 | Q3 | Q4
[6 empty] | Green | 100% | #DIV/0! | #DIV/0! | #DIV/0!
[6 empty] | Amber | 0% | #DIV/0! | #DIV/0! | #DIV/0!
[6 empty] | Red | 0% | #DIV/0! | #DIV/0! | #DIV/0!
|  | Back to index | Back to index | Back to index | Back to index
ENVIRONMENT & HOUSING
[7 empty] | Q1 | Q2 | Q3 | Q4
[6 empty] | Green | 96% | #DIV/0! | #DIV/0! | #DIV/0!
[6 empty] | Amber | 4% | #DIV/0! | #DIV/0! | #DIV/0!
[6 empty] | Red | 0% | #DIV/0! | #DIV/0! | #DIV/0!
|  | Back to index | Back to index | Back to index | Back to index
LEISURE, CULTURE & TOURISM
[7 empty] | Q1 | Q2 | Q3 | Q4
[6 empty] | Green | 90% | #DIV/0! | #DIV/0! | #DIV/0!
[6 empty] | Amber | 10% | #DIV/0! | #DIV/0! | #DIV/0!
[6 empty] | Red | 0% | #DIV/0! | #DIV/0! | #DIV/0!
|  | Back to index | Back to index | Back to index | Back to index
REGENERATION & PLANNING POLICY
[7 empty] | Q1 | Q2 | Q3 | Q4
[6 empty] | Green | 95.45% | #DIV/0! | #DIV/0! | #DIV/0!
[6 empty] | Amber | 4.545% | #DIV/0! | #DIV/0! | #DIV/0!
[6 empty] | Red | 0% | #DIV/0! | #DIV/0! | #DIV/0!
|  | Back to index | Back to index | Back to index | Back to index
REGULATORY & COMMUNITY SUPPORT
[7 empty] | Q1 | Q2 | Q3 | Q4
[6 empty] | Green | 100% | #DIV/0! | #DIV/0! | #DIV/0!
[6 empty] | Amber | 0% | #DIV/0! | #DIV/0! | #DIV/0!
[6 empty] | Red | 0% | #DIV/0! | #DIV/0! | #DIV/0!
|  | Back to index | Back to index | Back to index | Back to index
REGULATORY SERVICES
[7 empty] | Q1 | Q2 | Q3 | Q4
[6 empty] | Green | 0% | 0% | 0% | 0%
[6 empty] | Amber | 0% | 0% | 0% | 0%
[6 empty] | Red | 0% | 0% | 0% | 0%
|  | Back to index | Back to index | Back to index | Back to index
|  | Back to index | Back to index | Back to index | Back to index

## 4. Status Tracking (hidden)
Back to index
CP Ref | Measures | Target 2019/20 | Quarter 1 On track? (R/A/G) | Direction of Travel From Q1 to Q2 | Quarter 2 On track? (R/A/G) | Direction of Travel From Q2 to Q3 | Quarter 3 On track? (R/A/G) | Direction of Travel From Q3 to Q4 | Quarter 4 Achieved? (R/A/G)
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! | Ü
VFM 01 | Successful Delivery of Elections | Successfully Deliver Staffordshire County Council Elections | Fully Achieved |  | 0 |  | 0 |  | 0 | Ý |  | è
VFM 02 | Successful Delivery of Elections | Successfully Deliver PFCC Election as PARO with all constituent authorities submitting returns by 11 May | Fully Achieved |  | 0 |  | 0 |  | 0 | Þ |  | ê
VFM 03 | Implementation of Boundary Review Outcomes | Prepare for amended boundaries and complete Polling Place Review | On Track to be Achieved |  | 0 |  | 0 |  | 0 | n/a | ê
VFM 04 | Embracing Digital Opportunities | Maintain GeoPlaces Gold Standard in ESBC related categories | On Track to be Achieved |  | 0 |  | 0 |  | 0 |  | é
VFM 05 | Embracing Digital Opportunities | Establish a process for reviewing digital services that begins by identifying the intended outcome, designing the process and considering the technology most suitable to deliver that outcome | On Track to be Achieved |  | 0 |  | 0 |  | 0 |  | è
VFM 06 | Embracing Digital Opportunities | Implement Phase 1 of the UPRN project | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 07 | Embracing Digital Opportunities | Complete Feasibility Study investigating the possibility of introducing online customer accounts | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 08 | Continue to Develop Effective Communications | Implement Corporate E-Newsletter solution | Fully Achieved |  | 0 |  | 0 |  | 0
VFM 09 | Continue to Develop Effective Communications | Leader’s Blog live on the Council Website | Fully Achieved |  | 0 |  | 0 |  | 0
VFM 10 | Continue to Develop Effective Communications | New Targeted Cabinet Video Messaging commences | Fully Achieved |  | 0 |  | 0 |  | 0
VFM 11 | Continue to Develop Effective Communications | Develop New Communications Strategy | Not Yet Due |  | 0 |  | 0 |  | 0
VFM 12 | LGA Peer Review | Work with the LGA to deliver a peer review to another council/s to build up to hosting one in East Staffordshire | Not Yet Due |  | 0 |  | 0 |  | 0
VFM 13 | Improved Resilience Planning | Complete a Review of our Emergency and Business Continuity Planning approach | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 14 | Investigate Cloud Services | Provide report looking at the benefits/issues with Cloud Computing for ESBC | Not Yet Due |  | 0 |  | 0 |  | 0
VFM 15 | ICT Business Support | Continue with strategic support to OWBC – Two update reports | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 16 | ICT Business Support | Complete Desktop refresh | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 17 | Review of Council Committees | Complete a Review of Council Committee Functions | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 18 | Responding to Significant Local Government Finance Changes and Assessing the Impact on the Council’s Financial Position | Activities Throughout the Year Reported in Line with the Timed Responses | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 19 | Set the MTFS for 2022/23 onwards | Set Budget for Council Approval | Not Yet Due |  | 0 |  | 0 |  | 0
VFM 20 | Having an approved Statement of Accounts | Submit Statement of Accounts to Audit Committee by the earlier Statutory Deadline | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 21 | Continue to Improve Financial Resilience | Review and Refresh Financial Regulations | Not Yet Due |  | 0 |  | 0 |  | 0
VFM 22 | Continue to Improve Financial Resilience | Review and Refresh Contract Procedure Rules | Not Yet Due |  | 0 |  | 0 |  | 0
VFM 23 | Increasing Staffing Availability Through Reduced Sickness | Short Term Sickness Days Average: 2.7 days | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 24 | Maintain Timely Payment of Creditors | Average Time To Pay Creditors: Within 10 days of receipt of invoice | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 25 | Maintain Robust Mechanisms for Contract Managing the Leisure Service Arrangements | Report on the performance of the Leisure Operator on a quarterly basis | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 26 | Work with Leisure Operator to Continue to Provide High Quality Sports Facilities | Replace the Artificial Turf Pitch at Shobnall Leisure Complex* | In Danger of Falling Behind Target |  | 0 |  | 0 |  | 0
VFM 27 | Procurement of Grounds Maintenance Contractor | Complete the procurement of the Grounds Maintenance contract | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 28 | Developing Tourism within the Borough | Provide a first year update on the progress of the Tourism Plan including the investigation of options for a showcase event for local tourism businesses in a post Covid-19 environment | Not Yet Due |  | 0 |  | 0 |  | 0
VFM 29 | Improve Awareness of Council Services, Venues and Initiatives | Develop marketing plans for each service area and achieve 85% completion of 21/22 marketing targets | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 30 | Improve Awareness of Council Services, Venues and Initiatives | Deliver a minimum of 5 events to promote East Staffordshire and ESBC services and report performance to councillors each quarter* | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 31 | Improve Awareness of Council Services, Venues and Initiatives | Provide marketing support across ESBC departments and develop a minimum of 6 marketing campaigns around key events and projects across the council | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 32 | Continue to develop SMARTER working practices for Planning | Prepare the ‘Assure’ Migration Project Plan | Fully Achieved |  | 0 |  | 0 |  | 0
VFM 33 | Continue to develop SMARTER working practices for Planning | Implement new Online Mapping System Improvements | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 34 | Continuing to inform and improve Planning awareness with Members | At least 2 briefings delivered to elected members during the year | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 35 | Continuing to inform and improve Planning awareness with Members | Targeted Planning Committee Briefings - 10 throughout the year | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 36 | Monitor Local Plan Performance | Authority Monitoring Report Prepared | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 37 | Monitor Local Plan Performance | SHLAA completed | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 38 | Monitor Local Plan Performance | Consider review of the Local Plan | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 39 | New and Refreshed Planning Policies | Publish Infrastructure Funding Statement | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 40 | New and Refreshed Planning Policies | S106 Prioritisation Report Approved | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 41 | New and Refreshed Planning Policies | S106 Monitoring Fee Report Approved | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 42 | Continue to Maximise Income Through Effective Collection Processes | Collection Rates of Council Tax: 98% (Previously BVPI 9) | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 44 | Continue to Maximise Income Through Effective Collection Processes: Reduce Former Years Arrears | Former Years Arrears for Council Tax; £2,500,000 | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 45 | Continue to Maximise Income Through Effective Collection Processes: Reduce Former Years Arrears | Former Years Arrears for NNDR; £1,500,000 | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 46 | Continue to Maximise Income Through Effective Collection Processes: Reduce Former Years Arrears | Former Years Arrears for Sundry Debts; £80,000 | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 47 | Maintaining excellent customer access to services with face-to-face and telephony enquiries | 99% of CSC and Telephony Team Enquiries Resolved at First Point of Contact | Not Yet Due |  | 0 |  | 0 |  | 0
VFM 48 | Maintaining excellent customer access to services with face-to-face and telephony enquiries | Minimum 75% Telephony Team Calls Answered Within 10 Seconds | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 49 | Continue to Improve the Ways We Provide Benefits to Those Most in Need: | Time Taken to Process Benefit New Claims and Change Events (Previously NI 181) 4.5 days | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 50a | Working Towards the Reduction of Claimant Error Housing Benefit Overpayments (HBOPs): | % of HBOPs Overpayments Recovered During the Year; 90% | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 51 | Implement the new Recovery and Write-Off Policy Changes | Revised Policy changes implemented | Fully Achieved |  | 0 |  | 0 |  | 0
VFM 52 | Review and develop a new Local Council Tax Reduction Scheme | Local Council Tax Reduction Scheme approved | Not Yet Due |  | 0 |  | 0 |  | 0
VFM 53 | SMARTER Working in RBCC | Report on automation opportunities within RBCC software | Not Yet Due |  | 0 |  | 0 |  | 0
VFM 54 | SMARTER Working in RBCC | Report on Operations of the Council’s CSCs | Not Yet Due |  | 0 |  | 0 |  | 0
VFM 55a | Strategic Procurement Activities | Dry Recycling Treatment Procurement concluded | Fully Achieved |  | 0 |  | 0 |  | 0
VFM 56 | Strategic Procurement Activities | Implementation of new operational fleet | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 57 | Strategic Procurement Activities | Installation of new electric charging points for electric fleet | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 58 | Further Development of SMARTER working (Waste Collection) | 90% milestones achieved on the revised Project Plan focusing on Shared Service delivery | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 59 | Further Development of SMARTER working (Waste Collection) | Initiate new recycling communication campaign post Scrutiny Review | Not Yet Due |  | 0 |  | 0 |  | 0
VFM 60 | Further Development of SMARTER working (Street Cleaning) | New Street Cleaning Policies | Not Yet Due |  | 0 |  | 0 |  | 0
VFM 61 | Further Development of SMARTER working (Street Cleaning) | 90% milestones achieved on the revised Project Plan | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 62 | Respond to Government (Waste) Policy Announcements | Complete responses to Government consultations in line with consultation deadlines | Fully Achieved |  | 0 |  | 0 |  | 0
VFM 63 | Delivering Better Services to Support Homelessness | Project to maximise VFM and improve pathways out of supported housing - Project Initiation and approval of approach | Fully Achieved |  | 0 |  | 0 |  | 0
VFM 64 | Development of the Selective Licensing Scheme | Selective Licensing Fourth Year Review Complete | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 65 | Development of the Selective Licensing Scheme | New Selective Licensing Designation completed | Not Yet Due |  | 0 |  | 0 |  | 0
VFM 66 | Review of the Council’s CCTV Provision | Undertake a review of CCTV provision, including a survey of the existing fixed camera provision | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 67 | Review of the Council’s CCTV Provision | Implement new contract for monitoring and maintenance of fixed CCTV cameras | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 68 | Licensing and Enforcement Activities | Undertake a full review of the licensing fees and charges in accordance with the appropriate legislation | Not Yet Due |  | 0 |  | 0 |  | 0
VFM 69 | Licensing and Enforcement Activities | Undertake a review of the Gambling Act Policy | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 70 | Licensing and Enforcement Activities | Update the Taxi License and Private Hire Policy | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM 71 | Licensing and Enforcement Activities | Conclude the review of taxi ranks in Burton and Uttoxeter | Not Yet Due |  | 0 |  | 0 |  | 0
VFM 73 | Community & Civil Enforcement (CCE) | Complete a first year review of the use of the Parking App and consider proposals for further development | On Track to be Achieved |  | 0 |  | 0 |  | 0
CR 03 | Market Hall Development Initiatives | Provide an enhanced ‘Christmas offer’ to increase footfall to the town centre and Market Place area of Burton upon Trent during this annual peak period* | Not Yet Due |  | 0 |  | 0 |  | 0
CR 05 | Increase Capacity at Stapenhill Cemetery | Progress the Cemetery expansion plans including further groundwork investigations | Not Yet Due |  | 0 |  | 0 |  | 0
CR 06 | Supporting Sports and Leisure Delivery Partners | Identify and respond to appropriate opportunities to support the Birmingham 2022 Commonwealth Games-including the Queen’s Baton Relay and supporting cultural activities | On Track to be Achieved |  | 0 |  | 0 |  | 0
CR 09 | Minor Planning Applications Determined Within 8 Weeks | Top Quartile as measured against relevant MHCLG figures | On Track to be Achieved |  | 0 |  | 0 |  | 0
CR 10 | Other Planning Applications Determined in 8 Weeks | Top Quartile as measured against relevant MHCLG figures | On Track to be Achieved |  | 0 |  | 0 |  | 0
CR 11 | Supporting Neighbourhood Plans | Rolleston Neighbourhood Plan Made | Fully Achieved |  | 0 |  | 0 |  | 0
CR 12 | New and Refreshed Planning Policies | Tourism Technical Guide Finalised | Not Yet Due |  | 0 |  | 0 |  | 0
CR 13 | Deliver transformative regeneration for Burton upon Trent working in partnership with the Burton Towns Fund board | Agree the Heads of Terms with MHCLG for Burton’s Towns Fund bid | Fully Achieved |  | 0 |  | 0 |  | 0
CR 14 | Deliver transformative regeneration for Burton upon Trent working in partnership with the Burton Towns Fund board | Submit project confirmations and up to 2 shovel ready proposals to MHCLG | Fully Achieved |  | 0 |  | 0 |  | 0
CR 15 | Deliver transformative regeneration for Burton upon Trent working in partnership with the Burton Towns Fund board | Develop a business case for the High Street Property Intervention project and support strategic partners in developing business cases for the remaining Towns Fund projects | On Track to be Achieved |  | 0 |  | 0 |  | 0
CR 16 | Deliver transformative regeneration for Burton upon Trent working in partnership with the Burton Towns Fund board | Submit the Summary Documents for all the Burton Towns Fund projects to MHCLG | Not Yet Due |  | 0 |  | 0 |  | 0
CR 17 | Support the regeneration of Uttoxeter through the Uttoxeter Masterplan | Following consultation brought forward, review progress against the implementation of the Uttoxeter Masterplan – explore and bid for monies from the levelling up fund | On Track to be Achieved |  | 0 |  | 0 |  | 0
CR 18 | Support the regeneration of Uttoxeter through the Uttoxeter Masterplan | Work with Staffordshire County Council to develop a sustainable bus and parking strategy for Uttoxeter | Not Yet Due |  | 0 |  | 0 |  | 0
CR 19 | Support the delivery of affordable housing on brownfield land through the utilisation of S106 commuted sums | Review and update the Brownfield and Infill Regeneration Strategy in line with new Government guidance and policy | Not Yet Due |  | 0 |  | 0 |  | 0
CR 20 | Improve the Washlands as a regional attraction | Undertake a feasibility study to inform the development of a Washlands Visitor Centre | On Track to be Achieved |  | 0 |  | 0 |  | 0
CR 22 | Support economic growth in East Staffordshire | Working with the Worklessness Action Group and local MP, as appropriate, support the delivery of three physical or virtual job fairs | On Track to be Achieved |  | 0 |  | 0 |  | 0
CR 23 | Support economic growth in East Staffordshire | Administer the Small Business Fund grant scheme to support the growth of small businesses and start-ups | On Track to be Achieved |  | 0 |  | 0 |  | 0
CR 24 | Support economic growth in East Staffordshire | Hold 4 engagement events with Town Centre retailers | Not Yet Due |  | 0 |  | 0 |  | 0
CR 25 | Support economic growth in East Staffordshire | Consider creating a Business Improvement District in Uttoxeter | Not Yet Due |  | 0 |  | 0 |  | 0
CR 26 | Support economic growth in East Staffordshire | Commission inward investment consultants to drive private investment in Burton | Not Yet Due |  | 0 |  | 0 |  | 0
CR 27 | New and Refreshed Planning Policies | Produce Guidance on achieving Biodiversity net gains through Planning | Not Yet Due |  | 0 |  | 0 |  | 0
CR 28 | New and Refreshed Planning Policies | Draft Local Sustainable Development (Climate Change SPD) | Not Yet Due |  | 0 |  | 0 |  | 0
CR 29 | Partnership Working | Review the Council’s internal procedures and training in support of the Prevent Agenda | Not Yet Due |  | 0 |  | 0 |  | 0
CR 30 | Partnership Working | Consider the introduction of a Parish Council Forum/other communication channels | Fully Achieved |  | 0 |  | 0 |  | 0
EHB 01 | Open Spaces Initiatives | Achieve a minimum of 2 In Bloom gold awards for our In Bloom entries across the Borough* | On Track to be Achieved |  | 0 |  | 0 |  | 0
EHB 02 | Open Spaces Initiatives | Provide a first year update report on progress with the Parks Development Plan | Not Yet Due |  | 0 |  | 0 |  | 0
EHB 03 | Open Spaces Initiatives | Enter at least 5 of our parks into the ‘It’s Your Neighbourhood Awards’ scheme and achieve a minimum of Bronze Award* | Not Yet Due |  | 0 |  | 0 |  | 0
EHB 04 | Supporting Sports and Leisure Delivery Partners | Investigate opportunities to establish and enhanced Play Day event in conjunction with Everyone Active* | Deferred |  | 0 |  | 0 |  | 0
EHB 05 | Supporting Sports and Leisure Delivery Partners | Complete a Review of Health & Activity Strategy and Delivery in the Borough | On Track to be Achieved |  | 0 |  | 0 |  | 0
EHB 06 | Maintain Performance For Street Cleansing | Litter Detritus Graffiti Fly-posting 0% | Not Yet Due |  | 0 |  | 0 |  | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!