## 1. All Data
[6 empty] | QUARTER 1: April - June 2020 |  |  |  | QUARTER 2: July - September 2020 |  |  |  |  | QUARTER 3: October - December 2020 |  |  |  |  | QUARTER 4: January - March 2021
Reporting Officer | Reporting Officer | Corporate Plan Ref Number | Measures | Target 2020/21 | Target Date | Quarter 1 (April - June 2020) | End of year forecast as at end of Q1 (NUMERICAL INDICATORS ONLY) | Quarter 1 On Track? (R/A/G) | Comments / Further action (Q1) (IF APPLICABLE) | Quarter 2 (July - September 2020) | Year to date (April - Sept 2020) (NUMERICAL INDICATORS ONLY) | End of year forecast as at end of Q2 (NUMERICAL INDICATORS ONLY) | Quarter 2 On Track? (R/A/G) | Comments / Further action (Q2) (IF APPLICABLE) | Quarter 3 (October - December 2020) | Year to date (April - Dec 2020) (NUMERICAL INDICATORS ONLY) | End of year forecast as at end of Q3 (NUMERICAL INDICATORS ONLY) | Quarter 3 On Track? (R/A/G) | Comments / Further action (Q3) (IF APPLICABLE) | Quarter 4 (January - March 2021) | Cumulative Annual Outturn (NUMERICAL INDICATORS ONLY) | End of Year Achieved? (R/A/G) | Comments / Further action (Q4) (IF APPLICABLE) | Qtr | Service | Team | Corporate Priority | Portfolio |  | CP order | Previously identified as potentially impacted by CV19
| James Abbott | CR02 | Proactively Supporting the Boundary Review of East Staffordshire | Respond to Boundary Review Consultation in line with LGBCE timetable |  | The LGBCE has resumed the review of East Staffordshire, following a pause during the Covid-19 lockdown. The consultation on the LGBCE's proposed boundaries will run until September 7th 2020 & ESBC will respond from a electoral management perspective regarding the suggested names for the proposed new warded parishes. |  | On Track to be Achieved |  | The LGBCE's final recommendations are due to be published 1st December 2020 |  |  | On Track to be Achieved | [11 empty] | Andy O'Brien | Electoral Services | Community Regeneration | Leader | L19 | 2 | *
| Nicola Gilligan | CR03 | Proactively Supporting the Boundary Review of East Staffordshire | Prepare for Polling Place Review following completion of Boundary Review | March 2021 | Planning is in the preliminary stages in line with the LGBCE timetable and their initial recommendations published on 30 June 2020. LGBCE’s final recommendations are due to be published 1 December 2020. |  | On Track to be Achieved |  | The preparation for the Polling Place Review is ongoing and will be delivered by the target date. |  |  | On Track to be Achieved | The LGBCE's final recommendations are due to be published 1st December 2020 | [10 empty] | Andy O'Brien | Electoral Services | Community Regeneration | Leader | L20 | 3 | *
| Linda McDonald | CR04 | Increasing Staffing Availability Through Reduced Sickness | Short Term Sickness Days Average: 2.98 days |  | 0.21 days | 2.5 days | On Track to be Achieved | Q1 2019/20 (last year) 0.69 days | 0.54 days | 0.72 days | 2.37 days | On Track to be Achieved | [11 empty] | Andy O'Brien | HR & Payroll | Community Regeneration | Leader | L21 | 4 | *
| Linda McDonald | CR05 | Improve On The Average Time To Pay Creditors | Average Time To Pay Creditors: 10 days |  | 9 days | 10 days | On Track to be Achieved | Q1 2019/20 (last year) = 10 days | 10 days | 10 days | 10 days | On Track to be Achieved | [11 empty] | Andy O'Brien | HR & Payroll | Community Regeneration | Leader | L22 | 5 | *
| Angela Wakefield | CR06 | Legal and Assets | Commission a condition survey of the Council’s industrial units at Centrum 100 Business Park | September 2020 |  |  | Not Yet Due |  | Survey commissioned 28th August 2020 |  |  | Fully Achieved | [11 empty] | Andy O'Brien | Assets & Estates | Community Regeneration | Leader | L23 | 6 | *
| Angela Wakefield | CR07 | Legal and Assets | Carry out works to 8 of the Council’s commercial properties, as identified in the condition survey | March 2021 |  |  | Not Yet Due |  |  |  |  | Not yet due | [11 empty] | Andy O'Brien | Assets & Estates | Community Regeneration | Leader | L24 | 7 | *
| Michael Hovers | CR08 | Increase Capacity at Stapenhill Cemetery | Commence preparatory works for the expansion of Stapenhill Cemetery. | December 2020 | Consultants have been asked to update their revised quote from November 2019. Revised quote has been received and stage 1 investigation works have been ordered. |  | Fully Achieved |  | Tier 1 report received and passed to the Environment Agency for assessment |  |  | Fully Achieved | [11 empty] | Mark Rizk | Communities, Open Spaces & Facilities | Community Regeneration | Leisure, Culture & Tourism | LCT10 | 8 | *
| Michael Hovers | CR09 | Market Hall Development Initiatives | Implement the outcome of the Market Hall future options review | March 2021 | Deferred until later within this financial year, as this target is linked to the developing Stronger Towns work. Target to be revisited in October 2020. |  | Deferred |  | Target deferred as part of Q1 Review due to coronavirus situation. | N/A | N/A | Deferred | Government feedback in relation to Stronger Towns Fund not expected until March/April 2021 due to ongoing impact of Covid-19. | [10 empty] | Mark Rizk | Markets | Community Regeneration | Leisure, Culture & Tourism | LCT11 | 9 | *
| Michael Hovers | CR10 | Market Development Initiatives | Hold at least 7 commercial events in the Market Hall/Market Place | March 2021 | Whilst there has been an impact on opportunities to hold commercial events in and around the Market Hall during quarter 1, opportunities do exist to hold events in the Market Place moving forward. |  | On Track to be Achieved |  | Uncertainty regarding COVID19 restrictions has seen few enquires for the use of the market hall as an events venue. Ongoing restrictions are likely to place further pressure on the achievement of his target |  |  | In Danger of Falling Behind Target | [11 empty] | Mark Rizk | Markets | Community Regeneration | Leisure, Culture & Tourism | LCT12 | 10 | *
| Michael Hovers | CR11 | Market Hall Development Initiatives | Continue to benchmark Market Hall performance through APSE membership | March 2021 | We have joined APSE |  | On Track to be Achieved |  | Market Hall data has been supplied for APSE for analysis and benchmarking comparison |  |  | Fully Achieved | [11 empty] | Mark Rizk | Markets | Community Regeneration | Leisure, Culture & Tourism | LCT13 | 11 | *
| Naomi Perry | CR12 | Major Planning Applications Determined Within 13 Weeks | Top Quartile as measured against relevant MHCLG figures |  | 8 Applications all within time = 100% |  | On Track to be Achieved | Within top quartile based on CLG latest quarter reported. | 7 Applications all within time = 100% | 100 |  | On Track to be Achieved | Year to date figures are exceeding % MHCLG top quartile | [10 empty] | Sal Khan | Planning | Community Regeneration | Regeneration & Planning Policy | RPP08 | 12 | *
| Naomi Perry | CR13 | Minor Planning Applications Determined Within 8 Weeks | Top Quartile as measured against relevant MHCLG figures |  | 63 Applications of which 60 in time = 95% |  | On Track to be Achieved | Within top quartile based on CLG latest quarter reported. | 49 Applications of which 45 in time = 92% | 105 on time out of 112 = 93.75% |  | On Track to be Achieved | Year to date figures are exceeding % MHCLG top quartile | [10 empty] | Sal Khan | Planning | Community Regeneration | Regeneration & Planning Policy | RPP09 | 13 | *
| Naomi Perry | CR14 | Other Planning Applications Determined in 8 Weeks | Top Quartile as measured against relevant MHCLG figures |  | 124 Applications all within time = 100% |  | On Track to be Achieved | Within top quartile based on CLG latest quarter reported. | 142 Applications of which 135 in time = 95% | 259 out of 266 = 97.37% |  | On Track to be Achieved | Year to date figures are exceeding % MHCLG top quartile | [10 empty] | Sal Khan | Planning | Community Regeneration | Regeneration & Planning Policy | RPP10 | 14 | *
| Naomi Perry | CR15 | Supporting Neighbourhood Plans | Rolleston Neighbourhood Plan Made | Date TBC | Rolleston Neighbourhood Plan referendum delayed due to COVID-19. Target deferred to the next Corporate Plan year, as all elections have been postponed for 2020/21 |  | Deferred |  | Target deferred as part of Q1 Review due to ongoing coronavirus situation | N/A | N/A | Deferred | [11 empty] | Sal Khan | Planning | Community Regeneration | Regeneration & Planning Policy | RPP11 | 15 | *
| Naomi Perry | CR16 | New and Refreshed Planning Policies | Finalise and adopt Brewery Building Conversion Design Guidance SPD | October 2020 | On track - draft document have been considered by CMT and LDL. |  | On Track to be Achieved |  | SPD has gone to LDL and the groups - to be adopted via EDR in October. |  |  | On Track to be Achieved | [11 empty] | Sal Khan | Planning | Community Regeneration | Regeneration & Planning Policy | RPP12 | 16 | *
| Naomi Perry | CR17 | New and Refreshed Planning Policies | Publish Revised Statement of Community Involvement | March 2021 | On track - draft document have been considered by CMT and LDL. |  | On Track to be Achieved |  | Consultation draft has been undertaken and final version being prepared for November CMT. |  |  | On Track to be Achieved | [11 empty] | Sal Khan | Planning | Community Regeneration | Regeneration & Planning Policy | RPP13 | 17 | *
| Naomi Perry | CR18 | New and Refreshed Planning Policies | Produce report and approach regarding Brownfield Register Part 2 | October 2020 | On track - officers preparing documents to be considered in due course by CMT, LDL and Cabinet |  | On Track to be Achieved |  | Report prepared for October CMT and LDL |  |  | On Track to be Achieved | [11 empty] | Sal Khan | Planning | Community Regeneration | Regeneration & Planning Policy | RPP14 | 18
| Naomi Perry | CR19 | New and Refreshed Planning Policies | Revise and adopt Car parking SPD | October 2020 | On track - draft document have been considered by CMT and LDL. |  | On Track to be Achieved |  | SPD has gone to LDL and the groups - to be adopted via EDR in October. |  |  | On Track to be Achieved | [11 empty] | Sal Khan | Planning | Community Regeneration | Regeneration & Planning Policy | RPP15 | 19 | *
| Simon Humble | CR20 | Improve Burton town centre through significant environmental regeneration | Practical completion of the Station Street works via Amey | October 2020 | The Works process started in late March 2020 and was able to continue throughout the lockdown period as the works were categorised as essential. The works process is currently on programme and on target for practical completion to be achieved by the end of October 2020. |  | On Track to be Achieved |  | The work on Station Street has continued on programme and remains on target for practical completion to be achieved by the end of October 2020. |  |  | On Track to be Achieved | [11 empty] | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP16 | 20
| Thomas Deery | CR21 | Improve Burton town centre through significant environmental regeneration | Deliver phase 1 of the Washlands Enhancement Project, fully utilising the GBSLEP Local Growth Fund monies | March 2021 | The funding profile for the Washlands has been reshaped, meaning that there is no longer a requirement for £1m to be spend before March 2021. This will enable the single phased delivery of the project and so phase 1 will now comprise the remaining design and development work, such as the planning application, permitting, and appointment of contractors. |  | On Track to be Achieved |  | As per previous update, Phase 1 is now about completing the preparatory work for the implementation of the project. As such, during Q2, consultants (Black & Veatch) have been appointed and are currently working on the ground investigations, planning application(s), and specification for contractors. |  |  | On Track to be Achieved | [11 empty] | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP17 | 21 | *
| Thomas Deery | CR22 | Work towards achieving transformation regeneration for Burton upon Trent of up to £25m through the Towns Fund | Working with the Town Deal Board, develop a Town Investment Plan for Burton and create a business case for funding | March 2021 | A Town Investment Plan is being developed, following the publication of Government guidance in June 2020. This is intended to be submitted in October 2020. |  | On Track to be Achieved |  | A Town Investment Plan is being developed, following the publication of Government guidance in June 2020. This is intended to be submitted in October 2020. |  |  | On Track to be Achieved | [11 empty] | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP18 | 22 | *
| Thomas Deery | CR23 | Support the delivery of affordable housing on brownfield land through the utilisation of S106 commuted sums | Review the progress of existing S106 commuted sums and identify new projects for potential funding | October 2020 |  |  | Not Yet Due |  | A report will be considered by Cabinet at its October 2020 meeting. |  |  | On Track to be Achieved | [11 empty] | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP19 | 23
| Simon Humble | CR24 | Identify a vision for the future regeneration of Uttoxeter | Member approval of the final Uttoxeter Masterplan | December 2020 | Cushman and Wakefield were appointed in late March 2020 as consultants to carry out an assessment of the success of the original Uttoxeter Masterplan from 2003 along with the creation a new version. Cushman and Wakefield have already completed the assessment of the original masterplan and are now working on the development of the baseline study and stakeholder engagement process. |  | On Track to be Achieved |  | The consultants have undertaken a baseline review of Uttoxeter to identify the current functions of the town, its strengths and weaknesses, underlying threats to its future, identification of potential opportunities. Key local (community, business and political) stakeholders have been engaged and a public consultation process has also been completed. The consultants will review all aspects of the baseline work and responses from the consultation processes to move forward with the design options. These will be presented to the economic growth project group, before being finalised and presented at Full Council. |  |  | On Track to be Achieved | [11 empty] | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP20 | 24 | *
| Thomas Deery | CR25 | Promote local employment opportunities | Working with the Worklessness Action Group and local MP, support the delivery of three job fairs | March 2021 | The first job fair of the year was planned for June 2020 and this was unfortunately cancelled as a result of COVID-19. It is not yet determined whether 3 can still be achieved in the year using alternative methods (such as virtual). |  | In Danger of Falling Behind Target |  | Job fairs are currently being delivered in a different way with targeted supported and 'virtual' job fairs through social media. As such, the work is not taking place in the same way, but is hopefully having the same impact. | 2 Virtual Job Fairs |  | On Track to be Achieved | [11 empty] | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP21 | 25 | *
| Thomas Deery | CR26 | Continue to support local businesses to grow and innovate | Create a grant fund to support small businesses and deliver throughout the year | March 2021 |  |  | Not Yet Due |  | Members have recently been provided with a brief overview of how a scheme could operate and invited to provide comments, feedback and ideas. Whilst this is still being developed, it is imperative that any funding scheme complements national support rather than duplicates it and focuses on growth. |  |  | On Track to be Achieved | [11 empty] | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP22 | 26 | *
| Thomas Deery | CR27 | Continue to support local businesses to grow and innovate | Provide direct support to 20 businesses through the Growth Hub Advisor contract | March 2021 | Businesses are being supported by advice from the Growth Hub Advisor contract, however the nature of this advice has notably changed to reflect COVID-19. An exact number of businesses supported has not yet been issued, but it is believed to be proportionate to the quarter. |  | On Track to be Achieved |  | Businesses are being supported by advice from the Growth Hub Advisor contract, however the nature of this advice has notably changed to reflect COVID-19. An exact number of businesses supported has not yet been issued, but it is believed to be proportionate to the quarter. |  |  | On Track to be Achieved | [11 empty] | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RRP23 | 27 | *
| Thomas Deery | CR28 | Continue to work effectively with regeneration partners | Continue to work with strategic tourism partners, such as the National Forest, the Campaign to Reopen the Ivanhoe Line and the TTTV, on the regeneration of the borough | March 2021 | Work continues with these organisations. The Brook Hollows project is being taken forwards with the TTTV and now in partnership with the EA. The Ivanhoe Line project is progressing well, however members of that group were affected by Shielding requirements. |  | On Track to be Achieved | In May 2020 the government announced the Ivanhoe line would be 1 of 10 campaigns to received support from the 'restoring your railways fund' | Work continues with these organisations, with partnerships continuing to develop and grow. |  |  | On Track to be Achieved | [11 empty] | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP24 | 28 | *
| Brett Atkinson | EHW01 | Delivering Better Services to Support Homelessness | Promote, monitor and report on the Burton and East Staffordshire Partnership, produce two activity reports during the year | (Sep 20 / Mar 21) | The Partnership has been instrumental in responding to the lockdown and associated 'Everyone In' campaign. A virtual meeting to debrief and consider how we can consolidate the gains that have been made is taking place in July. |  | On Track to be Achieved |  | Following a successful bid to the MHCLG's NSAP Fund for interim accommodation, the Partnership has been instrumental in providing a joined up approach to recipients of the intervention. An activity report reviewing the East Staffs Homeless Partnership was considered at CMT & LDL in September 2020. |  |  | On Track to be Achieved | [11 empty] | Sal Khan | Housing Options | Environment and Health & Wellbeing | Environment & Housing | EH14 | 29
| Brett Atkinson | EHW02 | Delivering Better Services to Support Homelessness | Evaluate and build on the existing MHCLG/ESBC projects to target entrenched rough sleepers with two activity reports during the year Prepare and submit new applications to MHCLG as and when appropriate during the year | (Sept 2020 / Mar 2021) | The projects that are funded by the MHCLG's 'Rough Sleeping Initiative' have been effective in supporting individuals to exit from the 'Everyone In' campaign with settled solutions. There is an initial proposal for an additional project, although the MHCLG's prospectus to secure the funding has not yet been released. |  | On Track to be Achieved |  | An application to the MHCLG's NSAP Fund was submitted in August 2020. The application had two parts, with the first part having been successful and the second part yet to be determined. An activity report reviewing the rough sleeping projects was considered at CMT & LDL in September 2020. |  |  | On Track to be Achieved | [11 empty] | Sal Khan | Housing Options | Environment and Health & Wellbeing | Environment & Housing | EH15 | 30
| Brett Atkinson | EHW03 | Proactively reducing the number of empty homes in the borough | Produce annual contract performance report | March 2021 | This work is well underway, and early analysis indicates that the contract has delivered a strong set of results. |  | On Track to be Achieved |  | Grafton have been refining the list of empty homes to be considered for further enforcement in the forthcoming Cabinet report. An additional 111 properties that have remained empty for 2 years have been contacted with a stage 1 letter. |  |  | On Track to be Achieved | [11 empty] | Sal Khan | Housing Options | Environment and Health & Wellbeing | Environment & Housing | EH16 | 31
| Brett Atkinson | EHW04 | Delivering Better Services to Support Homelessness | Average time from appointment to initial decision for homeless applicants of 3 days |  | The Housing Options Team made 63 initial decisions this quarter, with an average time to decision of 0.75 days. | 1 day | On Track to be Achieved |  | The Housing Options Team made 65 initial decisions this quarter, with an average time of 0.0 days. | 0.35 days | 0.5 days | On Track to be Achieved | [11 empty] | Sal Khan | Housing Options | Environment and Health & Wellbeing | Environment & Housing | EH17 | 32 | *
| Brett Atkinson | EHW05 | Continue to Maximise Utilisation of Self Contained Temporary Accommodation for Homeless Applicants | Reduce ‘Key to Key’ Void Turnaround to an average of 6 working days |  | There was only 1 'Key to Key' occasion during this quarter; this is because households in B&B were prioritised to be moved directly into settled accommodation to avoid the number of contacts. This 1 move took 2 working days. | 5 days | On Track to be Achieved |  | There were 5 'Key to Key' occasions during this quarter. The average across the 5 moves is 5.2 days, with one move increasing the average at 12 days due to the need to replace white goods. | 4.7 days | 5 days | On Track to be Achieved | [11 empty] | Sal Khan | Housing Options | Environment and Health & Wellbeing | Environment & Housing | EH18 | 33
| Brett Atkinson | EHW06 | Improving our Housing Strategy Initiatives | Refreshed Housing Strategy | December 2020 | The lay out and structure of the document has been drafted, with a move toward the look and feel of the current Homelessness Strategy. |  | On Track to be Achieved |  | Following internal consultation, a draft Housing Strategy is now out to public consultation. |  |  | On Track to be Achieved | [11 empty] | Sal Khan | Housing Options | Environment and Health & Wellbeing | Environment & Housing | EH19 | 34
| Brett Atkinson | EHW07 | Improving our Housing Strategy Initiatives | Report opportunities for improving Housing Register Service | December 2020 | A streamlined digital application system has been undergoing rigorous testing and is due to launch to the public next month. |  | On Track to be Achieved |  | Online applications to join the Housing Register launched on 22 September, and early indications are that this project has been a success. Analysis of the data and consideration of the improvement to the customer journey to take place ahead of a report due in the next quarter. |  |  | On Track to be Achieved | [11 empty] | Sal Khan | Housing Options | Environment and Health & Wellbeing | Environment & Housing | EH20 | 35 | *
| Paul Farrer | EHW08 | Maintain Top Quartile Performance For Street Cleansing - Litter | Maintain Top Quartile Performance |  | Not yet due - surveys run April - July |  | Not Yet Due |  | 0% April - July |  |  | On Track to be Achieved | [11 empty] | Sal Khan | Environment | Environment and Health & Wellbeing | Environment & Housing | EH21 | 36 | *
| Paul Farrer | EHW09 | Maintain Top Quartile Performance For Street Cleansing - Detritus | Maintain Top Quartile Performance |  | Not yet due - surveys run April - July |  | Not Yet Due |  | 0% April - July |  |  | On Track to be Achieved | [11 empty] | Sal Khan | Environment | Environment and Health & Wellbeing | Environment & Housing | EH22 | 37 | *
| Paul Farrer | EHW10 | Maintain Top Quartile Performance For Street Cleansing - Graffiti | Maintain Top Quartile Performance |  | Not yet due - surveys run April - July |  | Not Yet Due |  | 0% April - July |  |  | On Track to be Achieved | [11 empty] | Sal Khan | Environment | Environment and Health & Wellbeing | Environment & Housing | EH23 | 38 | *
| Paul Farrer | EHW11 | Maintain Top Quartile Performance For Street Cleansing – Fly-Posting | Maintain Top Quartile Performance |  | Not yet due - surveys run April - July |  | Not Yet Due |  | 0% April - July |  |  | On Track to be Achieved | [11 empty] | Sal Khan | Environment | Environment and Health & Wellbeing | Environment & Housing | EH24 | 39 | *
| Paul Farrer | EHW12 | Maintain Top Quartile Performance On Recycling | Household Waste Recycled and Composted: Maintain Top Quartile Performance |  | 46.28% - estimated |  | On Track to be Achieved |  | 47% - estimated | 47.5% - estimated | 41% - estimated | On Track to be Achieved | [11 empty] | Sal Khan | Environment | Environment and Health & Wellbeing | Environment & Housing | EH25 | 40 | *
| Paul Farrer | EHW13 | Maintain Top Quartile Performance On Waste Reduction | Residual Household Waste Per Household: Maintain Top Quartile Performance |  | 144.65kg - estimated. Collection tonnages are higher than normal for Q1 due to the impact of the pandemic. This may effect the outturn figure. |  | On Track to be Achieved |  | 138.86kg - estimated | 276kg - estimated | 560kg - estimated | On Track to be Achieved | [11 empty] | Sal Khan | Environment | Environment and Health & Wellbeing | Environment & Housing | EH26 | 41 | *
| Michael Hovers | EHW14 | Open Spaces Initiatives | Develop a Borough wide parks development plan | December 2020 |  |  | Not Yet Due |  |  |  |  | Not Yet Due | [11 empty] | Mark Rizk | Communities, Open Spaces & Facilities | Environment and Health & Wellbeing | Leisure, Culture & Tourism | LCT14 | 42
| Michael Hovers | EHW15 | Open Spaces Initiatives | Achieve 2 in bloom gold awards and support Uttoxeter in the 2020 National In bloom awards | September 2020 | Target to be deferred to the next Corporate Plan year, as these awards have been postponed by the organiser until 2021/22 |  | Deferred |  | Target deferred as part of Q1 Review due to ongoing coronavirus situation | N/A | N/A | Deferred | [11 empty] | Mark Rizk | Communities, Open Spaces & Facilities | Environment and Health & Wellbeing | Leisure, Culture & Tourism | LCT15 | 43 | *
| Michael Hovers | EHW16 | Open Spaces Initiatives | Achieve 1 Green Flag award | September 2020 | Target to be deferred to the next Corporate Plan year, as these awards have been postponed by the organiser until 2021/22 |  | Deferred |  | Target deferred as part of Q1 Review due to ongoing coronavirus situation | N/A | N/A | Deferred | [11 empty] | Mark Rizk | Communities, Open Spaces & Facilities | Environment and Health & Wellbeing | Leisure, Culture & Tourism | LCT16 | 44 | *
| Michael Hovers | EHW17 | Open Spaces Initiatives | Increase the marks awarded to the 9 parks in the “It’s Your Neighbourhood” Parks category by an average of 10% | September 2020 | Target to be deferred to the next Corporate Plan year, as these awards have been postponed by the organiser until 2021/22 |  | Deferred |  | Target deferred as part of Q1 Review due to ongoing coronavirus situation | N/A | N/A | Deferred | [11 empty] | Mark Rizk | Communities, Open Spaces & Facilities | Environment and Health & Wellbeing | Leisure, Culture & Tourism | LCT17 | 45 | *
| Michael Hovers | EHW18 | Develop Tourism within the Borough | Develop a tactical approach and plan for tourism in East Staffordshire | October 2020 | Draft document to be shared with the Deputy Leader early in Quarter 2 |  | On Track to be Achieved |  | Plan to be approved by Cabinet in October |  |  | On Track to be Achieved | [11 empty] | Mark Rizk | Communities, Open Spaces & Facilities | Environment and Health & Wellbeing | Leisure, Culture & Tourism | LCT18 | 46
| Rachel Liddle | EHW19 | Compliance Inspections in support of Public Protection | Undertake two high profile initiatives aimed at monitoring compliance and ensuring public protection | March 2021 | Initiatives currently being taken to investigate Covid-19 compliance in businesses that are starting to reopen |  | On Track to be Achieved |  | Ongoing partnership work with Staffordshire County Council and the Police for Covid enforcement and compliance in high risk establishments |  |  | On Track to be Achieved | [11 empty] | Mark Rizk | Environmental Health | Environment and Health & Wellbeing | Regulatory & Community Support | RCS04 | 47 | *
| Carol Flannery | EHW20 | Community & Civil Enforcement Initiatives | Undertake 8 focused initiatives (including fly tipping) across the Borough and deliver at least 6 education programs in local schools. | March 2021 | Planned initiatives have not yet taken place. This is due to school closures and the CCEO's have been involved in Covid-19 related tasks, shielding or WFH. |  | In Danger of Falling Behind Target | Alternative options being looked into such as other community groups i.e. scouts, brownies, cadets. Those contacted are functioning remotely. | Two initiatives have been completed during September. The first in Anglesey and the second in Shobnall. A further two are organised for October, one in Horninglow and one in Eton. Due to COVID 19 and the challenges faced, including Covid Marshal activity, these have not & will not include schools at this stage. |  |  | In Danger of Falling Behind Target | [11 empty] | Mark Rizk | Civil Enforcement | Environment and Health & Wellbeing | Regulatory & Community Support | RCS05 | 48 | *
| Rachel Liddle | EHW21 | Development of the Selective Licensing Scheme | Selective Licensing Designation Approved | Date TBC | Target to be deferred to the next Corporate Plan year, as there is currently no indication that the necessary Government guidance will be received this year. |  | Deferred |  | Target deferred as part of Q1 Review due to ongoing coronavirus situation | N/A | N/A | Deferred | [11 empty] | Mark Rizk | Environmental Health | Environment and Health & Wellbeing | Regulatory & Community Support | RCS06 | 49 | *
| Rachel Liddle | EHW22 | Development of the Selective Licensing Scheme | Selective Licensing Third Year Review Complete | November 2020 | On track to be completed |  | On Track to be Achieved |  | Report completed for CMT |  |  | On Track to be Achieved | [11 empty] | Mark Rizk | Environmental Health | Environment and Health & Wellbeing | Regulatory & Community Support | RCS07 | 50 | *
| Rachel Liddle | EHW23 | Partnership working with Trading Standards Regarding Tenant Fees | Undertake a Targeted Initiative to Investigate and Enforce Compliance with Tenant Fees Legislation | March 2021 | 1 case of non compliance is currently being investigated in partnership with Staffordshire County Council |  | On Track to be Achieved |  | Draft strategy for targeting tenants and landlords to check for compliance |  |  | Not Yet Due | [11 empty] | Mark Rizk | Environmental Health | Environment and Health & Wellbeing | Regulatory & Community Support | RCS08 | 51 | *
| Rachel Liddle | EHW24 | Disabled Facilities Grant Review | Complete Annual Review of Disabled Facilities Grant Service | December 2020 | On track to be completed |  | On Track to be Achieved |  | CMT report currently being drafted |  |  | On Track to be Achieved | [11 empty] | Mark Rizk | Environmental Health | Environment and Health & Wellbeing | Regulatory & Community Support | RCS09 | 52 | *
| Rachel Liddle | EHW25 | Climate Change & Air Quality Policy | Consider the declaration of a Climate Emergency and implement and monitor a Climate Change action plan-including an annual update | August 2020 | The report for a Climate Change Emergency Declaration and supporting action plan has been completed and is being taken to the groups in July for approval in August. |  | On Track to be Achieved |  | Report completed and agreed in August 2020 |  |  | Fully Achieved | [11 empty] | Mark Rizk | Environmental Health | Environment and Health & Wellbeing | Regulatory & Community Support | RCS10 | 53 | *
| Rachel Liddle | EHW26 | Multi-agency Initiatives to Combat Modern Slavery | Carry out Covid-19 compliance checks across the Borough and report progress on a quarterly basis | March 2021 | Focussed covid compliance checks are being undertaken in licensed premises along with targeted initiatives to businesses within Uxbridge Street, Waterloo Street and Horninglow Road. Business packs have been distributed along with letters advising of additional restrictions that shops should put in place to reduce customer numbers and ensure customers wear face coverings. |  | On Track to be Achieved |  | Focussed compliance checks in high risk premises such as takeaways, licensed premises and warehouses |  |  | On Track to be Achieved | [11 empty] | Mark Rizk | Environmental Health | Environment and Health & Wellbeing | Regulatory & Community Support | RCS11 | 54 | *
Update not provided | Update not provided
Fully Achieved | Fully Achieved
Numerical Outturn Within 5% Tolerance | Numerical Outturn Within 5% Tolerance
Numerical Outturn Within 10% Tolerance | Numerical Outturn Within 10% Tolerance
Target Partially Met | Target Partially Met
Off Target | Off Target
Completed Significantly After Target Deadline | Completed Significantly After Target Deadline
Completion Date Within Reasonable Tolerance | Completion Date Within Reasonable Tolerance
Deferred | Deferred
Deleted | Deleted
Fully Achieved | Fully Achieved
On Track to be Achieved | On Track to be Achieved
In Danger of Falling Behind Target | In Danger of Falling Behind Target
Off Target | Off Target
Completed Behind Schedule | Completed Behind Schedule
Deleted | Deleted
Not Yet Due | Not Yet Due
Update Not Provided | Update Not Provided
Deferred | Deferred

## Q1 Summary (hidden)
Click here to return to index page
Quarter One (2020/21) | Green |  | Amber |  | Red
| Number of Indicators | Percentage | Number of Indicators | Percentage | Number of Indicators | Percentage
Overall Performance
All due targets | 36 | 94.74% | 2 | 5.263% | 0 | 0%
Corporate Priority
Value for Money Council | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Environment and Health & Well Being | 16 | 94.12% | 1 | 5.882% | 0 | 0%
Community Regeneration | 20 | 95.24% | 1 | 4.762% | 0 | 0%
Portfolio
Leader | 4 | 100% | 0 | 0% | 0 | 0%
Environment & Housing | 9 | 100% | 0 | 0% | 0 | 0%
Leisure, Culture & Tourism | 4 | 100% | 0 | 0% | 0 | 0%
Regeneration & Planning Policy | 13 | 92.86% | 1 | 7.143% | 0 | 0%
Regulatory & Community Support | 6 | 85.71% | 1 | 14.29% | 0 | 0%

## Q2 Summary
Click here to return to index page
Quarter Two (2020/21) | Green |  | Amber |  | Red
| Number of Indicators | Percentage | Number of Indicators | Percentage | Number of Indicators | Percentage
Overall Performance
All due targets | 42 | 95.45% | 2 | 4.545% | 0 | 0%
Corporate Priority
Environment and Health & Well Being | 19 | 95% | 1 | 5% | 0 | 0%
Community Regeneration | 23 | 95.83% | 1 | 4.167% | 0 | 0%

## Q3 Summary (hidden)
Click here to return to index page
Quarter Three (2020/21) | Green |  | Amber |  | Red
| Number of Indicators | Percentage | Number of Indicators | Percentage | Number of Indicators | Percentage
Overall Performance
All due targets | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Corporate Priority
Value for Money Council | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Environment and Health & Well Being | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Community Regeneration | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Portfolio
Leader | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Environment & Housing | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Leisure, Culture & Tourism | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Regeneration & Planning Policy | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Regulatory & Community Support | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!

## Q4 Summary (hidden)
Click here to return to index page
End of Year 2020/21 | Green |  | Amber |  | Red
| Number of Indicators | Percentage | Number of Indicators | Percentage | Number of Indicators | Percentage
Overall Performance
All due targets | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Corporate Priority
Value for Money Council | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Environment and Health & Well Being | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Community Regeneration | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Portfolio
Leader | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Environment & Housing | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Leisure, Culture & Tourism | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Regeneration & Planning Policy | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Regulatory & Community Support | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!

## 2a. % By Priority
QUARTER ONE (April - June 2020) | [5 empty] | QUARTER TWO (July - Sept 2020) | [5 empty] | QUARTER THREE (Oct - Dec 2020) | [5 empty] | QUARTER FOUR (Jan - Mar 2021)
ALL TARGETS | [5 empty] | ALL TARGETS | [5 empty] | ALL TARGETS | [5 empty] | ALL TARGETS
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | 1 | 1.887% | 67.92% | 2.632% | 94.74% | Target Fully Achieved | 4 | 7.547% | 79.25% | 9.091% | 95.45% | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
On Track to be Achieved | 35 | 66.04% |  | 92.11% |  | On Track to be Achieved | 38 | 71.7% |  | 86.36% |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | Numerical Outturn Within 5% Tolerance | 0 | #DIV/0! |  | #DIV/0!
In Danger of Falling Behind Target | 2 | 3.774% | 3.774% | 5.263% | 5.263% | In Danger of Falling Behind Target | 2 | 3.774% | 3.774% | 4.545% | 4.545% | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Numerical Outturn Within 10% Tolerance | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[18 empty] | Target Partially Met | 0 | #DIV/0! |  | #DIV/0!
[18 empty] | Completion Date Within Reasonable Tolerance | 0 | #DIV/0! |  | #DIV/0!
Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Significantly After Target Deadline | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0!
Not yet due to be reported | 9 | 16.98% | 16.98% |  |  | Not yet due to be reported | 3 | 5.66% | 5.66% |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0!
Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0!
Deferred | 6 | 11.32% | 11.32% |  |  | Deferred | 6 | 11.32% | 11.32% |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0!
Deleted | 0 | 0% | 0% |  |  | Deleted | 0 | 0% | 0% |  |  | Deleted | 0 | #DIV/0! | #DIV/0! |  | Back to index | Deleted | 0 | #DIV/0! | #DIV/0! |  | Back to index |  | Back to index
Totals | 53 |  |  |  |  | Totals | 53 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0
Due to be Reported | 38 |  |  |  |  | Due to be Reported | 44 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0
ENVIRONMENT AND HEALTH & WELL BEING | [5 empty] | ENVIRONMENT AND HEALTH & WELL BEING | [5 empty] | ENVIRONMENT AND HEALTH & WELL BEING | [5 empty] | ENVIRONMENT AND HEALTH & WELL BEING
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | 0 | 0% | 61.54% | 0% | 94.12% | Target Fully Achieved | 1 | 3.846% | 73.08% | 5% | 95% | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
On Track to be Achieved | 16 | 61.54% |  | 94.12% |  | On Track to be Achieved | 18 | 69.23% |  | 90% |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | Numerical Outturn Within 5% Tolerance | 0 | #DIV/0! |  | #DIV/0!
In Danger of Falling Behind Target | 1 | 3.846% | 3.846% | 5.882% | 5.882% | In Danger of Falling Behind Target | 1 | 3.846% | 3.846% | 5% | 5% | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Numerical Outturn Within 10% Tolerance | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[18 empty] | Target Partially Met | 0 | #DIV/0! |  | #DIV/0!
[18 empty] | Completion Date Within Reasonable Tolerance | 0 | #DIV/0! |  | #DIV/0!
Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Significantly After Target Deadline | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0!
Not yet due to be reported | 5 | 19.23% | 19.23% |  |  | Not yet due to be reported | 2 | 7.692% | 7.692% |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0!
Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0!
Deferred | 4 | 15.38% | 15.38% |  |  | Deferred | 4 | 15.38% | 15.38% |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0!
Deleted | 0 | 0% | 0% |  | Back to index | Deleted | 0 | 0% | 0% |  |  | Deleted | 0 | #DIV/0! | #DIV/0! |  | Back to index | Deleted | 0 | #DIV/0! | #DIV/0! |  |  | Back to index
Totals | 26 |  |  |  |  | Totals | 26 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0
Due to be Reported | 17 |  |  |  |  | Due to be Reported | 20 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0
COMMUNITY REGENERATION | [5 empty] | COMMUNITY REGENERATION | [5 empty] | COMMUNITY REGENERATION | [5 empty] | COMMUNITY REGENERATION
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | 1 | 3.704% | 74.07% | 4.762% | 95.24% | Target Fully Achieved | 3 | 11.11% | 85.19% | 12.5% | 95.83% | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
On Track to be Achieved | 19 | 70.37% |  | 90.48% |  | On Track to be Achieved | 20 | 74.07% |  | 83.33% |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | Numerical Outturn Within 5% Tolerance | 0 | #DIV/0! |  | #DIV/0!
In Danger of Falling Behind Target | 1 | 3.704% | 3.704% | 4.762% | 4.762% | In Danger of Falling Behind Target | 1 | 3.704% | 3.704% | 4.167% | 4.167% | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Numerical Outturn Within 10% Tolerance | 0 | #REF! | #REF! | #DIV/0! | #DIV/0!
[18 empty] | Target Partially Met | 0 | #REF! |  | #DIV/0!
[18 empty] | Completion Date Within Reasonable Tolerance | 0 | #REF! |  | #DIV/0!
Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Significantly After Target Deadline | 0 | #REF! | #REF! | #DIV/0! | #DIV/0!
Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #REF! |  | #DIV/0!
Not yet due to be reported | 4 | 14.81% | 14.81% |  |  | Not yet due to be reported | 1 | 3.704% | 3.704% |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #REF! | #REF!
Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #REF! | #REF!
Deferred | 2 | 7.407% | 7.407% |  |  | Deferred | 2 | 7.407% | 7.407% |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #REF! | #REF!
Deleted | 0 | 0% | 0% |  | Back to index | Deleted | 0 | 0% | 0% |  |  | Deleted | 0 | #DIV/0! | #DIV/0! |  | Back to index | Deleted | 0 | #REF! | #REF! |  |  | Back to index
Totals | 27 |  |  |  |  | Totals | 27 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0
Due to be Reported | 21 |  |  |  |  | Due to be Reported | 24 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0

## 2b. Charts by Priority
Charts by Corporate Priority | Please note that all charts shown below can be amended to be displayed in alternative styles. Please right click on the relevant chart, select "change chart type" and choose your preferred chart option.
Back to index
|  | Back to index | Back to index | Back to index | Back to index
OVERALL PERFORMANCE
[8 empty] | Q1 | Q2 | Q3 | Q4
[7 empty] | Green | 94.74% | 95.45% | #DIV/0! | #DIV/0!
[7 empty] | Amber | 5.263% | 4.545% | #DIV/0! | #DIV/0!
[7 empty] | Red | 0% | 0% | #DIV/0! | #DIV/0!
|  | Back to index | Back to index | Back to index | Back to index
VALUE FOR MONEY COUNCIL
[8 empty] | Q1 | Q2 | Q3 | Q4
[7 empty] | Green | #REF! | #REF! | #REF! | #REF!
[7 empty] | Amber | #REF! | #REF! | #REF! | #REF!
[7 empty] | Red | #REF! | #REF! | #REF! | #REF!
|  | Back to index | Back to index | Back to index | Back to index
ENVIRONMENT AND HEALTH & WELL BEING
[8 empty] | Q1 | Q2 | Q3 | Q4
[7 empty] | Green | 94.12% | 95% | #DIV/0! | #DIV/0!
[7 empty] | Amber | 5.882% | 5% | #DIV/0! | #DIV/0!
[7 empty] | Red | 0% | 0% | #DIV/0! | #DIV/0!
|  | Back to index | Back to index | Back to index |  | Back to index
COMMUNITY REGENERATION
[8 empty] | Q1 | Q2 | Q3 | Q4
[7 empty] | Green | 95.24% | 95.83% | #DIV/0! | #DIV/0!
[7 empty] | Amber | 4.762% | 4.167% | #DIV/0! | #DIV/0!
[7 empty] | Red | 0% | 0% | #DIV/0! | #DIV/0!

## 3a. % by Portfolio (hidden)
QUARTER ONE (April - June 2020) | [5 empty] | QUARTER TWO (July - Sept 2020) | [5 empty] | QUARTER THREE (Oct - Dec 2020) | [5 empty] | QUARTER FOUR (Jan - Mar 2021)
LEADER | [5 empty] | LEADER | [5 empty] | LEADER | [5 empty] | LEADER
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | 0 | 0% | 66.67% | 0% | 100% | Target Fully Achieved | 1 | 16.67% | 83.33% | 20% | 100% | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
On Track to be Achieved | 4 | 66.67% |  | 100% |  | On Track to be Achieved | 4 | 66.67% |  | 80% |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | Numerical Outturn Within 5% Tolerance | 0 | #DIV/0! |  | #DIV/0!
In Danger of Falling Behind Target | 0 | 0% | 0% | 0% | 0% | In Danger of Falling Behind Target | 0 | 0% | 0% | 0% | 0% | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Numerical Outturn Within 10% Tolerance | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[18 empty] | Target Partially Met | 0 | #DIV/0! |  | #DIV/0!
[18 empty] | Completion Date Within Reasonable Tolerance | 0 | #DIV/0! |  | #DIV/0!
Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Significantly After Target Deadline | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0!
Not yet due to be reported | 2 | 33.33% | 33.33% |  |  | Not yet due to be reported | 1 | 16.67% | 16.67% |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0!
Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0!
Deferred | 0 | 0% | 0% |  |  | Deferred | 0 | 0% | 0% |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0!
Deleted | 0 | 0% | 0% |  | Back to index | Deleted | 0 | 0% | 0% |  | Back to index | Deleted | 0 | #DIV/0! | #DIV/0! |  | Back to index | Deleted | 0 | #DIV/0! | #DIV/0! |  | Back to index
Totals | 6 |  |  |  |  | Totals | 6 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0
Due to be Reported | 4 |  |  |  |  | Due to be Reported | 5 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0
ENVIRONMENT & HOUSING | [5 empty] | ENVIRONMENT & HOUSING | [5 empty] | ENVIRONMENT & HOUSING | [5 empty] | ENVIRONMENT & HOUSING
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | 0 | 0% | 69.23% | 0% | 100% | Target Fully Achieved | 0 | 0% | 100% | 0% | 100% | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
On Track to be Achieved | 9 | 69.23% |  | 100% |  | On Track to be Achieved | 13 | 100% |  | 100% |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | Numerical Outturn Within 5% Tolerance | 0 | #DIV/0! |  | #DIV/0!
In Danger of Falling Behind Target | 0 | 0% | 0% | 0% | 0% | In Danger of Falling Behind Target | 0 | 0% | 0% | 0% | 0% | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Numerical Outturn Within 10% Tolerance | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[18 empty] | Target Partially Met | 0 | #DIV/0! |  | #DIV/0!
[18 empty] | Completion Date Within Reasonable Tolerance | 0 | #DIV/0! |  | #DIV/0!
Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Significantly After Target Deadline | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0!
Not yet due to be reported | 4 | 30.77% | 30.77% |  |  | Not yet due to be reported | 0 | 0% | 0% |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0!
Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0!
Deferred | 0 | 0% | 0% |  |  | Deferred | 0 | 0% | 0% |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0!
Deleted | 0 | 0% | 0% |  | Back to index | Deleted | 0 | 0% | 0% |  | Back to index | Deleted | 0 | #DIV/0! | #DIV/0! |  | Back to index | Deleted | 0 | #DIV/0! | #DIV/0! |  | Back to index
Totals | 13 |  |  |  |  | Totals | 13 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0
Due to be Reported | 9 |  |  |  |  | Due to be Reported | 13 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0
LEISURE, CULTURE & TOURISM | [5 empty] | LEISURE, CULTURE & TOURISM | [5 empty] | LEISURE, CULTURE & TOURISM | [5 empty] | LEISURE, CULTURE & TOURISM
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | 1 | 11.11% | 44.44% | 25% | 100% | Target Fully Achieved | 2 | 22.22% | 33.33% | 50% | 75% | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
On Track to be Achieved | 3 | 33.33% |  | 75% |  | On Track to be Achieved | 1 | 11.11% |  | 25% |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | Numerical Outturn Within 5% Tolerance | 0 | #DIV/0! |  | #DIV/0!
In Danger of Falling Behind Target | 0 | 0% | 0% | 0% | 0% | In Danger of Falling Behind Target | 1 | 11.11% | 11.11% | 25% | 25% | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Numerical Outturn Within 10% Tolerance | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[18 empty] | Target Partially Met | 0 | #DIV/0! |  | #DIV/0!
[18 empty] | Completion Date Within Reasonable Tolerance | 0 | #DIV/0! |  | #DIV/0!
Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Significantly After Target Deadline | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0!
Not yet due to be reported | 1 | 11.11% | 11.11% |  |  | Not yet due to be reported | 1 | 11.11% | 11.11% |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0!
Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0!
Deferred | 4 | 44.44% | 44.44% |  |  | Deferred | 4 | 44.44% | 44.44% |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0!
Deleted | 0 | 0% | 0% |  | Back to index | Deleted | 0 | 0% | 0% |  | Back to index | Deleted | 0 | #DIV/0! | #DIV/0! |  | Back to index | Deleted | 0 | #DIV/0! | #DIV/0! |  | Back to index
Totals | 9 |  |  |  |  | Totals | 9 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0
Due to be Reported | 4 |  |  |  |  | Due to be Reported | 4 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0
REGENERATION & PLANNING POLICY | [5 empty] | REGENERATION & PLANNING POLICY | [5 empty] | REGENERATION & PLANNING POLICY | [5 empty] | REGENERATION & PLANNING POLICY
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | 0 | 0% | 76.47% | 0% | 92.86% | Target Fully Achieved | 0 | 0% | 94.12% | 0% | 100% | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
On Track to be Achieved | 13 | 76.47% |  | 92.86% |  | On Track to be Achieved | 16 | 94.12% |  | 100% |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | Numerical Outturn Within 5% Tolerance | 0 | #DIV/0! |  | #DIV/0!
In Danger of Falling Behind Target | 1 | 5.882% | 5.882% | 7.143% | 7.143% | In Danger of Falling Behind Target | 0 | 0% | 0% | 0% | 0% | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Numerical Outturn Within 10% Tolerance | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[18 empty] | Target Partially Met | 0 | #DIV/0! |  | #DIV/0!
[18 empty] | Completion Date Within Reasonable Tolerance | 0 | #DIV/0! |  | #DIV/0!
Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Significantly After Target Deadline | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0!
Not yet due to be reported | 2 | 11.76% | 11.76% |  |  | Not yet due to be reported | 0 | 0% | 0% |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0!
Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0!
Deferred | 1 | 5.882% | 5.882% |  |  | Deferred | 1 | 5.882% | 5.882% |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0!
Deleted | 0 | 0% | 0% |  | Back to index | Deleted | 0 | 0% | 0% |  | Back to index | Deleted | 0 | #DIV/0! | #DIV/0! |  | Back to index | Deleted | 0 | #DIV/0! | #DIV/0! |  | Back to index
Totals | 17 |  |  |  |  | Totals | 17 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0
Due to be Reported | 14 |  |  |  |  | Due to be Reported | 16 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0
REGULATORY & COMMUNITY SUPPORT | [5 empty] | REGULATORY & COMMUNITY SUPPORT | [5 empty] | REGULATORY & COMMUNITY SUPPORT | [5 empty] | REGULATORY & COMMUNITY SUPPORT
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | 0 | 0% | 75% | 0% | 85.71% | Target Fully Achieved | 1 | 12.5% | 62.5% | 16.67% | 83.33% | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
On Track to be Achieved | 6 | 75% |  | 85.71% |  | On Track to be Achieved | 4 | 50% |  | 66.67% |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | Numerical Outturn Within 5% Tolerance | 0 | #DIV/0! |  | #DIV/0!
In Danger of Falling Behind Target | 1 | 12.5% | 12.5% | 14.29% | 14.29% | In Danger of Falling Behind Target | 1 | 12.5% | 12.5% | 16.67% | 16.67% | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Numerical Outturn Within 10% Tolerance | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[18 empty] | Target Partially Met | 0 | #DIV/0! |  | #DIV/0!
[18 empty] | Completion Date Within Reasonable Tolerance | 0 | #DIV/0! |  | #DIV/0!
Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Significantly After Target Deadline | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0!
Not yet due to be reported | 0 | 0% | 0% |  |  | Not yet due to be reported | 1 | 12.5% | 12.5% |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0!
Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0!
Deferred | 1 | 12.5% | 12.5% |  |  | Deferred | 1 | 12.5% | 12.5% |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0!
Deleted | 0 | 0% | 0% |  | Back to index | Deleted | 0 | 0% | 0% |  | Back to index | Deleted | 0 | #DIV/0! | #DIV/0! |  | Back to index | Deleted | 0 | #DIV/0! | #DIV/0! |  | Back to index
Totals | 8 |  |  |  |  | Totals | 8 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0
Due to be Reported | 7 |  |  |  |  | Due to be Reported | 6 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0

## 4. Status Tracking
Back to index
CP Ref | Measures | Target 2019/20 | Quarter 1 On track? (R/A/G) | Direction of Travel From Q1 to Q2 | Quarter 2 On track? (R/A/G) | Direction of Travel From Q2 to Q3 | Quarter 3 On track? (R/A/G) | Direction of Travel From Q3 to Q4 | Quarter 4 Achieved? (R/A/G)
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! | Ü
CR02 | Proactively Supporting the Boundary Review of East Staffordshire | Respond to Boundary Review Consultation in line with LGBCE timetable | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0 | Ý |  | è
CR03 | Proactively Supporting the Boundary Review of East Staffordshire | Prepare for Polling Place Review following completion of Boundary Review | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0 | Þ |  | ê
CR04 | Increasing Staffing Availability Through Reduced Sickness | Short Term Sickness Days Average: 2.98 days | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0 | n/a | ê
CR05 | Improve On The Average Time To Pay Creditors | Average Time To Pay Creditors: 10 days | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0 |  | é
CR06 | Legal and Assets | Commission a condition survey of the Council’s industrial units at Centrum 100 Business Park | Not Yet Due |  | Fully Achieved |  | 0 |  | 0 |  | è
CR07 | Legal and Assets | Carry out works to 8 of the Council’s commercial properties, as identified in the condition survey | Not Yet Due |  | Not yet due |  | 0 |  | 0
CR08 | Increase Capacity at Stapenhill Cemetery | Commence preparatory works for the expansion of Stapenhill Cemetery. | Fully Achieved |  | Fully Achieved |  | 0 |  | 0
CR09 | Market Hall Development Initiatives | Implement the outcome of the Market Hall future options review | Deferred |  | Deferred |  | 0 |  | 0
CR10 | Market Development Initiatives | Hold at least 7 commercial events in the Market Hall/Market Place | On Track to be Achieved |  | In Danger of Falling Behind Target |  | 0 |  | 0
CR11 | Market Hall Development Initiatives | Continue to benchmark Market Hall performance through APSE membership | On Track to be Achieved |  | Fully Achieved |  | 0 |  | 0
CR12 | Major Planning Applications Determined Within 13 Weeks | Top Quartile as measured against relevant MHCLG figures | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0
CR13 | Minor Planning Applications Determined Within 8 Weeks | Top Quartile as measured against relevant MHCLG figures | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0
CR14 | Other Planning Applications Determined in 8 Weeks | Top Quartile as measured against relevant MHCLG figures | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0
CR15 | Supporting Neighbourhood Plans | Rolleston Neighbourhood Plan Made | Deferred |  | Deferred |  | 0 |  | 0
CR16 | New and Refreshed Planning Policies | Finalise and adopt Brewery Building Conversion Design Guidance SPD | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0
CR17 | New and Refreshed Planning Policies | Publish Revised Statement of Community Involvement | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0
CR18 | New and Refreshed Planning Policies | Produce report and approach regarding Brownfield Register Part 2 | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0
CR19 | New and Refreshed Planning Policies | Revise and adopt Car parking SPD | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0
CR20 | Improve Burton town centre through significant environmental regeneration | Practical completion of the Station Street works via Amey | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0
CR21 | Improve Burton town centre through significant environmental regeneration | Deliver phase 1 of the Washlands Enhancement Project, fully utilising the GBSLEP Local Growth Fund monies | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0
CR22 | Work towards achieving transformation regeneration for Burton upon Trent of up to £25m through the Towns Fund | Working with the Town Deal Board, develop a Town Investment Plan for Burton and create a business case for funding | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0
CR23 | Support the delivery of affordable housing on brownfield land through the utilisation of S106 commuted sums | Review the progress of existing S106 commuted sums and identify new projects for potential funding | Not Yet Due |  | On Track to be Achieved |  | 0 |  | 0
CR24 | Identify a vision for the future regeneration of Uttoxeter | Member approval of the final Uttoxeter Masterplan | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0
CR25 | Promote local employment opportunities | Working with the Worklessness Action Group and local MP, support the delivery of three job fairs | In Danger of Falling Behind Target |  | On Track to be Achieved |  | 0 |  | 0
CR26 | Continue to support local businesses to grow and innovate | Create a grant fund to support small businesses and deliver throughout the year | Not Yet Due |  | On Track to be Achieved |  | 0 |  | 0
CR27 | Continue to support local businesses to grow and innovate | Provide direct support to 20 businesses through the Growth Hub Advisor contract | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0
CR28 | Continue to work effectively with regeneration partners | Continue to work with strategic tourism partners, such as the National Forest, the Campaign to Reopen the Ivanhoe Line and the TTTV, on the regeneration of the borough | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0
EHW01 | Delivering Better Services to Support Homelessness | Promote, monitor and report on the Burton and East Staffordshire Partnership, produce two activity reports during the year | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0
EHW02 | Delivering Better Services to Support Homelessness | Evaluate and build on the existing MHCLG/ESBC projects to target entrenched rough sleepers with two activity reports during the year Prepare and submit new applications to MHCLG as and when appropriate during the year | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0
EHW03 | Proactively reducing the number of empty homes in the borough | Produce annual contract performance report | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0
EHW04 | Delivering Better Services to Support Homelessness | Average time from appointment to initial decision for homeless applicants of 3 days | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0
EHW05 | Continue to Maximise Utilisation of Self Contained Temporary Accommodation for Homeless Applicants | Reduce ‘Key to Key’ Void Turnaround to an average of 6 working days | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0
EHW06 | Improving our Housing Strategy Initiatives | Refreshed Housing Strategy | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0
EHW07 | Improving our Housing Strategy Initiatives | Report opportunities for improving Housing Register Service | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0
EHW08 | Maintain Top Quartile Performance For Street Cleansing - Litter | Maintain Top Quartile Performance | Not Yet Due |  | On Track to be Achieved |  | 0 |  | 0
EHW09 | Maintain Top Quartile Performance For Street Cleansing - Detritus | Maintain Top Quartile Performance | Not Yet Due |  | On Track to be Achieved |  | 0 |  | 0
EHW10 | Maintain Top Quartile Performance For Street Cleansing - Graffiti | Maintain Top Quartile Performance | Not Yet Due |  | On Track to be Achieved |  | 0 |  | 0
EHW11 | Maintain Top Quartile Performance For Street Cleansing – Fly-Posting | Maintain Top Quartile Performance | Not Yet Due |  | On Track to be Achieved |  | 0 |  | 0
EHW12 | Maintain Top Quartile Performance On Recycling | Household Waste Recycled and Composted: Maintain Top Quartile Performance | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0
EHW13 | Maintain Top Quartile Performance On Waste Reduction | Residual Household Waste Per Household: Maintain Top Quartile Performance | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0
EHW14 | Open Spaces Initiatives | Develop a Borough wide parks development plan | Not Yet Due |  | Not Yet Due |  | 0 |  | 0
EHW15 | Open Spaces Initiatives | Achieve 2 in bloom gold awards and support Uttoxeter in the 2020 National In bloom awards | Deferred |  | Deferred |  | 0 |  | 0
EHW17 | Open Spaces Initiatives | Increase the marks awarded to the 9 parks in the “It’s Your Neighbourhood” Parks category by an average of 10% | Deferred |  | Deferred |  | 0 |  | 0
EHW18 | Develop Tourism within the Borough | Develop a tactical approach and plan for tourism in East Staffordshire | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0
EHW19 | Compliance Inspections in support of Public Protection | Undertake two high profile initiatives aimed at monitoring compliance and ensuring public protection | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0
EHW20 | Community & Civil Enforcement Initiatives | Undertake 8 focused initiatives (including fly tipping) across the Borough and deliver at least 6 education programs in local schools. | In Danger of Falling Behind Target |  | In Danger of Falling Behind Target |  | 0 |  | 0
EHW21 | Development of the Selective Licensing Scheme | Selective Licensing Designation Approved | Deferred |  | Deferred |  | 0 |  | 0
EHW22 | Development of the Selective Licensing Scheme | Selective Licensing Third Year Review Complete | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0
EHW23 | Partnership working with Trading Standards Regarding Tenant Fees | Undertake a Targeted Initiative to Investigate and Enforce Compliance with Tenant Fees Legislation | On Track to be Achieved |  | Not Yet Due |  | 0 |  | 0
EHW24 | Disabled Facilities Grant Review | Complete Annual Review of Disabled Facilities Grant Service | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0
EHW25 | Climate Change & Air Quality Policy | Consider the declaration of a Climate Emergency and implement and monitor a Climate Change action plan-including an annual update | On Track to be Achieved |  | Fully Achieved |  | 0 |  | 0
EHW26 | Multi-agency Initiatives to Combat Modern Slavery | Carry out Covid-19 compliance checks across the Borough and report progress on a quarterly basis | On Track to be Achieved |  | On Track to be Achieved |  | 0 |  | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!