## Index
East Staffordshire Borough Council
Corporate Plan 2020/21 - Performance Monitoring Spreadsheet
1. All Data
Summary Tables
Quarter 1 Summary Table
Quarter 2 Summary Table
Quarter 3 Summary Table
Quarter 4 Summary Table
Breakdown of peformance by Corporate Plan priorty
2a. % By Priority
2b. Charts by Priority
4. Status Tracking
Custom Pivot Table

## 1. All Data
[6 empty] | QUARTER 1: April - June 2020 |  |  |  | QUARTER 2: July - September 2020 |  |  |  |  | QUARTER 3: October - December 2020 |  |  |  |  | QUARTER 4: January - March 2021
Reporting Officer | Reporting Officer | Corporate Plan Ref Number | Measures | Target 2020/21 | Target Date | Quarter 1 (April - June 2020) | End of year forecast as at end of Q1 (NUMERICAL INDICATORS ONLY) | Quarter 1 On Track? (R/A/G) | Comments / Further action (Q1) (IF APPLICABLE) | Quarter 2 (July - September 2020) | Year to date (April - Sept 2020) (NUMERICAL INDICATORS ONLY) | End of year forecast as at end of Q2 (NUMERICAL INDICATORS ONLY) | Quarter 2 On Track? (R/A/G) | Comments / Further action (Q2) (IF APPLICABLE) | Quarter 3 (October - December 2020) | Year to date (April - Dec 2020) (NUMERICAL INDICATORS ONLY) | End of year forecast as at end of Q3 (NUMERICAL INDICATORS ONLY) | Quarter 3 On Track? (R/A/G) | Comments / Further action (Q3) (IF APPLICABLE) | Quarter 4 (January - March 2021) | Cumulative Annual Outturn (NUMERICAL INDICATORS ONLY) | End of Year Achieved? (R/A/G) | Comments / Further action (Q4) (IF APPLICABLE) | Qtr | Service | Team | Corporate Priority | Portfolio |  | CP order | Previously identified as potentially impacted by CV19
| James Abbott | CR02 | Proactively Supporting the Boundary Review of East Staffordshire | Respond to Boundary Review Consultation in line with LGBCE timetable |  | The LGBCE has resumed the review of East Staffordshire, following a pause during the Covid-19 lockdown. The consultation on the LGBCE's proposed boundaries will run until September 7th 2020 & ESBC will respond from a electoral management perspective regarding the suggested names for the proposed new warded parishes. |  | On Track to be Achieved | [16 empty] | Andy O'Brien | Electoral Services | Community Regeneration | Leader | L19 | 2 | *
| Nicola Gilligan | CR03 | Proactively Supporting the Boundary Review of East Staffordshire | Prepare for Polling Place Review following completion of Boundary Review | March 2021 | Planning is in the preliminary stages in line with the LGBCE timetable and their initial recommendations published on 30 June 2020. LGBCE’s final recommendations are due to be published 1 December 2020. |  | On Track to be Achieved | [16 empty] | Andy O'Brien | Electoral Services | Community Regeneration | Leader | L20 | 3 | *
| Linda McDonald | CR04 | Increasing Staffing Availability Through Reduced Sickness | Short Term Sickness Days Average: 2.98 days |  | 0.21 days | 2.5 days | On Track to be Achieved | Q1 2019/20 (last year) 0.69 days | [15 empty] | Andy O'Brien | HR & Payroll | Community Regeneration | Leader | L21 | 4 | *
| Linda McDonald | CR05 | Improve On The Average Time To Pay Creditors | Average Time To Pay Creditors: 10 days |  | 9 days | 10 days | On Track to be Achieved | Q1 2019/20 (last year) = 10 days | [15 empty] | Andy O'Brien | HR & Payroll | Community Regeneration | Leader | L22 | 5 | *
| Angela Wakefield | CR06 | Legal and Assets | Commission a condition survey of the Council’s industrial units at Centrum 100 Business Park | September 2020 |  |  | Not Yet Due | [16 empty] | Andy O'Brien | Assets & Estates | Community Regeneration | Leader | L23 | 6 | *
| Angela Wakefield | CR07 | Legal and Assets | Carry out works to 8 of the Council’s commercial properties, as identified in the condition survey | March 2021 |  |  | Not Yet Due | [16 empty] | Andy O'Brien | Assets & Estates | Community Regeneration | Leader | L24 | 7 | *
| Michael Hovers | CR08 | Increase Capacity at Stapenhill Cemetery | Commence preparatory works for the expansion of Stapenhill Cemetery. | December 2020 | Consultants have been asked to update their revised quote from November 2019. Revised quote has been received and stage 1 investigation works have been ordered. |  | Fully Achieved | [16 empty] | Mark Rizk | Communities, Open Spaces & Facilities | Community Regeneration | Leisure, Culture & Tourism | LCT10 | 8 | *
| Michael Hovers | CR09 | Market Hall Development Initiatives | Implement the outcome of the Market Hall future options review | March 2021 | Deferred until later within this financial year, as this target is linked to the developing Stronger Towns work. Target to be revisited in October 2020. |  | Deferred | [16 empty] | Mark Rizk | Markets | Community Regeneration | Leisure, Culture & Tourism | LCT11 | 9 | *
| Michael Hovers | CR10 | Market Development Initiatives | Hold at least 7 commercial events in the Market Hall/Market Place | March 2021 | Whilst there has been an impact on opportunities to hold commercial events in and around the Market Hall during quarter 1, opportunities do exist to hold events in the Market Place moving forward. |  | On Track to be Achieved | [16 empty] | Mark Rizk | Markets | Community Regeneration | Leisure, Culture & Tourism | LCT12 | 10 | *
| Michael Hovers | CR11 | Market Hall Development Initiatives | Continue to benchmark Market Hall performance through APSE membership | March 2021 | We have joined APSE |  | On Track to be Achieved | [16 empty] | Mark Rizk | Markets | Community Regeneration | Leisure, Culture & Tourism | LCT13 | 11 | *
| Ashley Baldwin | CR12 | Major Planning Applications Determined Within 13 Weeks | Top Quartile as measured against relevant MHCLG figures |  | 8 Applications all within time = 100% |  | On Track to be Achieved | Within top quartile based on CLG latest quarter reported. | [15 empty] | Sal Khan | Planning | Community Regeneration | Regeneration & Planning Policy | RPP08 | 12 | *
| Ashley Baldwin | CR13 | Minor Planning Applications Determined Within 8 Weeks | Top Quartile as measured against relevant MHCLG figures |  | 63 Applications of which 60 in time = 95% |  | On Track to be Achieved | Within top quartile based on CLG latest quarter reported. | [15 empty] | Sal Khan | Planning | Community Regeneration | Regeneration & Planning Policy | RPP09 | 13 | *
| Ashley Baldwin | CR14 | Other Planning Applications Determined in 8 Weeks | Top Quartile as measured against relevant MHCLG figures |  | 124 Applications all within time = 100% |  | On Track to be Achieved | Within top quartile based on CLG latest quarter reported. | [15 empty] | Sal Khan | Planning | Community Regeneration | Regeneration & Planning Policy | RPP10 | 14 | *
| Ashley Baldwin | CR15 | Supporting Neighbourhood Plans | Rolleston Neighbourhood Plan Made | Date TBC | Rolleston Neighbourhood Plan referendum delayed due to COVID-19. Target deferred to the next Corporate Plan year, as all elections have been postponed for 2020/21 |  | Deferred | [16 empty] | Sal Khan | Planning | Community Regeneration | Regeneration & Planning Policy | RPP11 | 15 | *
| Ashley Baldwin | CR16 | New and Refreshed Planning Policies | Finalise and adopt Brewery Building Conversion Design Guidance SPD | October 2020 | On track - draft document have been considered by CMT and LDL. |  | On Track to be Achieved | [16 empty] | Sal Khan | Planning | Community Regeneration | Regeneration & Planning Policy | RPP12 | 16 | *
| Ashley Baldwin | CR17 | New and Refreshed Planning Policies | Publish Revised Statement of Community Involvement | March 2021 | On track - draft document have been considered by CMT and LDL. |  | On Track to be Achieved | [16 empty] | Sal Khan | Planning | Community Regeneration | Regeneration & Planning Policy | RPP13 | 17 | *
| Ashley Baldwin | CR18 | New and Refreshed Planning Policies | Produce report and approach regarding Brownfield Register Part 2 | October 2020 | On track - officers preparing documents to be considered in due course by CMT, LDL and Cabinet |  | On Track to be Achieved | [16 empty] | Sal Khan | Planning | Community Regeneration | Regeneration & Planning Policy | RPP14 | 18
| Ashley Baldwin | CR19 | New and Refreshed Planning Policies | Revise and adopt Car parking SPD | October 2020 | On track - draft document have been considered by CMT and LDL. |  | On Track to be Achieved | [16 empty] | Sal Khan | Planning | Community Regeneration | Regeneration & Planning Policy | RPP15 | 19 | *
| Simon Humble | CR20 | Improve Burton town centre through significant environmental regeneration | Practical completion of the Station Street works via Amey | October 2020 | The Works process started in late March 2020 and was able to continue throughout the lockdown period as the works were categorised as essential. The works process is currently on programme and on target for practical completion to be achieved by the end of October 2020. |  | On Track to be Achieved | [16 empty] | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP16 | 20
| Thomas Deery | CR21 | Improve Burton town centre through significant environmental regeneration | Deliver phase 1 of the Washlands Enhancement Project, fully utilising the GBSLEP Local Growth Fund monies | March 2021 | The funding profile for the Washlands has been reshaped, meaning that there is no longer a requirement for £1m to be spend before March 2021. This will enable the single phased delivery of the project and so phase 1 will now comprise the remaining design and development work, such as the planning application, permitting, and appointment of contractors. |  | On Track to be Achieved | [16 empty] | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP17 | 21 | *
| Thomas Deery | CR22 | Work towards achieving transformation regeneration for Burton upon Trent of up to £25m through the Towns Fund | Working with the Town Deal Board, develop a Town Investment Plan for Burton and create a business case for funding | March 2021 | A Town Investment Plan is being developed, following the publication of Government guidance in June 2020. This is intended to be submitted in October 2020. |  | On Track to be Achieved | [16 empty] | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP18 | 22 | *
| Thomas Deery | CR23 | Support the delivery of affordable housing on brownfield land through the utilisation of S106 commuted sums | Review the progress of existing S106 commuted sums and identify new projects for potential funding | October 2020 |  |  | Not Yet Due | [16 empty] | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP19 | 23
| Thomas Deery | CR24 | Identify a vision for the future regeneration of Uttoxeter | Member approval of the final Uttoxeter Masterplan | December 2020 | Cushman and Wakefield were appointed in late March 2020 as consultants to carry out an assessment of the success of the original Uttoxeter Masterplan from 2003 along with the creation a new version. Cushman and Wakefield have already completed the assessment of the original masterplan and are now working on the development of the baseline study and stakeholder engagement process. |  | On Track to be Achieved | [16 empty] | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP20 | 24 | *
| Thomas Deery | CR25 | Promote local employment opportunities | Working with the Worklessness Action Group and local MP, support the delivery of three job fairs | March 2021 | The first job fair of the year was planned for June 2020 and this was unfortunately cancelled as a result of COVID-19. It is not yet determined whether 3 can still be achieved in the year using alternative methods (such as virtual). |  | In Danger of Falling Behind Target | [16 empty] | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP21 | 25 | *
| Thomas Deery | CR26 | Continue to support local businesses to grow and innovate | Create a grant fund to support small businesses and deliver throughout the year | March 2021 |  |  | Not Yet Due | [16 empty] | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP22 | 26 | *
| Thomas Deery | CR27 | Continue to support local businesses to grow and innovate | Provide direct support to 20 businesses through the Growth Hub Advisor contract | March 2021 | Businesses are being supported by advice from the Growth Hub Advisor contract, however the nature of this advice has notably changed to reflect COVID-19. An exact number of businesses supported has not yet been issued, but it is believed to be proportionate to the quarter. |  | On Track to be Achieved | [16 empty] | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RRP23 | 27 | *
| Thomas Deery | CR28 | Continue to work effectively with regeneration partners | Continue to work with strategic tourism partners, such as the National Forest, the Campaign to Reopen the Ivanhoe Line and the TTTV, on the regeneration of the borough | March 2021 | Work continues with these organisations. The Brook Hollows project is being taken forwards with the TTTV and now in partnership with the EA. The Ivanhoe Line project is progressing well, however members of that group were affected by Shielding requirements. |  | On Track to be Achieved | In May 2020 the government announced the Ivanhoe line would be 1 of 10 campaigns to received support from the 'restoring your railways fund' | [15 empty] | Andy O'Brien | Enterprise | Community Regeneration | Regeneration & Planning Policy | RPP24 | 28 | *
| Brett Atkinson | EHW01 | Delivering Better Services to Support Homelessness | Promote, monitor and report on the Burton and East Staffordshire Partnership, produce two activity reports during the year | (Sep 20 / Mar 21) | The Partnership has been instrumental in responding to the lockdown and associated 'Everyone In' campaign. A virtual meeting to debrief and consider how we can consolidate the gains that have been made is taking place in July. |  | On Track to be Achieved | [16 empty] | Sal Khan | Housing Options | Environment and Health & Wellbeing | Environment & Housing | EH14 | 29
| Brett Atkinson | EHW02 | Delivering Better Services to Support Homelessness | Evaluate and build on the existing MHCLG/ESBC projects to target entrenched rough sleepers with two activity reports during the year Prepare and submit new applications to MHCLG as and when appropriate during the year | (Sept 2020 / Mar 2021) | The projects that are funded by the MHCLG's 'Rough Sleeping Initiative' have been effective in supporting individuals to exit from the 'Everyone In' campaign with settled solutions. There is an initial proposal for an additional project, although the MHCLG's prospectus to secure the funding has not yet been released. |  | On Track to be Achieved | [16 empty] | Sal Khan | Housing Options | Environment and Health & Wellbeing | Environment & Housing | EH15 | 30
| Brett Atkinson | EHW03 | Proactively reducing the number of empty homes in the borough | Produce annual contract performance report | March 2021 | This work is well underway, and early analysis indicates that the contract has delivered a strong set of results. |  | On Track to be Achieved | [16 empty] | Sal Khan | Housing Options | Environment and Health & Wellbeing | Environment & Housing | EH16 | 31
| Brett Atkinson | EHW04 | Delivering Better Services to Support Homelessness | Average time from appointment to initial decision for homeless applicants of 3 days |  | The Housing Options Team made 63 initial decisions this quarter, with an average time to decision of 0.75 days. | 1 day | On Track to be Achieved | [16 empty] | Sal Khan | Housing Options | Environment and Health & Wellbeing | Environment & Housing | EH17 | 32 | *
| Brett Atkinson | EHW05 | Continue to Maximise Utilisation of Self Contained Temporary Accommodation for Homeless Applicants | Reduce ‘Key to Key’ Void Turnaround to an average of 6 working days |  | There was only 1 'Key to Key' occasion during this quarter; this is because households in B&B were prioritised to be moved directly into settled accommodation to avoid the number of contacts. This 1 move took 2 working days. | 5 days | On Track to be Achieved | [16 empty] | Sal Khan | Housing Options | Environment and Health & Wellbeing | Environment & Housing | EH18 | 33
| Brett Atkinson | EHW06 | Improving our Housing Strategy Initiatives | Refreshed Housing Strategy | December 2020 | The lay out and structure of the document has been drafted, with a move toward the look and feel of the current Homelessness Strategy. |  | On Track to be Achieved | [16 empty] | Sal Khan | Housing Options | Environment and Health & Wellbeing | Environment & Housing | EH19 | 34
| Brett Atkinson | EHW07 | Improving our Housing Strategy Initiatives | Report opportunities for improving Housing Register Service | December 2020 | A streamlined digital application system has been undergoing rigorous testing and is due to launch to the public next month. |  | On Track to be Achieved | [16 empty] | Sal Khan | Housing Options | Environment and Health & Wellbeing | Environment & Housing | EH20 | 35 | *
| Paul Farrer | EHW08 | Maintain Top Quartile Performance For Street Cleansing - Litter | Maintain Top Quartile Performance |  | Not yet due - surveys run April - July |  | Not Yet Due | [16 empty] | Sal Khan | Environment | Environment and Health & Wellbeing | Environment & Housing | EH21 | 36 | *
| Paul Farrer | EHW09 | Maintain Top Quartile Performance For Street Cleansing - Detritus | Maintain Top Quartile Performance |  | Not yet due - surveys run April - July |  | Not Yet Due | [16 empty] | Sal Khan | Environment | Environment and Health & Wellbeing | Environment & Housing | EH22 | 37 | *
| Paul Farrer | EHW10 | Maintain Top Quartile Performance For Street Cleansing - Graffiti | Maintain Top Quartile Performance |  | Not yet due - surveys run April - July |  | Not Yet Due | [16 empty] | Sal Khan | Environment | Environment and Health & Wellbeing | Environment & Housing | EH23 | 38 | *
| Paul Farrer | EHW11 | Maintain Top Quartile Performance For Street Cleansing – Fly-Posting | Maintain Top Quartile Performance |  | Not yet due - surveys run April - July |  | Not Yet Due | [16 empty] | Sal Khan | Environment | Environment and Health & Wellbeing | Environment & Housing | EH24 | 39 | *
| Paul Farrer | EHW12 | Maintain Top Quartile Performance On Recycling | Household Waste Recycled and Composted: Maintain Top Quartile Performance |  | 46.28% - estimated |  | On Track to be Achieved | [16 empty] | Sal Khan | Environment | Environment and Health & Wellbeing | Environment & Housing | EH25 | 40 | *
| Paul Farrer | EHW13 | Maintain Top Quartile Performance On Waste Reduction | Residual Household Waste Per Household: Maintain Top Quartile Performance |  | 144.65kg - estimated. Collection tonnages are higher than normal for Q1 due to the impact of the pandemic. This may effect the outturn figure. |  | On Track to be Achieved | [16 empty] | Sal Khan | Environment | Environment and Health & Wellbeing | Environment & Housing | EH26 | 41 | *
| Michael Hovers | EHW14 | Open Spaces Initiatives | Develop a Borough wide parks development plan | December 2020 |  |  | Not Yet Due | [16 empty] | Mark Rizk | Communities, Open Spaces & Facilities | Environment and Health & Wellbeing | Leisure, Culture & Tourism | LCT14 | 42
| Michael Hovers | EHW15 | Open Spaces Initiatives | Achieve 2 in bloom gold awards and support Uttoxeter in the 2020 National In bloom awards | September 2020 | Target to be deferred to the next Corporate Plan year, as these awards have been postponed by the organiser until 2021/22 |  | Deferred | [16 empty] | Mark Rizk | Communities, Open Spaces & Facilities | Environment and Health & Wellbeing | Leisure, Culture & Tourism | LCT15 | 43 | *
| Michael Hovers | EHW16 | Open Spaces Initiatives | Achieve 1 Green Flag award | September 2020 | Target to be deferred to the next Corporate Plan year, as these awards have been postponed by the organiser until 2021/22 |  | Deferred | [16 empty] | Mark Rizk | Communities, Open Spaces & Facilities | Environment and Health & Wellbeing | Leisure, Culture & Tourism | LCT16 | 44 | *
| Michael Hovers | EHW17 | Open Spaces Initiatives | Increase the marks awarded to the 9 parks in the “It’s Your Neighbourhood” Parks category by an average of 10% | September 2020 | Target to be deferred to the next Corporate Plan year, as these awards have been postponed by the organiser until 2021/22 |  | Deferred | [16 empty] | Mark Rizk | Communities, Open Spaces & Facilities | Environment and Health & Wellbeing | Leisure, Culture & Tourism | LCT17 | 45 | *
| Michael Hovers | EHW18 | Develop Tourism within the Borough | Develop a tactical approach and plan for tourism in East Staffordshire | October 2020 | Draft document to be shared with the Deputy Leader early in Quarter 2 |  | On Track to be Achieved | [16 empty] | Mark Rizk | Communities, Open Spaces & Facilities | Environment and Health & Wellbeing | Leisure, Culture & Tourism | LCT18 | 46
| Rachel Liddle | EHW19 | Compliance Inspections in support of Public Protection | Undertake two high profile initiatives aimed at monitoring compliance and ensuring public protection | March 2021 | Initiatives currently being taken to investigate Covid-19 compliance in businesses that are starting to reopen |  | On Track to be Achieved | [16 empty] | Mark Rizk | Environmental Health | Environment and Health & Wellbeing | Regulatory & Community Support | RCS04 | 47 | *
| Carol Flannery | EHW20 | Community & Civil Enforcement Initiatives | Undertake 8 focused initiatives (including fly tipping) across the Borough and deliver at least 6 education programs in local schools. | March 2021 | Planned initiatives have not yet taken place. This is due to school closures and the CCEO's have been involved in Covid-19 related tasks, shielding or WFH. |  | In Danger of Falling Behind Target | Alternative options being looked into such as other community groups i.e. scouts, brownies, cadets. Those contacted are functioning remotely. | [15 empty] | Mark Rizk | Civil Enforcement | Environment and Health & Wellbeing | Regulatory & Community Support | RCS05 | 48 | *
| Rachel Liddle | EHW21 | Development of the Selective Licensing Scheme | Selective Licensing Designation Approved | Date TBC | Target to be deferred to the next Corporate Plan year, as there is currently no indication that the necessary Government guidance will be received this year. |  | Deferred | [16 empty] | Mark Rizk | Environmental Health | Environment and Health & Wellbeing | Regulatory & Community Support | RCS06 | 49 | *
| Rachel Liddle | EHW22 | Development of the Selective Licensing Scheme | Selective Licensing Third Year Review Complete | November 2020 | On track to be completed |  | On Track to be Achieved | [16 empty] | Mark Rizk | Environmental Health | Environment and Health & Wellbeing | Regulatory & Community Support | RCS07 | 50 | *
| Rachel Liddle | EHW23 | Partnership working with Trading Standards Regarding Tenant Fees | Undertake a Targeted Initiative to Investigate and Enforce Compliance with Tenant Fees Legislation | March 2021 | 1 case of non compliance is currently being investigated in partnership with Staffordshire County Council |  | On Track to be Achieved | [16 empty] | Mark Rizk | Environmental Health | Environment and Health & Wellbeing | Regulatory & Community Support | RCS08 | 51 | *
| Rachel Liddle | EHW24 | Disabled Facilities Grant Review | Complete Annual Review of Disabled Facilities Grant Service | December 2020 | On track to be completed |  | On Track to be Achieved | [16 empty] | Mark Rizk | Environmental Health | Environment and Health & Wellbeing | Regulatory & Community Support | RCS09 | 52 | *
| Rachel Liddle | EHW25 | Climate Change & Air Quality Policy | Consider the declaration of a Climate Emergency and implement and monitor a Climate Change action plan-including an annual update | August 2020 | The report for a Climate Change Emergency Declaration and supporting action plan has been completed and is being taken to the groups in July for approval in August. |  | On Track to be Achieved | [16 empty] | Mark Rizk | Environmental Health | Environment and Health & Wellbeing | Regulatory & Community Support | RCS10 | 53 | *
| Rachel Liddle | EHW26 | Multi-agency Initiatives to Combat Modern Slavery | Carry out Covid-19 compliance checks across the Borough and report progress on a quarterly basis | March 2021 | Focussed covid compliance checks are being undertaken in licensed premises along with targeted initiatives to businesses within Uxbridge Street, Waterloo Street and Horninglow Road. Business packs have been distributed along with letters advising of additional restrictions that shops should put in place to reduce customer numbers and ensure customers wear face coverings. |  | On Track to be Achieved | [16 empty] | Mark Rizk | Environmental Health | Environment and Health & Wellbeing | Regulatory & Community Support | RCS11 | 54 | *
| Lisa Turner | VFM01 | Continue to Improve Financial Resilience | Compliance with HMRC VAT Digitalisation Requirements | 31st March 2020 | HMRC have deferred this requirement until April 2021 due to Covid-19 (target date revised to refelect this) |  | On Track to be Achieved | [16 empty] | Sal Khan | FMU | Value for Money Council | Leader | L01 | 55 | *
| Lisa Turner | VFM02 | Continue to Improve Financial Resilience | Review compliance against CIPFA FM Code of Practice | December 2020 |  |  | Not Yet Due | [16 empty] | Sal Khan | FMU | Value for Money Council | Leader | L02 | 56
| Lisa Turner | VFM03 | Continue to Improve Financial Resilience | Review and Refresh Financial Regulations | March 2021 |  |  | Not Yet Due | [16 empty] | Sal Khan | FMU | Value for Money Council | Leader | L03 | 57
| Lisa Turner | VFM04 | Continue to Improve Financial Resilience | Review and Refresh Contract Procedure Rules | March 2021 |  |  | Not Yet Due | [16 empty] | Sal Khan | FMU | Value for Money Council | Leader | L04 | 58
| Lisa Turner | VFM05 | Continue to Improve Financial Resilience | Undertake a Procurement Exercise for the Council’s Insurance and related support | October 2020 | Mini competition to appoint insurance broker and agreed process and timescales for procurement of insurer. |  | On Track to be Achieved | [16 empty] | Sal Khan | FMU | Value for Money Council | Leader | L05 | 59
| James Abbott | VFM06 | Continue to Improve Financial Resilience | Develop Procurement Policy | June 2020 | The newly developed Procurement Policy has been drafted. This will be considered further by senior officers and Members in July / August and is scheduled to be presented to Cabinet in September. There has been a slight delay in the Policy being approved due to additional pressures on resource arising from the COVID-19 situation. |  | Off Target | [16 empty] | Sal Khan | Programmes & Transformation | Value for Money Council | Leader | L06 | 60 | *
| Lisa Turner | VFM07 | Responding to Significant Local Government Finance Changes and Assessing the Impact on the Council’s Financial Position | Activities Throughout the Year Reported in Line with the Timed Responses | March 2021 | Due to Covid-19 the government has announced the many of the expected reforms will be deferred. Officers are monitoring developments and proactively engaging with Government in relation to developments in respect of additional funding in 2020/21 towards Covid-19 related pressures and also the approach to funding for 2021/22. |  | On Track to be Achieved | [16 empty] | Sal Khan | FMU | Value for Money Council | Leader | L07 | 61
| Lisa Turner | VFM08 | Set the MTFS for 2021/22 onwards | Set Budget for Council Approval | February 2021 | Work to commence in Quarter 2. |  | Not Yet Due | [16 empty] | Sal Khan | FMU | Value for Money Council | Leader | L08 | 62
| Lisa Turner | VFM09 | Savings targets for 2020/21 | Achieve Savings Targets as Stated in the Medium Term Financial Strategy | March 2021 | Current forecast indicates that pressures arising from Covid-19 exceed the additional funding support from Government. |  | Deleted | [16 empty] | Sal Khan | FMU | Value for Money Council | Leader | L09 | 63 | *
| Lisa Turner | VFM10 | Having an approved Statement of Accounts | Submit Statement of Accounts to Audit Committee by the earlier Statutory Deadline | 30th November 2020 | Statutory deadlines have been amended due to Covid-19. This has been moved from 31st July to 30th November and the Council is currently working towards sign-off in September. |  | On Track to be Achieved | [16 empty] | Sal Khan | FMU | Value for Money Council | Leader | L10 | 64 | *
| Guy Thornhill | VFM11 | Prepare for a Corporate ICT refresh | Commence Desktop Hardware Renewal | June 2020 | Standard models identified, pilot group to deploy |  | Fully Achieved | [16 empty] | Sal Khan | ICT | Value for Money Council | Leader | L11 | 65 | *
| Guy Thornhill | VFM12 | Explore opportunities for shared service/income generation | Report on ICT income generation | June 2020 | Discussions are ongoing with another District LA regarding how ESBC can provide professional support with their ICT Strategy, ICT architecture and service delivery. However scoping for this piece of work has been impacted by Covid-19 and it is anticipated that it will be finalised before the end of the year. |  | Off Target | [16 empty] | Sal Khan | ICT | Value for Money Council | Leader | L12 | 66 | *
| Daniel Arnold | VFM13 | Continuing to digitise SMARTER services | Digital Strategy Refreshed and approved | October 2020 | Development of the Strategy is underway and is expected to be approved in October. |  | On Track to be Achieved | [16 empty] | Sal Khan | Programmes & Transformation | Value for Money Council | Leader | L13 | 67
| Daniel Arnold | VFM14 | Continuing to digitise SMARTER services | 80% of revised Digital Strategy targets achieved | March 2021 | Strategy due to be approved by October |  | Not Yet Due | [16 empty] | Sal Khan | Programmes & Transformation | Value for Money Council | Leader | L14 | 68
| Daniel Arnold | VFM15 | Continuing to digitise SMARTER services | GeoPlaces Gold Standard in ESBC related categories | March 2021 | Data is currently rated as 'Gold' in 6 out of 10 ESBC related categories, 2 categories are rated silver and 2 are rated as bronze. Due to revised thresholds introduced every May, it was anticipated that some categories would be rated as bronze or silver, and it is expected that Gold will be achieved by year end in line with the target. |  | On Track to be Achieved | [16 empty] | Sal Khan | Programmes & Transformation | Value for Money Council | Leader | L15 | 69
| James Abbott | VFM16 | Improved Resilience Planning | Review of Rest Centres Complete | March 2021 |  |  | Not Yet Due | [16 empty] | Sal Khan | Democratic Services & Emergency Planning | Value for Money Council | Leader | L16 | 70
| James Abbott | VFM17 | LGA Peer Review | Work with the LGA to deliver a peer review to another council/s to build up to hosting one in East Staffordshire | October 2020 | It has been indicated to the Council that the Peer Review programme is not proceeding. |  | Deleted | [16 empty] | Andy O'Brien | Programmes & Transformation | Value for Money Council | Leader | L17 | 71 | *
| Sarah Richardson | VFM18a | Continue to Maximise Income Through Effective Collection Processes (Previously BVPI9) | Collection Rates of Council Tax : 98% |  | 28.7% | 98% | On Track to be Achieved | Target is annual. Current collection is 0.9% down on the same period 2019/20. Formal recovery procedures are starting July 2020. | [15 empty] | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Environment & Housing | EH01 | 72 | *
| Sarah Richardson | VFM18b | Continue to Maximise Income Through Effective Collection Processes (Previously BVPI10) | Collection Rates of NNDR : 99% |  | 25.51% | 99% | On Track to be Achieved | Target is annual. Current collection is 7.51% down on the same period 2019/20. Formal recovery procedures are starting July 2020. | [15 empty] | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Environment & Housing | EH01 | 73 | *
| Sarah Richardson | VFM19a | Continue to Maximise Income Through Effective Collection Processes: Reduce Former Years Arrears for Council Tax; NNDR; Sundry Debts | Former Years Arrears for Council Tax £2,500,000 (net of credits, amounts on arrangement and identified write offs) |  | 2220350.39 | 2000000 | On Track to be Achieved | Target is annual. Formal recovery procedures are starting July 2020 following suspension during Covid-19 lockdown. | [15 empty] | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Environment & Housing | EH02 | 74 | *
| Sarah Richardson | VFM19b | Continue to Maximise Income Through Effective Collection Processes: Reduce Former Years Arrears for Council Tax; NNDR; Sundry Debts | Former Years Arrears for NNDR £2,000,000 (net of credits, amounts on arrangement and identified write offs) |  | 2155042.42 | 2000000 | On Track to be Achieved | Target is annual. Formal recovery procedures are starting July 2020 following suspension during Covid-19 lockdown. | [15 empty] | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Environment & Housing | EH02 | 75 | *
| Sarah Richardson | VFM19c | Continue to Maximise Income Through Effective Collection Processes: Reduce Former Years Arrears for Council Tax; NNDR; Sundry Debts | Current years arrears for sundry debts (older than 90 days) £80,000 (net of credits, amounts on arrangement and identified write offs) |  | 0 | 40000 | On Track to be Achieved | Target is annual. | [15 empty] | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Environment & Housing | EH02 | 76 | *
| Sarah Richardson | VFM20a | Maintaining excellent customer access to services with face-to-face and telephony enquiries | 99% of CSC and Telephony Team Enquiries Resolved at First Point of Contact |  | None | n/a | Not Yet Due | The CSCs were closed on 23rd March due to lockdown restrictions imposed by Govt. No date has yet been agreed for their re-opening. | [15 empty] | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Environment & Housing | EH03 | 77 | *
| Sarah Richardson | VFM20b | Maintaining excellent customer access to services with face-to-face and telephony enquiries | Minimum 75% Telephony Team Calls Answered Within 10 Seconds |  | 79% All services are being offered via telephone or online enquiries. High call volumes on Switchboard due to Waste changes (initial suspension of brown bin waste and re-introduction of bulky waste collections). Switchboard staff have now taken over calls from residents who are classified as Covid-19 vulnerable, and are being signposted to the relevant support agencies in partnership with the County Council. | 75% | On Track to be Achieved | [16 empty] | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Environment & Housing | EH03 | 78 | *
| Sarah Richardson | VFM21 | Continue to Improve the Ways We Provide Benefits to Those Most in Need: | Time Taken to Process Benefit New Claims and Change Events (Previously NI 181) 5 days |  | 5.12 days Claims processing has improved during June now that claims made as a result of the pandemic have reduced to normal levels. We anticipate the number of claims to increase over the coming months as the Govt's furlough scheme is pared back. | 5 days | On Track to be Achieved | [16 empty] | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Environment & Housing | EH04 | 79 | *
| Sarah Richardson | VFM22ai | Working Towards the Reduction of Claimant Error Housing Benefit Overpayments (HBOPs) | % HBOPs recovered during the year; 90% |  | 145.3% | 80% | On Track to be Achieved | [16 empty] | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Environment & Housing | EH05 | 80 | *
| Sarah Richardson | VFM22aii | Working Towards the Reduction of Claimant Error Housing Benefit Overpayments (HBOPs) | % in year HBOPs recovered during the year; 70% |  | 69% | 70% | On Track to be Achieved | [16 empty] | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Environment & Housing | EH05 | 81 | *
| Sarah Richardson | VFM22b | Working Towards the Reduction of Claimant Error Housing Benefit Overpayments (HBOPs) | % of HBOPS Processed and on Payment Arrangement; 90% |  | 91% | 90% | On Track to be Achieved | [16 empty] | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Environment & Housing | EH05 | 81 | *
| Sarah Richardson | VFM23 | Implement the new Business Rates Rate Relief policy | Revised Policy implemented | April 2020 | Implemented 1st April 2020 | n/a | Fully Achieved | [16 empty] | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Environment & Housing | EH06 | 82 | *
| Sarah Richardson | VFM24 | Prepare for Universal Credit Managed Migration | Two Member Briefings | March 2021 | Deferred to the next Corporate Plan year, as there is currently no indication that the necessary Government guidance will be received this year. |  | Deferred | We await further information from the DWP as to when Managed Migration is likely to be rolled out nationwide. | [15 empty] | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Environment & Housing | EH07 | 83 | *
| Paul Farrer | VFM25 | Further Development of SMARTER working (Waste Collection) | Continue with SMARTER Waste Review Service Two Update Reports with next steps | March 2021 | Work is progressing with options for reviewing service delivery. |  | On Track to be Achieved | [16 empty] | Sal Khan | Environment | Value for Money Council | Environment & Housing | EH08 | 84 | *
| Paul Farrer | VFM26 | Further Development of SMARTER working (Street Cleaning) | Implement the SMARTER Street Cleaning Programme Update report on IT Management System | March 2021 |  |  | Not Yet Due | [16 empty] | Sal Khan | Environment | Value for Money Council | Environment & Housing | EH09 | 85 | *
| Paul Farrer | VFM27 | Essential Procurement Activities | Dry Recycling Contract / Garden Waste Contract Procurement commenced (Options Report) | June 2020 | Options report approved by Cabinet in June 2020. |  | Fully Achieved | [16 empty] | Sal Khan | Environment | Value for Money Council | Environment & Housing | EH10 | 86 | *
| Paul Farrer | VFM28 | Essential Procurement Activities | Vehicle Procurement concluded | November 2020 | Contract documents being prepared for procurement. Timetable in place. |  | On Track to be Achieved | [16 empty] | Sal Khan | Environment | Value for Money Council | Environment & Housing | EH11 | 87
| Paul Farrer | VFM29 | Minimise The Number Of Missed Bin Collections | Number Of Missed Bin Collections: Achieve 99.97% successful bin collections across the Borough | March 2021 | 99.97% successfully collected | 99.97 | On Track to be Achieved | [16 empty] | Sal Khan | Environment | Value for Money Council | Environment & Housing | EH12 | 88 | *
| Paul Farrer | VFM30 | Respond to Government Policy Announcements | Complete responses to Government consultations in line with consultation deadlines |  | COVID-19 has resulted in a delay in the Government publishing the next stage of consultations for the emerging Environment Bill. A revised timetable is yet to be confirmed. |  | Not Yet Due | [16 empty] | Sal Khan | Environment | Value for Money Council | Environment & Housing | EH13 | 89
| James Abbott | VFM31 | Maintain Robust Mechanisms for Contract Managing the Leisure Service Arrangements | Report on the performance of the Leisure Operator on a quarterly basis |  | Detailed report on the performance of the Leisure Services contractor (Everyone Active) was presented to CMT, LDL, LAG, LOAG, IAAG and the AVFM Scrutiny Committee during May / June 2020. |  | On Track to be Achieved | [16 empty] | Mark Rizk | Leisure Services Contract | Value for Money Council | Leisure, Culture & Tourism | LCT01 | 90
| James Abbott | VFM32 | Review Strategic Sport and Leisure Approach in Line with Leisure Services Contract Arrangements | Undertake a follow-up benchmarking exercise supporting the delivery of the leisure operating contract | February 2021 |  |  | Not Yet Due | [16 empty] | Mark Rizk | Leisure Services Contract | Value for Money Council | Leisure, Culture & Tourism | LCT02 | 91 | *
| James Abbott | VFM33 | Work with Leisure Operator to Continue to Provide High Quality Sports Facilities | Replace the Artificial Turf Pitch at Shobnall Leisure Complex | November 2020 | Target deferred to the next Corporate Plan year, as the enforced closure of the facility has prevented the project from proceeding as planned so completion is now anticipated in 2021/22. |  | Deferred | [16 empty] | Mark Rizk | Leisure Services Contract | Value for Money Council | Leisure, Culture & Tourism | LCT03 | 92 | *
| Nathan Gallagher | VFM34a | Improve Awareness of Council Services, Venues and Initiatives | Develop and communicate annual marketing plans for each leisure, culture and tourism service | April 2020 | Each service has a specific Marketing Plan for 2020/21, although specific performance targets were unable to be added by the deadline due to COVID 19 uncertainties. |  | Completed Behind Schedule | [16 empty] | Mark Rizk | Marketing | Value for Money Council | Leisure, Culture & Tourism | LCT04 | 93 | *
| Nathan Gallagher | VFM34b | Improve Awareness of Council Services, Venues and Initiatives | Achieve 85% of these targets by year end | March 2021 |  |  | Not Yet Due | [16 empty] | Mark Rizk | Marketing | Value for Money Council | Leisure, Culture & Tourism | LCT04 | 93 | *
| Nathan Gallagher | VFM35 | Improve Awareness of Council Services, Venues and Initiatives | Attend and deliver a minimum of 5 events/outreach days (including Burton Market Place, Indoor shopping centres and Parks/open spaces etc.) to promote Council services in conjunction with partners. | March 2021 | No events or outreach days were organised in quarter 1 due to the Coronavirus outbreak. Due to the current conditions and social distancing, it's unknown if achieving this target will be possible in 2020/21 |  | In Danger of Falling Behind Target | [16 empty] | Mark Rizk | Marketing | Value for Money Council | Leisure, Culture & Tourism | LCT05 | 94 | *
| Michael Hovers | VFM36 | Procurement of Grounds Maintenance Contractor | Commence the process for the Grounds Maintenance contract retender | March 2021 | Open Spaces and Procurement Teams have held initial discussions regarding the re-tendering of the contract. |  | On Track to be Achieved | [16 empty] | Mark Rizk | Communities, Open Spaces & Facilities | Value for Money Council | Leisure, Culture & Tourism | LCT06 | 95
| Michael Hovers | VFM37 | Improving Energy Efficiency-Facility Developments | Review energy usage in Council owned buildings (e.g. Town Hall, Cemetery etc.) and investigate alternative energy sources. | March 2021 |  |  | Not Yet Due | [16 empty] | Mark Rizk | Communities, Open Spaces & Facilities | Value for Money Council | Leisure, Culture & Tourism | LCT07 | 96
| Chloe Brown | VFM38 | Brewhouse, Arts and Town Hall Developments | Complete the implementation of a new service delivery model. | March 2021 | Awaiting outcome of current situation with COVID-19 and current closure of venues -before reviewing future strategy of service - it will be unlikely that this is known before the end of the year |  | Not Yet Due | [16 empty] | Mark Rizk | Brewhouse, Arts & Civic Function Suite | Value for Money Council | Leisure, Culture & Tourism | LCT08 | 97 | *
| Chloe Brown | VFM39 | Brewhouse, Arts and Town Hall Developments | New Brewhouse, Arts and Town Hall service strategy document completed | October 2020 | Awaiting outcome of current situation with COVID-19 before reviewing future strategy of service - it will be unlikely that this is known before the end of the year |  | In Danger of Falling Behind Target | [16 empty] | Mark Rizk | Brewhouse, Arts & Civic Function Suite | Value for Money Council | Leisure, Culture & Tourism | LCT09 | 98 | *
| Ashley Baldwin | VFM40 | Continue to develop SMARTER working practices for Planning | Two reports identifying reviews, changes and improvements | March 2021 |  |  | Not Yet Due | [16 empty] | Sal Khan | Planning | Value for Money Council | Regeneration & Planning Policy | RPP01 | 99
| Ashley Baldwin | VFM41 | Continue to develop SMARTER working practices for Planning | Electronic Document Management System Review and recommendation | March 2021 |  |  | Not Yet Due | [16 empty] | Sal Khan | Planning | Value for Money Council | Regeneration & Planning Policy | RPP02 | 100
| Ashley Baldwin | VFM42 | Continuing to inform and improve Planning awareness with Members | At least 2 briefings delivered to elected members during the year |  | Planning Committee Members have received training at the June 2020 Committee. Full Member training will be delivered on the forthcoming Planning White paper |  | On Track to be Achieved | [16 empty] | Sal Khan | Planning | Value for Money Council | Regeneration & Planning Policy | RPP03 | 101 | *
| Ashley Baldwin | VFM43 | Continuing to inform and improve Planning awareness with Members | Targeted Planning Committee Briefings - 10 throughout the year |  | Planning Committee Members have received training at the June 2020 Committee. A full programme of training is scheduled for the year. Viability training took place at June meeting. National Forest are scheduled for July and transport for August. |  | On Track to be Achieved | [16 empty] | Sal Khan | Planning | Value for Money Council | Regeneration & Planning Policy | RPP04 | 102 | *
| Ashley Baldwin | VFM44 | Monitor Local Plan Performance | Authority Monitoring Report Prepared | December 2020 | Officers have undertaken collection of data |  | On Track to be Achieved | [16 empty] | Sal Khan | Planning | Value for Money Council | Regeneration & Planning Policy | RPP05 | 103
| Ashley Baldwin | VFM45 | Monitor Local Plan Performance | Consider review of the Local Plan | October 2020 | In progress. |  | On Track to be Achieved | [16 empty] | Sal Khan | Planning | Value for Money Council | Regeneration & Planning Policy | RPP06 | 104
| Ashley Baldwin | VFM46 | New and Refreshed Planning Policies | Prepare and publish Infrastructure Funding Statement | January 2021 | Officers have undertaken collection of data |  | On Track to be Achieved | [16 empty] | Sal Khan | Planning | Value for Money Council | Regeneration & Planning Policy | RPP07 | 105
| Margaret Woolley | VFM47 | Review of the Council’s CCTV Provision | Preparation of tender documentation for the CCTV Contract Renewal Completed | January 2021 | Discussions have begun with the project team and external auditor to facilitate this target |  | On Track to be Achieved | [16 empty] | Mark Rizk | Communities & Open Spaces | Value for Money Council | Regulatory & Community Support | RCS01 | 106
| Margaret Woolley | VFM48 | Review of the Council’s CCTV Provision | Develop a Code of Practice for the use of Mobile CCTV Camera | September 2020 | Work has begun on the Code of Practice and a sample will be sent to the external auditor for comment |  | On Track to be Achieved | [16 empty] | Mark Rizk | Civil Enforcement | Value for Money Council | Regulatory & Community Support | RCS02 | 107
| Margaret Woolley | VFM49 | Improvements for the Hackney Carriage and Private Hire Service | Improvement Plan Completed | February 2021 | · Work has begun on a review of the Hackney Carriage Tariff. A sample tariff has been submitted by the trade. Safeguarding Training has been sourced however is on hold until restrictions are released as we need large volumes of drivers to attend each session in order to keep costs low. Verbal/Oral test has been implemented and applicants are being able to be assessed. Medicals are currently on hold due to the pandemic and our inability for drivers to have medicals with doctors. DBS service implemented and being utilised. · Safeguarding training for all Private Hire and Hackney Carriage Drivers · The introduction of a formal Verbal Test for new applicants for a Private Hire and Hackney Carriage Drivers Licence and Operators. · Also to propose recommendations for Medicals for Private Hire and Hackney Carriage Drivers and · Introduce the DBS update service for Private Hire and Hackney Carriage Drivers and Operators |  | On Track to be Achieved | On target however there will be certain restrictions due to the pandemic | [15 empty] | Mark Rizk | Licensing | Value for Money Council | Regulatory & Community Support | RCS03 | 108
Update not provided | Update not provided
Fully Achieved | Fully Achieved
Numerical Outturn Within 5% Tolerance | Numerical Outturn Within 5% Tolerance
Numerical Outturn Within 10% Tolerance | Numerical Outturn Within 10% Tolerance
Target Partially Met | Target Partially Met
Off Target | Off Target
Completed Significantly After Target Deadline | Completed Significantly After Target Deadline
Completion Date Within Reasonable Tolerance | Completion Date Within Reasonable Tolerance
Deferred | Deferred
Deleted | Deleted
Fully Achieved | Fully Achieved
On Track to be Achieved | On Track to be Achieved
In Danger of Falling Behind Target | In Danger of Falling Behind Target
Off Target | Off Target
Completed Behind Schedule | Completed Behind Schedule
Deleted | Deleted
Not Yet Due | Not Yet Due
Update Not Provided | Update Not Provided
Deferred | Deferred

## Q1 Summary
Click here to return to index page
Quarter One (2020/21) | Green |  | Amber |  | Red
| Number of Indicators | Percentage | Number of Indicators | Percentage | Number of Indicators | Percentage
Overall Performance
All due targets | 68 | 90.67% | 4 | 5.333% | 3 | 4%
Corporate Priority
Value for Money Council | 32 | 86.49% | 2 | 5.405% | 3 | 8.108%
Environment and Health & Well Being | 16 | 94.12% | 1 | 5.882% | 0 | 0%
Community Regeneration | 20 | 95.24% | 1 | 4.762% | 0 | 0%
Portfolio
Leader | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Environment & Housing | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Leisure, Culture & Tourism | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Regeneration & Planning Policy | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Regulatory & Community Support | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Q2 Summary (hidden)
Click here to return to index page
Quarter Two (2020/21) | Green |  | Amber |  | Red
| Number of Indicators | Percentage | Number of Indicators | Percentage | Number of Indicators | Percentage
Overall Performance
All due targets | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Corporate Priority
Value for Money Council | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Environment and Health & Well Being | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Community Regeneration | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Portfolio
Leader | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Environment & Housing | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Leisure, Culture & Tourism | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Regeneration & Planning Policy | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Regulatory & Community Support | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Q3 Summary (hidden)
Click here to return to index page
Quarter Three (2020/21) | Green |  | Amber |  | Red
| Number of Indicators | Percentage | Number of Indicators | Percentage | Number of Indicators | Percentage
Overall Performance
All due targets | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Corporate Priority
Value for Money Council | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Environment and Health & Well Being | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Community Regeneration | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Portfolio
Leader | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Environment & Housing | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Leisure, Culture & Tourism | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Regeneration & Planning Policy | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Regulatory & Community Support | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Q4 Summary (hidden)
Click here to return to index page
End of Year 2020/21 | Green |  | Amber |  | Red
| Number of Indicators | Percentage | Number of Indicators | Percentage | Number of Indicators | Percentage
Overall Performance
All due targets | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Corporate Priority
Value for Money Council | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Environment and Health & Well Being | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Community Regeneration | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Portfolio
Leader | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Environment & Housing | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Leisure, Culture & Tourism | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Regeneration & Planning Policy | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Regulatory & Community Support | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## 2a. % By Priority
QUARTER ONE (April - June 2020) | [5 empty] | QUARTER TWO (July - Sept 2020) | [5 empty] | QUARTER THREE (Oct - Dec 2020) | [5 empty] | QUARTER FOUR (Jan - Mar 2021)
ALL TARGETS | [5 empty] | ALL TARGETS | [5 empty] | ALL TARGETS | [5 empty] | ALL TARGETS
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | 4 | 3.67% | 62.39% | 5.333% | 90.67% | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
On Track to be Achieved | 64 | 58.72% |  | 85.33% |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | Numerical Outturn Within 5% Tolerance | 0 | #DIV/0! |  | #DIV/0!
In Danger of Falling Behind Target | 4 | 3.67% | 3.67% | 5.333% | 5.333% | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Numerical Outturn Within 10% Tolerance | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[18 empty] | Target Partially Met | 0 | #DIV/0! |  | #DIV/0!
[18 empty] | Completion Date Within Reasonable Tolerance | 0 | #DIV/0! |  | #DIV/0!
Completed Behind Schedule | 1 | 0.9174% | 2.752% | 1.333% | 4% | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Significantly After Target Deadline | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Off Target | 2 | 1.835% |  | 2.667% |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0!
Not yet due to be reported | 24 | 22.02% | 22.02% |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0!
Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0!
Deferred | 8 | 7.339% | 7.339% |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0!
Deleted | 2 | 1.835% | 1.835% |  |  | Deleted | 0 | #DIV/0! | #DIV/0! |  | Back to index | Deleted | 0 | #DIV/0! | #DIV/0! |  | Back to index | Deleted | 0 | #DIV/0! | #DIV/0! |  | Back to index
Totals | 109 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0
Due to be Reported | 75 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0
VALUE FOR MONEY | [5 empty] | VALUE FOR MONEY | [5 empty] | VALUE FOR MONEY | [5 empty] | VALUE FOR MONEY COUNCIL
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | 3 | 5.357% | 57.14% | 8.108% | 86.49% | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
On Track to be Achieved | 29 | 51.79% |  | 78.38% |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | Numerical Outturn Within 5% Tolerance | 0 | #DIV/0! |  | #DIV/0!
In Danger of Falling Behind Target | 2 | 3.571% | 3.571% | 5.405% | 5.405% | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Numerical Outturn Within 10% Tolerance | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[18 empty] | Target Partially Met | 0 | #DIV/0! |  | #DIV/0!
[18 empty] | Completion Date Within Reasonable Tolerance | 0 | #DIV/0! |  | #DIV/0!
Completed Behind Schedule | 1 | 1.786% | 5.357% | 2.703% | 8.108% | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Significantly After Target Deadline | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Off Target | 2 | 3.571% |  | 5.405% |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0!
Not yet due to be reported | 15 | 26.79% | 26.79% |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0!
Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0!
Deferred | 2 | 3.571% | 3.571% |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0!
Deleted | 2 | 3.571% | 3.571% |  | Back to index | Deleted | 0 | #DIV/0! | #DIV/0! |  | Back to index | Deleted | 0 | #DIV/0! | #DIV/0! |  | Back to index | Deleted | 0 | #DIV/0! | #DIV/0! |  |  | Back to index
Totals | 56 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0
Due to be Reported | 37 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0
ENVIRONMENT AND HEALTH & WELL BEING | [5 empty] | ENVIRONMENT AND HEALTH & WELL BEING | [5 empty] | ENVIRONMENT AND HEALTH & WELL BEING | [5 empty] | ENVIRONMENT AND HEALTH & WELL BEING
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | 0 | 0% | 61.54% | 0% | 94.12% | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
On Track to be Achieved | 16 | 61.54% |  | 94.12% |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | Numerical Outturn Within 5% Tolerance | 0 | #DIV/0! |  | #DIV/0!
In Danger of Falling Behind Target | 1 | 3.846% | 3.846% | 5.882% | 5.882% | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Numerical Outturn Within 10% Tolerance | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[18 empty] | Target Partially Met | 0 | #DIV/0! |  | #DIV/0!
[18 empty] | Completion Date Within Reasonable Tolerance | 0 | #DIV/0! |  | #DIV/0!
Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Significantly After Target Deadline | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0!
Not yet due to be reported | 5 | 19.23% | 19.23% |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0!
Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0!
Deferred | 4 | 15.38% | 15.38% |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0!
Deleted | 0 | 0% | 0% |  | Back to index | Deleted | 0 | #DIV/0! | #DIV/0! |  | Back to index | Deleted | 0 | #DIV/0! | #DIV/0! |  | Back to index | Deleted | 0 | #DIV/0! | #DIV/0! |  |  | Back to index
Totals | 26 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0
Due to be Reported | 17 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0
COMMUNITY REGENERATION | [5 empty] | COMMUNITY REGENERATION | [5 empty] | COMMUNITY REGENERATION | [5 empty] | COMMUNITY REGENERATION
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | 1 | 3.704% | 74.07% | 4.762% | 95.24% | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Target Fully Achieved | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
On Track to be Achieved | 19 | 70.37% |  | 90.48% |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | On Track to be Achieved | 0 | #DIV/0! |  | #DIV/0! |  | Numerical Outturn Within 5% Tolerance | 0 | #DIV/0! |  | #DIV/0!
In Danger of Falling Behind Target | 1 | 3.704% | 3.704% | 4.762% | 4.762% | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | In Danger of Falling Behind Target | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Numerical Outturn Within 10% Tolerance | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[18 empty] | Target Partially Met | 0 | #DIV/0! |  | #DIV/0!
[18 empty] | Completion Date Within Reasonable Tolerance | 0 | #DIV/0! |  | #DIV/0!
Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Behind Schedule | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Completed Significantly After Target Deadline | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0! |  | Off Target | 0 | #DIV/0! |  | #DIV/0!
Not yet due to be reported | 4 | 14.81% | 14.81% |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0! |  |  | Not yet due to be reported | 0 | #DIV/0! | #DIV/0!
Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0! |  |  | Update not provided | 0 | #DIV/0! | #DIV/0!
Deferred | 2 | 7.407% | 7.407% |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0! |  |  | Deferred | 0 | #DIV/0! | #DIV/0!
Deleted | 0 | 0% | 0% |  | Back to index | Deleted | 0 | #DIV/0! | #DIV/0! |  | Back to index | Deleted | 0 | #DIV/0! | #DIV/0! |  | Back to index | Deleted | 0 | #DIV/0! | #DIV/0! |  |  | Back to index
Totals | 27 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0 |  |  |  |  | Totals | 0
Due to be Reported | 21 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported | 0

## 2b. Charts by Priority
Charts by Corporate Priority | Please note that all charts shown below can be amended to be displayed in alternative styles. Please right click on the relevant chart, select "change chart type" and choose your preferred chart option.
Back to index
|  | Back to index | Back to index | Back to index | Back to index
OVERALL PERFORMANCE
[8 empty] | Q1 | Q2 | Q3 | Q4
[7 empty] | Green | 90.67% | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | Amber | 5.333% | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | Red | 4% | #DIV/0! | #DIV/0! | #DIV/0!
|  | Back to index | Back to index | Back to index | Back to index
VALUE FOR MONEY COUNCIL
[8 empty] | Q1 | Q2 | Q3 | Q4
[7 empty] | Green | 86.49% | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | Amber | 5.405% | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | Red | 8.108% | #DIV/0! | #DIV/0! | #DIV/0!
|  | Back to index | Back to index | Back to index | Back to index
ENVIRONMENT AND HEALTH & WELL BEING
[8 empty] | Q1 | Q2 | Q3 | Q4
[7 empty] | Green | 94.12% | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | Amber | 5.882% | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | Red | 0% | #DIV/0! | #DIV/0! | #DIV/0!
|  | Back to index | Back to index | Back to index |  | Back to index
COMMUNITY REGENERATION
[8 empty] | Q1 | Q2 | Q3 | Q4
[7 empty] | Green | 95.24% | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | Amber | 4.762% | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | Red | 0% | #DIV/0! | #DIV/0! | #DIV/0!

## 3a. % by Portfolio (hidden)
QUARTER ONE (April - June 2020) | [5 empty] | QUARTER TWO (July - Sept 2020) | [5 empty] | QUARTER THREE (Oct - Dec 2020) | [5 empty] | QUARTER FOUR (Jan - Mar 2021)
LEADER | [5 empty] | LEADER | [5 empty] | LEADER | [5 empty] | LEADER
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Target Fully Achieved | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Target Fully Achieved | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Target Fully Achieved | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
On Track to be Achieved | #VALUE! | #VALUE! |  | #VALUE! |  | On Track to be Achieved | #VALUE! | #VALUE! |  | #VALUE! |  | On Track to be Achieved | #VALUE! | #VALUE! |  | #VALUE! |  | Numerical Outturn Within 5% Tolerance | #VALUE! | #VALUE! |  | #VALUE!
In Danger of Falling Behind Target | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | In Danger of Falling Behind Target | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | In Danger of Falling Behind Target | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Numerical Outturn Within 10% Tolerance | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[18 empty] | Target Partially Met | #VALUE! | #VALUE! |  | #VALUE!
[18 empty] | Completion Date Within Reasonable Tolerance | #VALUE! | #VALUE! |  | #VALUE!
Completed Behind Schedule | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Completed Behind Schedule | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Completed Behind Schedule | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Completed Significantly After Target Deadline | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Off Target | #VALUE! | #VALUE! |  | #VALUE! |  | Off Target | #VALUE! | #VALUE! |  | #VALUE! |  | Off Target | #VALUE! | #VALUE! |  | #VALUE! |  | Off Target | #VALUE! | #VALUE! |  | #VALUE!
Not yet due to be reported | #VALUE! | #VALUE! | #VALUE! |  |  | Not yet due to be reported | #VALUE! | #VALUE! | #VALUE! |  |  | Not yet due to be reported | #VALUE! | #VALUE! | #VALUE! |  |  | Not yet due to be reported | #VALUE! | #VALUE! | #VALUE!
Update not provided | #VALUE! | #VALUE! | #VALUE! |  |  | Update not provided | #VALUE! | #VALUE! | #VALUE! |  |  | Update not provided | #VALUE! | #VALUE! | #VALUE! |  |  | Update not provided | #VALUE! | #VALUE! | #VALUE!
Deferred | #VALUE! | #VALUE! | #VALUE! |  |  | Deferred | #VALUE! | #VALUE! | #VALUE! |  |  | Deferred | #VALUE! | #VALUE! | #VALUE! |  |  | Deferred | #VALUE! | #VALUE! | #VALUE!
Deleted | #VALUE! | #VALUE! | #VALUE! |  | Back to index | Deleted | #VALUE! | #VALUE! | #VALUE! |  | Back to index | Deleted | #VALUE! | #VALUE! | #VALUE! |  | Back to index | Deleted | #VALUE! | #VALUE! | #VALUE! |  | Back to index
Totals | #VALUE! |  |  |  |  | Totals | #VALUE! |  |  |  |  | Totals | #VALUE! |  |  |  |  | Totals | #VALUE!
Due to be Reported | #VALUE! |  |  |  |  | Due to be Reported | #VALUE! |  |  |  |  | Due to be Reported | #VALUE! |  |  |  |  | Due to be Reported | #VALUE!
ENVIRONMENT & HOUSING | [5 empty] | ENVIRONMENT & HOUSING | [5 empty] | ENVIRONMENT & HOUSING | [5 empty] | ENVIRONMENT & HOUSING
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Target Fully Achieved | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Target Fully Achieved | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Target Fully Achieved | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
On Track to be Achieved | #VALUE! | #VALUE! |  | #VALUE! |  | On Track to be Achieved | #VALUE! | #VALUE! |  | #VALUE! |  | On Track to be Achieved | #VALUE! | #VALUE! |  | #VALUE! |  | Numerical Outturn Within 5% Tolerance | #VALUE! | #VALUE! |  | #VALUE!
In Danger of Falling Behind Target | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | In Danger of Falling Behind Target | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | In Danger of Falling Behind Target | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Numerical Outturn Within 10% Tolerance | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[18 empty] | Target Partially Met | #VALUE! | #VALUE! |  | #VALUE!
[18 empty] | Completion Date Within Reasonable Tolerance | #VALUE! | #VALUE! |  | #VALUE!
Completed Behind Schedule | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Completed Behind Schedule | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Completed Behind Schedule | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Completed Significantly After Target Deadline | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Off Target | #VALUE! | #VALUE! |  | #VALUE! |  | Off Target | #VALUE! | #VALUE! |  | #VALUE! |  | Off Target | #VALUE! | #VALUE! |  | #VALUE! |  | Off Target | #VALUE! | #VALUE! |  | #VALUE!
Not yet due to be reported | #VALUE! | #VALUE! | #VALUE! |  |  | Not yet due to be reported | #VALUE! | #VALUE! | #VALUE! |  |  | Not yet due to be reported | #VALUE! | #VALUE! | #VALUE! |  |  | Not yet due to be reported | #VALUE! | #VALUE! | #VALUE!
Update not provided | #VALUE! | #VALUE! | #VALUE! |  |  | Update not provided | #VALUE! | #VALUE! | #VALUE! |  |  | Update not provided | #VALUE! | #VALUE! | #VALUE! |  |  | Update not provided | #VALUE! | #VALUE! | #VALUE!
Deferred | #VALUE! | #VALUE! | #VALUE! |  |  | Deferred | #VALUE! | #VALUE! | #VALUE! |  |  | Deferred | #VALUE! | #VALUE! | #VALUE! |  |  | Deferred | #VALUE! | #VALUE! | #VALUE!
Deleted | #VALUE! | #VALUE! | #VALUE! |  | Back to index | Deleted | #VALUE! | #VALUE! | #VALUE! |  | Back to index | Deleted | #VALUE! | #VALUE! | #VALUE! |  | Back to index | Deleted | #VALUE! | #VALUE! | #VALUE! |  | Back to index
Totals | #VALUE! |  |  |  |  | Totals | #VALUE! |  |  |  |  | Totals | #VALUE! |  |  |  |  | Totals | #VALUE!
Due to be Reported | #VALUE! |  |  |  |  | Due to be Reported | #VALUE! |  |  |  |  | Due to be Reported | #VALUE! |  |  |  |  | Due to be Reported | #VALUE!
LEISURE, CULTURE & TOURISM | [5 empty] | LEISURE, CULTURE & TOURISM | [5 empty] | LEISURE, CULTURE & TOURISM | [5 empty] | LEISURE, CULTURE & TOURISM
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Target Fully Achieved | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Target Fully Achieved | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Target Fully Achieved | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
On Track to be Achieved | #VALUE! | #VALUE! |  | #VALUE! |  | On Track to be Achieved | #VALUE! | #VALUE! |  | #VALUE! |  | On Track to be Achieved | #VALUE! | #VALUE! |  | #VALUE! |  | Numerical Outturn Within 5% Tolerance | #VALUE! | #VALUE! |  | #VALUE!
In Danger of Falling Behind Target | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | In Danger of Falling Behind Target | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | In Danger of Falling Behind Target | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Numerical Outturn Within 10% Tolerance | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[18 empty] | Target Partially Met | #VALUE! | #VALUE! |  | #VALUE!
[18 empty] | Completion Date Within Reasonable Tolerance | #VALUE! | #VALUE! |  | #VALUE!
Completed Behind Schedule | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Completed Behind Schedule | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Completed Behind Schedule | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Completed Significantly After Target Deadline | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Off Target | #VALUE! | #VALUE! |  | #VALUE! |  | Off Target | #VALUE! | #VALUE! |  | #VALUE! |  | Off Target | #VALUE! | #VALUE! |  | #VALUE! |  | Off Target | #VALUE! | #VALUE! |  | #VALUE!
Not yet due to be reported | #VALUE! | #VALUE! | #VALUE! |  |  | Not yet due to be reported | #VALUE! | #VALUE! | #VALUE! |  |  | Not yet due to be reported | #VALUE! | #VALUE! | #VALUE! |  |  | Not yet due to be reported | #VALUE! | #VALUE! | #VALUE!
Update not provided | #VALUE! | #VALUE! | #VALUE! |  |  | Update not provided | #VALUE! | #VALUE! | #VALUE! |  |  | Update not provided | #VALUE! | #VALUE! | #VALUE! |  |  | Update not provided | #VALUE! | #VALUE! | #VALUE!
Deferred | #VALUE! | #VALUE! | #VALUE! |  |  | Deferred | #VALUE! | #VALUE! | #VALUE! |  |  | Deferred | #VALUE! | #VALUE! | #VALUE! |  |  | Deferred | #VALUE! | #VALUE! | #VALUE!
Deleted | #VALUE! | #VALUE! | #VALUE! |  | Back to index | Deleted | #VALUE! | #VALUE! | #VALUE! |  | Back to index | Deleted | #VALUE! | #VALUE! | #VALUE! |  | Back to index | Deleted | #VALUE! | #VALUE! | #VALUE! |  | Back to index
Totals | #VALUE! |  |  |  |  | Totals | #VALUE! |  |  |  |  | Totals | #VALUE! |  |  |  |  | Totals | #VALUE!
Due to be Reported | #VALUE! |  |  |  |  | Due to be Reported | #VALUE! |  |  |  |  | Due to be Reported | #VALUE! |  |  |  |  | Due to be Reported | #VALUE!
REGENERATION & PLANNING POLICY | [5 empty] | REGENERATION & PLANNING POLICY | [5 empty] | REGENERATION & PLANNING POLICY | [5 empty] | REGENERATION & PLANNING POLICY
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Target Fully Achieved | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Target Fully Achieved | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Target Fully Achieved | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
On Track to be Achieved | #VALUE! | #VALUE! |  | #VALUE! |  | On Track to be Achieved | #VALUE! | #VALUE! |  | #VALUE! |  | On Track to be Achieved | #VALUE! | #VALUE! |  | #VALUE! |  | Numerical Outturn Within 5% Tolerance | #VALUE! | #VALUE! |  | #VALUE!
In Danger of Falling Behind Target | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | In Danger of Falling Behind Target | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | In Danger of Falling Behind Target | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Numerical Outturn Within 10% Tolerance | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[18 empty] | Target Partially Met | #VALUE! | #VALUE! |  | #VALUE!
[18 empty] | Completion Date Within Reasonable Tolerance | #VALUE! | #VALUE! |  | #VALUE!
Completed Behind Schedule | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Completed Behind Schedule | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Completed Behind Schedule | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Completed Significantly After Target Deadline | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Off Target | #VALUE! | #VALUE! |  | #VALUE! |  | Off Target | #VALUE! | #VALUE! |  | #VALUE! |  | Off Target | #VALUE! | #VALUE! |  | #VALUE! |  | Off Target | #VALUE! | #VALUE! |  | #VALUE!
Not yet due to be reported | #VALUE! | #VALUE! | #VALUE! |  |  | Not yet due to be reported | #VALUE! | #VALUE! | #VALUE! |  |  | Not yet due to be reported | #VALUE! | #VALUE! | #VALUE! |  |  | Not yet due to be reported | #VALUE! | #VALUE! | #VALUE!
Update not provided | #VALUE! | #VALUE! | #VALUE! |  |  | Update not provided | #VALUE! | #VALUE! | #VALUE! |  |  | Update not provided | #VALUE! | #VALUE! | #VALUE! |  |  | Update not provided | #VALUE! | #VALUE! | #VALUE!
Deferred | #VALUE! | #VALUE! | #VALUE! |  |  | Deferred | #VALUE! | #VALUE! | #VALUE! |  |  | Deferred | #VALUE! | #VALUE! | #VALUE! |  |  | Deferred | #VALUE! | #VALUE! | #VALUE!
Deleted | #VALUE! | #VALUE! | #VALUE! |  | Back to index | Deleted | #VALUE! | #VALUE! | #VALUE! |  | Back to index | Deleted | #VALUE! | #VALUE! | #VALUE! |  | Back to index | Deleted | #VALUE! | #VALUE! | #VALUE! |  | Back to index
Totals | #VALUE! |  |  |  |  | Totals | #VALUE! |  |  |  |  | Totals | #VALUE! |  |  |  |  | Totals | #VALUE!
Due to be Reported | #VALUE! |  |  |  |  | Due to be Reported | #VALUE! |  |  |  |  | Due to be Reported | #VALUE! |  |  |  |  | Due to be Reported | #VALUE!
REGULATORY & COMMUNITY SUPPORT | [5 empty] | REGULATORY & COMMUNITY SUPPORT | [5 empty] | REGULATORY & COMMUNITY SUPPORT | [5 empty] | REGULATORY & COMMUNITY SUPPORT
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Target Fully Achieved | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Target Fully Achieved | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Target Fully Achieved | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
On Track to be Achieved | #VALUE! | #VALUE! |  | #VALUE! |  | On Track to be Achieved | #VALUE! | #VALUE! |  | #VALUE! |  | On Track to be Achieved | #VALUE! | #VALUE! |  | #VALUE! |  | Numerical Outturn Within 5% Tolerance | #VALUE! | #VALUE! |  | #VALUE!
In Danger of Falling Behind Target | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | In Danger of Falling Behind Target | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | In Danger of Falling Behind Target | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Numerical Outturn Within 10% Tolerance | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[18 empty] | Target Partially Met | #VALUE! | #VALUE! |  | #VALUE!
[18 empty] | Completion Date Within Reasonable Tolerance | #VALUE! | #VALUE! |  | #VALUE!
Completed Behind Schedule | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Completed Behind Schedule | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Completed Behind Schedule | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Completed Significantly After Target Deadline | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Off Target | #VALUE! | #VALUE! |  | #VALUE! |  | Off Target | #VALUE! | #VALUE! |  | #VALUE! |  | Off Target | #VALUE! | #VALUE! |  | #VALUE! |  | Off Target | #VALUE! | #VALUE! |  | #VALUE!
Not yet due to be reported | #VALUE! | #VALUE! | #VALUE! |  |  | Not yet due to be reported | #VALUE! | #VALUE! | #VALUE! |  |  | Not yet due to be reported | #VALUE! | #VALUE! | #VALUE! |  |  | Not yet due to be reported | #VALUE! | #VALUE! | #VALUE!
Update not provided | #VALUE! | #VALUE! | #VALUE! |  |  | Update not provided | #VALUE! | #VALUE! | #VALUE! |  |  | Update not provided | #VALUE! | #VALUE! | #VALUE! |  |  | Update not provided | #VALUE! | #VALUE! | #VALUE!
Deferred | #VALUE! | #VALUE! | #VALUE! |  |  | Deferred | #VALUE! | #VALUE! | #VALUE! |  |  | Deferred | #VALUE! | #VALUE! | #VALUE! |  |  | Deferred | #VALUE! | #VALUE! | #VALUE!
Deleted | #VALUE! | #VALUE! | #VALUE! |  | Back to index | Deleted | #VALUE! | #VALUE! | #VALUE! |  | Back to index | Deleted | #VALUE! | #VALUE! | #VALUE! |  | Back to index | Deleted | #VALUE! | #VALUE! | #VALUE! |  | Back to index
Totals | #VALUE! |  |  |  |  | Totals | #VALUE! |  |  |  |  | Totals | #VALUE! |  |  |  |  | Totals | #VALUE!
Due to be Reported | #VALUE! |  |  |  |  | Due to be Reported | #VALUE! |  |  |  |  | Due to be Reported | #VALUE! |  |  |  |  | Due to be Reported | #VALUE!

## 3b. Charts by Portfolio (hidden)
Charts by Portfolio | Please note that all charts shown below can be amended to be displayed in alternative styles. Please right click on the relevant chart, select "change chart type" and choose your preferred chart option.
|  | Back to index | Back to index | Back to index | Back to index
LEADER OF THE COUNCIL
[7 empty] | Q1 | Q2 | Q3 | Q4
[6 empty] | Green | 84.62% | #DIV/0! | #DIV/0! | #DIV/0!
[6 empty] | Amber | 0% | #DIV/0! | #DIV/0! | #DIV/0!
[6 empty] | Red | 15.38% | #DIV/0! | #DIV/0! | #DIV/0!
|  | Back to index | Back to index | Back to index | Back to index
ENVIRONMENT & HOUSING
[7 empty] | Q1 | Q2 | Q3 | Q4
[6 empty] | Green | 100% | #DIV/0! | #DIV/0! | #DIV/0!
[6 empty] | Amber | 0% | #DIV/0! | #DIV/0! | #DIV/0!
[6 empty] | Red | 0% | #DIV/0! | #DIV/0! | #DIV/0!
|  | Back to index | Back to index | Back to index | Back to index
LEISURE, CULTURE & TOURISM
[7 empty] | Q1 | Q2 | Q3 | Q4
[6 empty] | Green | 66.67% | #DIV/0! | #DIV/0! | #DIV/0!
[6 empty] | Amber | 22.22% | #DIV/0! | #DIV/0! | #DIV/0!
[6 empty] | Red | 11.11% | #DIV/0! | #DIV/0! | #DIV/0!
|  | Back to index | Back to index | Back to index | Back to index
REGENERATION & PLANNING POLICY
[7 empty] | Q1 | Q2 | Q3 | Q4
[6 empty] | Green | 94.74% | #DIV/0! | #DIV/0! | #DIV/0!
[6 empty] | Amber | 5.263% | #DIV/0! | #DIV/0! | #DIV/0!
[6 empty] | Red | 0% | #DIV/0! | #DIV/0! | #DIV/0!
|  | Back to index | Back to index | Back to index | Back to index
REGULATORY & COMMUNITY SUPPORT
[7 empty] | Q1 | Q2 | Q3 | Q4
[6 empty] | Green | 90% | #DIV/0! | #DIV/0! | #DIV/0!
[6 empty] | Amber | 10% | #DIV/0! | #DIV/0! | #DIV/0!
[6 empty] | Red | 0% | #DIV/0! | #DIV/0! | #DIV/0!
|  | Back to index | Back to index | Back to index | Back to index
REGULATORY SERVICES
[7 empty] | Q1 | Q2 | Q3 | Q4
[6 empty] | Green | 0% | 0% | 0% | 0%
[6 empty] | Amber | 0% | 0% | 0% | 0%
[6 empty] | Red | 0% | 0% | 0% | 0%
|  | Back to index | Back to index | Back to index | Back to index
|  | Back to index | Back to index | Back to index | Back to index

## 4. Status Tracking
Back to index
CP Ref | Measures | Target 2019/20 | Quarter 1 On track? (R/A/G) | Direction of Travel From Q1 to Q2 | Quarter 2 On track? (R/A/G) | Direction of Travel From Q2 to Q3 | Quarter 3 On track? (R/A/G) | Direction of Travel From Q3 to Q4 | Quarter 4 Achieved? (R/A/G)
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! | Ü
CR02 | Proactively Supporting the Boundary Review of East Staffordshire | Respond to Boundary Review Consultation in line with LGBCE timetable | On Track to be Achieved |  | 0 |  | 0 |  | 0 | Ý |  | è
CR03 | Proactively Supporting the Boundary Review of East Staffordshire | Prepare for Polling Place Review following completion of Boundary Review | On Track to be Achieved |  | 0 |  | 0 |  | 0 | Þ |  | ê
CR04 | Increasing Staffing Availability Through Reduced Sickness | Short Term Sickness Days Average: 2.98 days | On Track to be Achieved |  | 0 |  | 0 |  | 0 | n/a | ê
CR05 | Improve On The Average Time To Pay Creditors | Average Time To Pay Creditors: 10 days | On Track to be Achieved |  | 0 |  | 0 |  | 0 |  | é
CR06 | Legal and Assets | Commission a condition survey of the Council’s industrial units at Centrum 100 Business Park | Not Yet Due |  | 0 |  | 0 |  | 0 |  | è
CR07 | Legal and Assets | Carry out works to 8 of the Council’s commercial properties, as identified in the condition survey | Not Yet Due |  | 0 |  | 0 |  | 0
CR08 | Increase Capacity at Stapenhill Cemetery | Commence preparatory works for the expansion of Stapenhill Cemetery. | Fully Achieved |  | 0 |  | 0 |  | 0
CR09 | Market Hall Development Initiatives | Implement the outcome of the Market Hall future options review | Deferred |  | 0 |  | 0 |  | 0
CR10 | Market Development Initiatives | Hold at least 7 commercial events in the Market Hall/Market Place | On Track to be Achieved |  | 0 |  | 0 |  | 0
CR11 | Market Hall Development Initiatives | Continue to benchmark Market Hall performance through APSE membership | On Track to be Achieved |  | 0 |  | 0 |  | 0
CR12 | Major Planning Applications Determined Within 13 Weeks | Top Quartile as measured against relevant MHCLG figures | On Track to be Achieved |  | 0 |  | 0 |  | 0
CR13 | Minor Planning Applications Determined Within 8 Weeks | Top Quartile as measured against relevant MHCLG figures | On Track to be Achieved |  | 0 |  | 0 |  | 0
CR14 | Other Planning Applications Determined in 8 Weeks | Top Quartile as measured against relevant MHCLG figures | On Track to be Achieved |  | 0 |  | 0 |  | 0
CR15 | Supporting Neighbourhood Plans | Rolleston Neighbourhood Plan Made | Deferred |  | 0 |  | 0 |  | 0
CR16 | New and Refreshed Planning Policies | Finalise and adopt Brewery Building Conversion Design Guidance SPD | On Track to be Achieved |  | 0 |  | 0 |  | 0
CR17 | New and Refreshed Planning Policies | Publish Revised Statement of Community Involvement | On Track to be Achieved |  | 0 |  | 0 |  | 0
CR18 | New and Refreshed Planning Policies | Produce report and approach regarding Brownfield Register Part 2 | On Track to be Achieved |  | 0 |  | 0 |  | 0
CR19 | New and Refreshed Planning Policies | Revise and adopt Car parking SPD | On Track to be Achieved |  | 0 |  | 0 |  | 0
CR20 | Improve Burton town centre through significant environmental regeneration | Practical completion of the Station Street works via Amey | On Track to be Achieved |  | 0 |  | 0 |  | 0
CR21 | Improve Burton town centre through significant environmental regeneration | Deliver phase 1 of the Washlands Enhancement Project, fully utilising the GBSLEP Local Growth Fund monies | On Track to be Achieved |  | 0 |  | 0 |  | 0
CR22 | Work towards achieving transformation regeneration for Burton upon Trent of up to £25m through the Towns Fund | Working with the Town Deal Board, develop a Town Investment Plan for Burton and create a business case for funding | On Track to be Achieved |  | 0 |  | 0 |  | 0
CR23 | Support the delivery of affordable housing on brownfield land through the utilisation of S106 commuted sums | Review the progress of existing S106 commuted sums and identify new projects for potential funding | Not Yet Due |  | 0 |  | 0 |  | 0
CR24 | Identify a vision for the future regeneration of Uttoxeter | Member approval of the final Uttoxeter Masterplan | On Track to be Achieved |  | 0 |  | 0 |  | 0
CR25 | Promote local employment opportunities | Working with the Worklessness Action Group and local MP, support the delivery of three job fairs | In Danger of Falling Behind Target |  | 0 |  | 0 |  | 0
CR26 | Continue to support local businesses to grow and innovate | Create a grant fund to support small businesses and deliver throughout the year | Not Yet Due |  | 0 |  | 0 |  | 0
CR27 | Continue to support local businesses to grow and innovate | Provide direct support to 20 businesses through the Growth Hub Advisor contract | On Track to be Achieved |  | 0 |  | 0 |  | 0
CR28 | Continue to work effectively with regeneration partners | Continue to work with strategic tourism partners, such as the National Forest, the Campaign to Reopen the Ivanhoe Line and the TTTV, on the regeneration of the borough | On Track to be Achieved |  | 0 |  | 0 |  | 0
EHW01 | Delivering Better Services to Support Homelessness | Promote, monitor and report on the Burton and East Staffordshire Partnership, produce two activity reports during the year | On Track to be Achieved |  | 0 |  | 0 |  | 0
EHW02 | Delivering Better Services to Support Homelessness | Evaluate and build on the existing MHCLG/ESBC projects to target entrenched rough sleepers with two activity reports during the year Prepare and submit new applications to MHCLG as and when appropriate during the year | On Track to be Achieved |  | 0 |  | 0 |  | 0
EHW03 | Proactively reducing the number of empty homes in the borough | Produce annual contract performance report | On Track to be Achieved |  | 0 |  | 0 |  | 0
EHW04 | Delivering Better Services to Support Homelessness | Average time from appointment to initial decision for homeless applicants of 3 days | On Track to be Achieved |  | 0 |  | 0 |  | 0
EHW05 | Continue to Maximise Utilisation of Self Contained Temporary Accommodation for Homeless Applicants | Reduce ‘Key to Key’ Void Turnaround to an average of 6 working days | On Track to be Achieved |  | 0 |  | 0 |  | 0
EHW06 | Improving our Housing Strategy Initiatives | Refreshed Housing Strategy | On Track to be Achieved |  | 0 |  | 0 |  | 0
EHW07 | Improving our Housing Strategy Initiatives | Report opportunities for improving Housing Register Service | On Track to be Achieved |  | 0 |  | 0 |  | 0
EHW08 | Maintain Top Quartile Performance For Street Cleansing - Litter | Maintain Top Quartile Performance | Not Yet Due |  | 0 |  | 0 |  | 0
EHW09 | Maintain Top Quartile Performance For Street Cleansing - Detritus | Maintain Top Quartile Performance | Not Yet Due |  | 0 |  | 0 |  | 0
EHW10 | Maintain Top Quartile Performance For Street Cleansing - Graffiti | Maintain Top Quartile Performance | Not Yet Due |  | 0 |  | 0 |  | 0
EHW11 | Maintain Top Quartile Performance For Street Cleansing – Fly-Posting | Maintain Top Quartile Performance | Not Yet Due |  | 0 |  | 0 |  | 0
EHW12 | Maintain Top Quartile Performance On Recycling | Household Waste Recycled and Composted: Maintain Top Quartile Performance | On Track to be Achieved |  | 0 |  | 0 |  | 0
EHW13 | Maintain Top Quartile Performance On Waste Reduction | Residual Household Waste Per Household: Maintain Top Quartile Performance | On Track to be Achieved |  | 0 |  | 0 |  | 0
EHW14 | Open Spaces Initiatives | Develop a Borough wide parks development plan | Not Yet Due |  | 0 |  | 0 |  | 0
EHW15 | Open Spaces Initiatives | Achieve 2 in bloom gold awards and support Uttoxeter in the 2020 National In bloom awards | Deferred |  | 0 |  | 0 |  | 0
EHW17 | Open Spaces Initiatives | Increase the marks awarded to the 9 parks in the “It’s Your Neighbourhood” Parks category by an average of 10% | Deferred |  | 0 |  | 0 |  | 0
EHW18 | Develop Tourism within the Borough | Develop a tactical approach and plan for tourism in East Staffordshire | On Track to be Achieved |  | 0 |  | 0 |  | 0
EHW19 | Compliance Inspections in support of Public Protection | Undertake two high profile initiatives aimed at monitoring compliance and ensuring public protection | On Track to be Achieved |  | 0 |  | 0 |  | 0
EHW20 | Community & Civil Enforcement Initiatives | Undertake 8 focused initiatives (including fly tipping) across the Borough and deliver at least 6 education programs in local schools. | In Danger of Falling Behind Target |  | 0 |  | 0 |  | 0
EHW21 | Development of the Selective Licensing Scheme | Selective Licensing Designation Approved | Deferred |  | 0 |  | 0 |  | 0
EHW22 | Development of the Selective Licensing Scheme | Selective Licensing Third Year Review Complete | On Track to be Achieved |  | 0 |  | 0 |  | 0
EHW23 | Partnership working with Trading Standards Regarding Tenant Fees | Undertake a Targeted Initiative to Investigate and Enforce Compliance with Tenant Fees Legislation | On Track to be Achieved |  | 0 |  | 0 |  | 0
EHW24 | Disabled Facilities Grant Review | Complete Annual Review of Disabled Facilities Grant Service | On Track to be Achieved |  | 0 |  | 0 |  | 0
EHW25 | Climate Change & Air Quality Policy | Consider the declaration of a Climate Emergency and implement and monitor a Climate Change action plan-including an annual update | On Track to be Achieved |  | 0 |  | 0 |  | 0
EHW26 | Multi-agency Initiatives to Combat Modern Slavery | Carry out Covid-19 compliance checks across the Borough and report progress on a quarterly basis | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM01 | Continue to Improve Financial Resilience | Compliance with HMRC VAT Digitalisation Requirements | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM02 | Continue to Improve Financial Resilience | Review compliance against CIPFA FM Code of Practice | Not Yet Due |  | 0 |  | 0 |  | 0
VFM03 | Continue to Improve Financial Resilience | Review and Refresh Financial Regulations | Not Yet Due |  | 0 |  | 0 |  | 0
VFM04 | Continue to Improve Financial Resilience | Review and Refresh Contract Procedure Rules | Not Yet Due |  | 0 |  | 0 |  | 0
VFM05 | Continue to Improve Financial Resilience | Undertake a Procurement Exercise for the Council’s Insurance and related support | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM06 | Continue to Improve Financial Resilience | Develop Procurement Policy | Off Target |  | 0 |  | 0 |  | 0
VFM07 | Responding to Significant Local Government Finance Changes and Assessing the Impact on the Council’s Financial Position | Activities Throughout the Year Reported in Line with the Timed Responses | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM08 | Set the MTFS for 2021/22 onwards | Set Budget for Council Approval | Not Yet Due |  | 0 |  | 0 |  | 0
VFM09 | Savings targets for 2020/21 | Achieve Savings Targets as Stated in the Medium Term Financial Strategy | Deleted |  | 0 |  | 0 |  | 0
VFM10 | Having an approved Statement of Accounts | Submit Statement of Accounts to Audit Committee by the earlier Statutory Deadline | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM11 | Prepare for a Corporate ICT refresh | Commence Desktop Hardware Renewal | Fully Achieved |  | 0 |  | 0 |  | 0
VFM12 | Explore opportunities for shared service/income generation | Report on ICT income generation | Off Target |  | 0 |  | 0 |  | 0
VFM13 | Continuing to digitise SMARTER services | Digital Strategy Refreshed and approved | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM14 | Continuing to digitise SMARTER services | 80% of revised Digital Strategy targets achieved | Not Yet Due |  | 0 |  | 0 |  | 0
VFM15 | Continuing to digitise SMARTER services | GeoPlaces Gold Standard in ESBC related categories | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM16 | Improved Resilience Planning | Review of Rest Centres Complete | Not Yet Due |  | 0 |  | 0 |  | 0
VFM17 | LGA Peer Review | Work with the LGA to deliver a peer review to another council/s to build up to hosting one in East Staffordshire | Deleted |  | 0 |  | 0 |  | 0
VFM18a | Continue to Maximise Income Through Effective Collection Processes (Previously BVPI9) | Collection Rates of Council Tax : 98% | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM19a | Continue to Maximise Income Through Effective Collection Processes: Reduce Former Years Arrears for Council Tax; NNDR; Sundry Debts | Former Years Arrears for Council Tax £2,500,000 (net of credits, amounts on arrangement and identified write offs) | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM20a | Maintaining excellent customer access to services with face-to-face and telephony enquiries | 99% of CSC and Telephony Team Enquiries Resolved at First Point of Contact | Not Yet Due |  | 0 |  | 0 |  | 0
VFM21 | Continue to Improve the Ways We Provide Benefits to Those Most in Need: | Time Taken to Process Benefit New Claims and Change Events (Previously NI 181) 5 days | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM22ai | Working Towards the Reduction of Claimant Error Housing Benefit Overpayments (HBOPs) | % HBOPs recovered during the year; 90% | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM23 | Implement the new Business Rates Rate Relief policy | Revised Policy implemented | Fully Achieved |  | 0 |  | 0 |  | 0
VFM24 | Prepare for Universal Credit Managed Migration | Two Member Briefings | Deferred |  | 0 |  | 0 |  | 0
VFM25 | Further Development of SMARTER working (Waste Collection) | Continue with SMARTER Waste Review Service Two Update Reports with next steps | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM26 | Further Development of SMARTER working (Street Cleaning) | Implement the SMARTER Street Cleaning Programme Update report on IT Management System | Not Yet Due |  | 0 |  | 0 |  | 0
VFM27 | Essential Procurement Activities | Dry Recycling Contract / Garden Waste Contract Procurement commenced (Options Report) | Fully Achieved |  | 0 |  | 0 |  | 0
VFM28 | Essential Procurement Activities | Vehicle Procurement concluded | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM29 | Minimise The Number Of Missed Bin Collections | Number Of Missed Bin Collections: Achieve 99.97% successful bin collections across the Borough | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM30 | Respond to Government Policy Announcements | Complete responses to Government consultations in line with consultation deadlines | Not Yet Due |  | 0 |  | 0 |  | 0
VFM31 | Maintain Robust Mechanisms for Contract Managing the Leisure Service Arrangements | Report on the performance of the Leisure Operator on a quarterly basis | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM32 | Review Strategic Sport and Leisure Approach in Line with Leisure Services Contract Arrangements | Undertake a follow-up benchmarking exercise supporting the delivery of the leisure operating contract | Not Yet Due |  | 0 |  | 0 |  | 0
VFM33 | Work with Leisure Operator to Continue to Provide High Quality Sports Facilities | Replace the Artificial Turf Pitch at Shobnall Leisure Complex | Deferred |  | 0 |  | 0 |  | 0
VFM34a | Improve Awareness of Council Services, Venues and Initiatives | Develop and communicate annual marketing plans for each leisure, culture and tourism service | Completed Behind Schedule |  | 0 |  | 0 |  | 0
VFM35 | Improve Awareness of Council Services, Venues and Initiatives | Attend and deliver a minimum of 5 events/outreach days (including Burton Market Place, Indoor shopping centres and Parks/open spaces etc.) to promote Council services in conjunction with partners. | In Danger of Falling Behind Target |  | 0 |  | 0 |  | 0
VFM36 | Procurement of Grounds Maintenance Contractor | Commence the process for the Grounds Maintenance contract retender | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM37 | Improving Energy Efficiency-Facility Developments | Review energy usage in Council owned buildings (e.g. Town Hall, Cemetery etc.) and investigate alternative energy sources. | Not Yet Due |  | 0 |  | 0 |  | 0
VFM38 | Brewhouse, Arts and Town Hall Developments | Complete the implementation of a new service delivery model. | Not Yet Due |  | 0 |  | 0 |  | 0
VFM39 | Brewhouse, Arts and Town Hall Developments | New Brewhouse, Arts and Town Hall service strategy document completed | In Danger of Falling Behind Target |  | 0 |  | 0 |  | 0
VFM40 | Continue to develop SMARTER working practices for Planning | Two reports identifying reviews, changes and improvements | Not Yet Due |  | 0 |  | 0 |  | 0
VFM41 | Continue to develop SMARTER working practices for Planning | Electronic Document Management System Review and recommendation | Not Yet Due |  | 0 |  | 0 |  | 0
VFM42 | Continuing to inform and improve Planning awareness with Members | At least 2 briefings delivered to elected members during the year | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM43 | Continuing to inform and improve Planning awareness with Members | Targeted Planning Committee Briefings - 10 throughout the year | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM44 | Monitor Local Plan Performance | Authority Monitoring Report Prepared | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM45 | Monitor Local Plan Performance | Consider review of the Local Plan | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM46 | New and Refreshed Planning Policies | Prepare and publish Infrastructure Funding Statement | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM47 | Review of the Council’s CCTV Provision | Preparation of tender documentation for the CCTV Contract Renewal Completed | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM48 | Review of the Council’s CCTV Provision | Develop a Code of Practice for the use of Mobile CCTV Camera | On Track to be Achieved |  | 0 |  | 0 |  | 0
VFM49 | Improvements for the Hackney Carriage and Private Hire Service | Improvement Plan Completed | On Track to be Achieved |  | 0 |  | 0 |  | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!