## Index
East Staffordshire Borough Council
Corporate Plan 2019/20 - Performance Monitoring Spreadsheet
1. All Data
Summary Tables
Quarter 1 Summary Table
Quarter 2 Summary Table
Quarter 3 Summary Table
Quarter 4 Summary Table
Breakdown of peformance by Corporate Plan priorty
2a. % By Priority
2b. Charts by Priority
4. Status Tracking
Custom Pivot Table

## 1. All Data
[5 empty] | QUARTER 1: April - June 2019 |  |  |  | QUARTER 2: July - September 2019 |  |  |  |  | QUARTER 3: October - December 2019 |  |  |  |  | QUARTER 4: January - March 2020
Reporting Officer | Corporate Plan Ref Number | Measures | Target 2019/20 | Target Date | Quarter 1 (April - June 2019) | End of year forecast as at end of Q1 (NUMERICAL INDICATORS ONLY) | Quarter 1 On Track? (R/A/G) | Comments / Further action (Q1) (IF APPLICABLE) | Quarter 2 (July - September 2019) | Year to date (April - Sept 2019) (NUMERICAL INDICATORS ONLY) | End of year forecast as at end of Q2 (NUMERICAL INDICATORS ONLY) | Quarter 2 On Track? (R/A/G) | Comments / Further action (Q2) (IF APPLICABLE) | Quarter 3 (October - December 2019) | Year to date (April - Dec 2019) (NUMERICAL INDICATORS ONLY) | End of year forecast as at end of Q3 (NUMERICAL INDICATORS ONLY) | Quarter 3 On Track? (R/A/G) | Comments / Further action (Q3) (IF APPLICABLE) | Quarter 4 (January - March 2020) | Cumulative Annual Outturn (NUMERICAL INDICATORS ONLY) | End of Year Achieved? (R/A/G) | Comments / Further action (Q4) (IF APPLICABLE) | Qtr | Service | Team | Corporate Priority | Portfolio @ time of CP adoption | Portfolio | CP order
Lisa Turner | VFM01 | Set the MTFS for 2020/21 onwards | Set Budget for Council Approval | 2020-02-29 | The Quarter 1 Outturn report forecasts a small underspend at this very early stage of the year. It does however highlight risks associated with the capital financing budget. |  | On Track to be Achieved |  | LDL and Conservative Away Evening presentation on latest MTFS position. Government announcements at Spending Round in September 2019 taken into consideration as well as local pressures and savings identified. |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Sal Khan | Finance | Value for Money Council | Leader & Finance | Leader | 1
Lisa Turner | VFM02 | Savings targets for 2019/20 | Achieve Savings Targets as Stated in the Medium Term Financial Strategy | 2020-03-31 | Information not yet available. |  | Not Yet Due |  | Information not yet available |  |  | Not Yet Due |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Sal Khan | Finance | Value for Money Council | Leader & Finance | Leader | 2
Lisa Turner | VFM03 | Having an approved Statement of Accounts | Submit Statement of Accounts by New Statutory Deadline | 2019-07-31 | Draft accounts published by statutory deadline and external audit largely complete. |  | On Track to be Achieved |  | Audited accounts approved and signed in July 2019. It is estimated that 40% of authorities nationally did not meet this target. |  |  | Fully Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q2 | Sal Khan | Finance | Value for Money Council | Leader & Finance | Leader | 3
Lisa Turner | VFM04 | Responding to Significant Local Government Finance Changes and Assessing the Impact on the Council’s Financial Position | Activities Throughout the Year Reported in Line with the Timed Responses | 2020-03-31 | Monitoring updates on the national funding system and proposals. |  | On Track to be Achieved |  | Government announced deferral of implementation date to April 2021. |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Sal Khan | Finance | Value for Money Council | Leader & Finance | Leader | 4
Lisa Turner | VFM05 | Internal Audit Service Procurement | Procurement concluded and new contract awarded | 2020-03-31 | Preliminary work undertaken and suitable framework agreement identified. |  | On Track to be Achieved |  | Procurement mobilisation, project team established, documentation complete. Invites for tender to commence from October. |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Sal Khan | Finance | Value for Money Council | Leader & Finance | Leader | 5
Lisa Turner | VFM06 | Working towards the Government’s new HMRC VAT Digitalisation Compliance requirements | Compliance Report completed | 2020-03-31 |  |  | Not Yet Due |  | Interim solution for Making Tax Digital (MTD) to meet the initial requirements put in place and formally registered for MTD with HMRC. |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Sal Khan | Finance | Value for Money Council | Leader & Finance | Leader | 6
Daniel Arnold | VFM07 | Continuing to digitise SMARTER services | Secure Integrated Service Request and Payment mechanism developed and implemented | 2019-12-31 | Project initiation meeting took place in July |  | On Track to be Achieved |  | The necessary upgrade to UNIT 4 (part of the Agresso Financial Management System) could potentially delay the delivery of this project depending on the upgrade timescales |  |  | In Danger of Falling Behind Target |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q3 | Sal Khan | Corporate & Commercial | Value for Money Council | Leader & Finance | Leader | 7
Chris Ebberley | VFM08 | Continuing to digitise SMARTER services | Audio recording of Council meetings added to Corporate Website | 2019-09-30 | New microphones were purchased and installed by June 2019. The June Council meeting was recorded using the new equipment. Meetings throughout July will be recorded using the new equipment to test the recording software. Meetings held in August onwards will be added to the Website. |  | On Track to be Achieved |  | All committee meetings from August 2019 onwards are recorded and uploaded to the Council website |  |  | Fully Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q2 | Sal Khan | Corporate & Commercial | Value for Money Council | Leader & Finance | Leader | 8
Daniel Arnold | VFM09 | Continuing to digitise SMARTER services | 80% of 2019/20 Milestones in New Digital Strategy Achieved | 2020-03-31 |  |  | Not Yet Due |  | Over 80% of milestones have been achieved or are on track to being achieved by Q4. |  | 86% | On Track to be Achieved | On track to achieve 18/21 2019/2020 milestones. |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Sal Khan | Corporate & Commercial | Value for Money Council | Leader & Finance | Leader | 9
Guy Thornhill | VFM10 | Providing a more secure ICT working environment | Security Arrangements to Meet Requirements of PSN (or Replacement) | 2020-03-31 | Ongoing adjustments made in line with emerging threats and recommendations, still no clarity as to the future of PSN |  | On Track to be Achieved |  | Ongoing adjustments made in line with emerging threats and recommendations, still no clarity as to the future of PSN |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Sal Khan | ICT | Value for Money Council | Leader & Finance | Leader | 10
Guy Thornhill | VFM11 | Providing a more secure ICT working environment | Preferred biometric approach to password replacement identified and commenced | 2019-12-31 | Selected solution planned to be rolled out at next hardware renewal |  | On Track to be Achieved |  | Best solution identified and advance preparations completed, end user elements to be implemented at next hardware renewal |  |  | Fully Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q3 | Sal Khan | ICT | Value for Money Council | Leader & Finance | Leader | 11
Chris Ebberley | VFM12 | Successfully deliver local elections | Local elections delivered | 2019-05-31 | Borough wide and several Parish Elections were successfully held in May 2019. This was swiftly followed by the European Parliamentary Elections. |  | Fully Achieved |  | Delivered in Q1. |  |  | Fully Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q1 | Andy O'Brien | Electoral Services | Value for Money Council | Leader & Finance | Leader | 12
Chris Ebberley | VFM13 | Carry out detailed Procurement / Contractor Consolidation / Spend Analysis | Report and way forward approved | 2019-12-31 |  |  | Not Yet Due |  |  |  |  | Not Yet Due |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q3 | Sal Khan | Corporate & Commercial | Value for Money Council | Leader & Finance | Leader | 13
Linda McDonald | VFM14 | Increasing Staffing Availability Through Reduced Sickness | Short Term Sickness Days Average: 2.75 days |  | 0.71 days |  | On Track to be Achieved |  | 0.62 | 1.32 | 2.75 | On Track to be Achieved | NB Quarter 1 figure updated to incorporate late reported sickness |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Andy O'Brien | Human Resources | Value for Money Council | Leader & Finance | Leader | 14
Linda McDonald | VFM15 | Improve On The Average Time To Pay Creditors | Average Time To Pay Creditors: 12 days |  | 10 |  | On Track to be Achieved |  | 10 | 10 | 12 | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Andy O'Brien | Human Resources | Value for Money Council | Leader & Finance | Leader | 15
Angela Wakefield | VFM16 | Legal and Assets | Carry out works to Canal Street industrial units, as identified in the condition survey | 2020-03-31 |  |  | Not Yet Due |  |  |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Andy O'Brien | Assets & Estates | Value for Money Council | Leader & Finance | Leader | 16
Angela Wakefield | VFM17 | Legal and Assets | Condition Survey commissioned for miscellaneous Council properties | 2019-10-31 |  |  | Not Yet Due |  |  |  |  | Fully Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q3 | Andy O'Brien | Assets & Estates | Value for Money Council | Leader & Finance | Leader | 17
James Abbott | VFM18 | Maintain Robust Mechanisms for Contract Managing the New Leisure Service Arrangements | Report on the performance of the Leisure Services contractor on a quarterly basis | (Q1, Q2, Q3 and Q4 2020) | Detailed report on the performance of the Leisure Services contractor (Everyone Active) covering the first contract quarter was presented to CMT, LDL, LAG, LOAG, IAAG and AVFM Scrutiny Committee during May / June 2019 in line with the target. |  | On Track to be Achieved | The quarterly contract performance report was also presented to the Leisure Services Partnership Board on 1st July 2019. | Detailed report on the performance of the Leisure Services contractor (Everyone Active) covering Quarter 1 was presented to CMT, LDL, LAG, LOAG, IAAG and AVFM Scrutiny Committee during August / September 2019 in line with the target. |  |  | On Track to be Achieved | The quarterly contract performance report was also presented to the Leisure Services Partnership Board on 16th September 2019. |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Mark Rizk | Leisure Services Contract | Value for Money Council | Cultural Services | Leisure, Culture & Tourism | 18
James Abbott | VFM19 | Review Strategic Sport and Leisure Approach in Line with New Leisure Service Arrangements | Undertake a benchmarking exercise to support the delivery of the leisure management contract | 2019-11-30 | To commence in Quarter 2. |  | Not Yet Due |  | Initial VFM benchmarking exercise to be completed by November in line with the target, and will include considerations for additional benchmarking later in the year. |  |  | On Track to be Achieved | Discussions with local authority partners from PALS (Physical Activity Leaderships in Staffordshire) to benchmark operational contract management elements. Through PALS in July 2019 the Council’s Leisure Services Contract Manager requested that Contract Management Operations in outsourced leisure partnership arrangements be a formal work-stream of the group. This was agreed and will ensure that leisure contract management is a priority among the PALS partners. |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q3 | Mark Rizk | Leisure Services Contract | Value for Money Council | Cultural Services | Leisure, Culture & Tourism | 19
James Abbott | VFM20 | Review Strategic Sport and Leisure Approach in Line with New Leisure Service Arrangements | Conduct a review of the relevant Sport and Leisure Strategy and Policy Documents and create a plan for their delivery | 2020-03-31 | Initial scoping meeting held with Sport Across Staffordshire and Stoke on Trent (SASSOT) in June 2019 to commence this review. |  | On Track to be Achieved |  | Initial scoping meeting held with Sport Across Staffordshire and Stoke on Trent (SASSOT) in June 2019 to commence this process. Additional conversations held with ESBC Planning Policy Team to gain additional information on how the review of Leisure Strategy aligns to wider Council documents such as the Local Plan. |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Mark Rizk | Leisure Services Contract | Value for Money Council | Cultural Services | Leisure, Culture & Tourism | 20
Michael Hovers | VFM21 | Open Spaces Service Development Initiatives | Review the Open Spaces/Grounds Maintenance Contract in preparation for retendering in 2020/21 | 2020-03-31 | Contract specification is currently being reviewed and is building upon operational learning from the last decade to form and shape a potential new contract specification. |  | On Track to be Achieved |  |  |  |  | Not Yet Due |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Mark Rizk | Communities & Open Spaces | Value for Money Council | Cultural Services | Leisure, Culture & Tourism | 21
Michael Hovers | VFM22 | Open Spaces Service Development Initiatives | Commission a consultant to assess the potential practical and capital requirements for the expansion of Stapenhill Cemetery | 2019-08-31 | A consultant has been commissioned and has taken some exploratory soil samples and provided an indicative layout for the proposed expansion. A meeting is scheduled in Q2 to look at potential costs. |  | On Track to be Achieved |  | Consultants have identified the estimated costs for the Cemetery extension. Capital bid to be prepared for 2020/21. |  |  | Fully Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q2 | Mark Rizk | Communities & Open Spaces | Value for Money Council | Cultural Services | Leisure, Culture & Tourism | 22
Michael Hovers | VFM23 | Open Spaces Service Development Initiatives | Review the options for improving the energy efficiency of lighting stock on Council land across the Borough | 2019-07-31 | EON has been commissioned to produce a lighting study for each of the Council ran car parks and Stapenhill Gardens |  | On Track to be Achieved |  | Energy studies received with estimated return on investment on capital investment to be between 3-4 years. |  |  | Fully Achieved | Report to be completed for CMT (December) to request draw down of funds from the Parking reserve. |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q2 | Mark Rizk | Communities & Open Spaces | Value for Money Council | Cultural Services | Leisure, Culture & Tourism | 23
Paul Nephin | VFM24 | Open Spaces Service Development Initiatives | Review the first years performance of the Alertcom lone working system | 2019-06-30 | Report completed and discussed at H&S briefing with CEO. 09/07/2019 |  | Fully Achieved | Improvements to lone working arrangements implemented. Lone working compliance has been successful. |  |  |  | Fully Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q1 | Mark Rizk | Health & Safety | Value for Money Council | Cultural Services | Leisure, Culture & Tourism | 24
Chloe Brown | VFM25 | Brewhouse, Arts and Town Hall Developments | Investigate new models of delivery for the Brewhouse Arts Facilities, Civic Function Suite and Arts Development | 2020-03-31 | Project Initiation Document complete and initial research undertaken; including meetings with FMU and benchmarking with other Arts Services/Venues in other local authorities. |  | On Track to be Achieved |  | Visit to Tamworth Assembly Rooms Arts Centre as they complete their £5m refurbishment as part of research for the project. Updated BAG on project scope and amendments made to widen scope of the project. |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Mark Rizk | Brewhouse, Arts & Civic Function Suite | Value for Money Council | Cultural Services | Leisure, Culture & Tourism | 25
Nathan Gallagher | VFM26 | Improve Awareness of ESBC Venues and Initiatives | Produce Marketing and Development Plans for key services and provide quarterly updates on performance | 2020-03-31 | 2019/20 marketing plans have been produced for services. |  | On Track to be Achieved | Quarterly performance reports will be circulated to members. | Quarterly performance reports will be circulated to members. |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Mark Rizk | Marketing | Value for Money Council | Cultural Services | Leisure, Culture & Tourism | 26
Nathan Gallagher | VFM27 | Improve Awareness of ESBC Venues and Initiatives | Deliver a minimum of 2 Town Centre initiatives in Conjunction with local partners | 2019-12-31 | In Quarter 1 the Brewhouse delivered Burton Children's Festival events, with support and sponsorship from Coopers Square Shopping Centre. |  | On Track to be Achieved |  | This quarter we partnered with Coopers Square Shopping Centre to run themed activities from the Brewhouse autumn programme, in centre. |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q3 | Mark Rizk | Marketing | Value for Money Council | Cultural Services | Leisure, Culture & Tourism | 27
Nathan Gallagher | VFM28 | Improve Awareness of ESBC Venues and Initiatives | Organise a minimum of 4 “Outreach” Days (1 Per Quarter) to raise the profile of the Council’s services | 2020-03-31 | In Quarter 1 we attended the Burton Jobs Fair to promote the Market Hall's 'Be Your Own Boss' campaign, highlighting self employment opportunities. |  | On Track to be Achieved | In quarter 2 we will attend and organise a number of summer holiday outreach events. | During this quarter we developed a number of outreach days, including make and take activities to promote the Brewhouse autumn programme and activities in the Town Centre to promote ESBC summer holiday activities. |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Mark Rizk | Marketing | Value for Money Council | Cultural Services | Leisure, Culture & Tourism | 28
Paul Farrer | VFM29 | Further Development of SMARTER working (Waste Collection) | Conduct review of Waste Service Two Findings / Update Reports with next steps | 2020-03-31 | Establishing the scope of the review. First report to be provided in October. |  | On Track to be Achieved |  | First report establishing a position statement for the current service, work undertaken to date, next steps and identifying the key challenges/future work strands was approved by Cabinet in October. |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Sal Khan | Environment | Value for Money Council | Environment | Environment & Housing | 29
Paul Farrer | VFM30 | Further Development of SMARTER working (Street Cleaning) | Implement the SMARTER Street Cleaning Programme Two update reports | 2020-03-31 |  |  | Not Yet Due |  | First update report providing an update on the recommendations from the review approved by Cabinet in October. |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Sal Khan | Environment | Value for Money Council | Environment | Environment & Housing | 30
Paul Farrer | VFM31 | Further Development of SMARTER working (Street Cleaning) | Produce Strategy for engaging with Highways England to improve cleanliness around A38 and associated access roads | 2019-06-30 | EDR approved in June-19 establishing a programme for working with Highways England. |  | Fully Achieved |  |  |  |  | Fully Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q1 | Sal Khan | Environment | Value for Money Council | Environment | Environment & Housing | 31
Paul Farrer | VFM32 | Further Development of SMARTER Working (Building Control) | Implement ISO Quality Management System for Building Control | 2020-03-31 |  |  | Not Yet Due |  | Work continuing on self audit of all documents to ensure compliance with LABC Quality Management System. Request made to LABC for support. |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Sal Khan | Building Consultancy | Value for Money Council | Environment | Environment & Housing | 32
Paul Farrer | VFM33 | Minimise The Number Of Missed Bin Collections | Number Of Missed Bin Collections: 2 missed bins per 10,000 collections | 2020-03-31 | 2.7 per 10,000 | 2 per 10,000 | In Danger of Falling Behind Target | Q1 figure is slightly higher than annual target. Increased levels of staff absences have led to a greater use of agency staff with less familiarisation of the collection rounds. | 3.4 per 10,000 | 3.0 per 10,000 |  | In Danger of Falling Behind Target | Figure remains high predominantly due to use of temporary staff to cover leave and sickness in summer months and unfamiliarity with rounds. Operations Manager now monitors weekly with crews to reduce figure. |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Sal Khan | Environment | Value for Money Council | Environment | Environment & Housing | 33
Paul Farrer | VFM34 | Carry out SMARTER Digital Communications | Refreshed Web / Social Media Waste Management and Street Cleaning Section launched | 2019-07-31 | Work underway to 'go live' during July. |  | On Track to be Achieved |  | All pages of website refreshed, with additional information added for residents. |  |  | Fully Achieved | http://www.eaststaffsbc.gov.uk/bins-rubbish-recycling |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q2 | Sal Khan | Environment | Value for Money Council | Environment | Environment & Housing | 34
Paul Farrer | VFM35 | Respond to Government Policy Announcements | Complete responses to Government consultations in line with consultation deadlines |  | Formal responses submitted to Defra in May-19 for consistency in waste collections, deposit return scheme and end producer responsibility. |  | On Track to be Achieved |  | Consultation responses for consistency, deposit return scheme and end producer responsibility completed and submitted to DEFRA. |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Sal Khan | Environment | Value for Money Council | Environment | Environment & Housing | 35
Sarah Richardson | VFM36a | Continue to Maximise Income Through Effective Collection Processes (Previously BV9) | Council Tax Collection Rates: 98% |  | 29.61% | 98% | On Track to be Achieved | Target is annual | 57.41% | 57.41% | 98% | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Housing & Homelessness | Environment & Housing | 36
Sarah Richardson | VFM36b | Continue to Maximise Income Through Effective Collection Processes (Previously BV10) | NNDR Collection Rates: 99% |  | 33.02% | 99% | On Track to be Achieved | Target is annual | 59.86% | 59.86% | 99% | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Housing & Homelessness | Environment & Housing | 37
Sarah Richardson | VFM37a | Continue to Maximise Income Through Effective Collection Processes: Reduce Former Years Arrears for Council Tax; NNDR; Sundry Debts | Former Years Arrears for Council Tax; £1,900,000 (net) |  | 2076546.74 | 1900000 | On Track to be Achieved | Figures are net of credits, amounts on arrangement and identified write offs | 2206158.57 | 2206158.57 | 1900000 | On Track to be Achieved | Target is annual |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Housing & Homelessness | Environment & Housing | 38
Sarah Richardson | VFM37b | Continue to Maximise Income Through Effective Collection Processes: Reduce Former Years Arrears for Council Tax; NNDR; Sundry Debts | Former Years Arrears for NNDR; £500,000 (net) |  | 898218.91 | 500000 | On Track to be Achieved | Figures are net of credits, amounts on arrangement and identified write offs | 1176309.54 | 1176309.54 | 500000 | On Track to be Achieved | Collection of arrears is impacted by the charges relating to liabilities before 31st March 2019 that have been raised since 1st April 2019. We are obliged to raise these charges following changes notified to us from the Valuation Office Agency resulting from appeals and new properties brought into the business rates list. |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Housing & Homelessness | Environment & Housing | 39
Sarah Richardson | VFM37c | Continue to Maximise Income Through Effective Collection Processes: Reduce Former Years Arrears for Council Tax; NNDR; Sundry Debts | Current Years Arrears for Sundry debts; £40,000 (older than 90 days) |  | 0 | 40000 | On Track to be Achieved | Target is annual | 21887.71 | 21887.71 | 40000 | On Track to be Achieved | Target is annual |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Housing & Homelessness | Environment & Housing | 40
Sarah Richardson | VFM38a | Maintaining excellent customer access to services with face-to-face and telephony enquiries | 99% of CSC and Telephony Team Enquiries Resolved at First Point of Contact |  | 100% | 100% | On Track to be Achieved | Target is annual | 99% | 99% | 99% | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Housing & Homelessness | Environment & Housing | 41
Sarah Richardson | VFM38b | Maintaining excellent customer access to services with face-to-face and telephony enquiries | Minimum 75% Telephony Team Calls Answered Within 10 Seconds |  | 85% | 80% | On Track to be Achieved | Target is annual | 76% | 77% | 75% | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Housing & Homelessness | Environment & Housing | 42
Sarah Richardson | VFM39a | Maximise Tax Bases through continued reviews of discounts, exemptions and reliefs | Empty Properties – October 2019 | 2019-10-01 | Staffs CC signed contracts with the confirmed suppliers in June 2019. SSCM & RTL will agree timetable of reviews during July 2019. |  | Not Yet Due | See proposed target in main body of the report. | Empty Property review completed by Capita during September as part of the Staffordshire County-wide Discount Review contract. |  |  | Fully Achieved | Target adopted post tender via Q1 report to Cabinet |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Housing & Homelessness | Environment & Housing | 43
Sarah Richardson | VFM39b | Maximise Tax Bases through continued reviews of discounts, exemptions and reliefs | Occupied Property Discounts – March 2020 | 2020-03-01 | Staffs CC signed contracts with the confirmed suppliers in June 2019. SSCM & RTL will agree timetable of reviews during July 2019. |  | Not Yet Due | See proposed target in main body of the report. | Not yet due |  |  | Not Yet Due | Target adopted post tender via Q1 report to Cabinet |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Housing & Homelessness | Environment & Housing | 43
Sarah Richardson | VFM40 | Continue to Improve the Ways We Provide Benefits to Those Most in Need: Time Taken to Process Benefit New Claims and Change Events (Previously NI 181) | 5 days |  | 4.36 days | 5 days | On Track to be Achieved | Performance aided by offsite remote processing assistance funded by DWP. | 4.81 days | 4.55 days | 5 days | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Housing & Homelessness | Environment & Housing | 44
Sarah Richardson | VFM41a | Working Towards the Reduction of Claimant Error Housing Benefit Overpayments (HBOPs) | 80% of HBOPs Overpayments Recovered During the Year |  | 92.9% | 85% | On Track to be Achieved | Target is annual | 135.4% | 105.7% | 80% | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Housing & Homelessness | Environment & Housing | 45
Sarah Richardson | VFM41b | Working Towards the Reduction of Claimant Error Housing Benefit Overpayments (HBOPs) | 85% of HBOPS Processed and on Payment Arrangement |  | 81.9% | 85% | On Track to be Achieved | Target is annual | 84.8% | 85.9% | 85% | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Housing & Homelessness | Environment & Housing | 46
Sarah Richardson | VFM42 | Review Council Tax Reduction scheme | Carry Out Review of the Council Tax Reduction Scheme | 2019-12-31 |  |  | Not Yet Due | Modelling currently being undertaken before report is sent to CMT. | Completed and approved via EDR October 2019 |  |  | Fully Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q3 | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Housing & Homelessness | Environment & Housing | 47
Sarah Richardson | VFM43 | Review Business Rates Rate Relief policy | Policy reviewed (for next year’s implementation) | 2020-03-31 |  |  | Not Yet Due | Main review will be undertaken during Q3 | Not yet due |  |  | Not Yet Due |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Housing & Homelessness | Environment & Housing | 48
Sarah Richardson | VFM44 | Prepare for Universal Credit Managed Migration | Work with DWP and partners, prepare 2 in year progress reports and 1 Member briefing | 2020-03-31 |  |  | Not Yet Due | DWP are undertaking a test of Managed Migration in the North East of England over the Summer/Autumn and we await details of that testing. | Not yet due |  |  | Not Yet Due |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Sal Khan | Revenues, Benefits & Customer Care | Value for Money Council | Housing & Homelessness | Environment & Housing | 49
Planning Manager | VFM45 | Continuing to inform and improve Planning awareness with Members | At least 2 briefings delivered to elected members during the year |  | The first member briefing is programmed for September – there is also potential for a member briefing in August on HS2. |  | On Track to be Achieved |  | HS2 Member briefing delivered |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Sal Khan | Planning | Value for Money Council | Planning | Regeneration & Planning Policy | 50
Planning Manager | VFM46 | Continuing to inform and improve Planning awareness with Members | Strategic Sites Progress Report delivered | 2019-12-31 | Monitoring to support this report is underway |  | On Track to be Achieved |  | Monitoring to support this report is underway |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q3 | Sal Khan | Planning | Value for Money Council | Planning | Regeneration & Planning Policy | 51
Planning Manager | VFM47 | Monitor Local Plan Performance | Annual Monitoring Report Prepared | 2019-12-31 | Monitoring to support this report is underway |  | On Track to be Achieved |  | Monitoring to support this report is underway |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q3 | Sal Khan | Planning | Value for Money Council | Planning | Regeneration & Planning Policy | 52
Planning Manager | VFM48 | Continue to develop SMARTER working practices for Planning | Invalid Applications Review and Report | 2020-03-31 | Consultation on a new validations website will be launched in August |  | On Track to be Achieved |  | Consultation launched |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Sal Khan | Planning | Value for Money Council | Planning | Regeneration & Planning Policy | 53
Planning Manager | VFM49 | Continue to develop SMARTER working practices for Planning | Adoption of SMARTER Developer Contributions SPD | 2019-12-31 | Report drafted |  | On Track to be Achieved |  | Consultation closes Friday 18th October |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q3 | Sal Khan | Planning | Value for Money Council | Planning | Regeneration & Planning Policy | 54
Margaret Woolley | VFM50 | Ensure Robust Licensing Policies | Complete a Review of the Scrap Metal Dealers Policy | 2019-09-30 | Completed and signed EDR June 2019 |  | Fully Achieved | Completed |  |  |  | Fully Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q2 | Mark Rizk | Licensing | Value for Money Council | Regulatory Services | Regulatory & Community Support | 55
Margaret Woolley | VFM51 | Ensure Robust Licensing Policies | Complete a Review of the Charitable Collection Policy | 2019-09-30 | CMT 16 July 2019 |  | On Track to be Achieved | Licensing Committee 6 August 2019 | Reported to Licensing Committee 6 August 2019 |  |  | Fully Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q2 | Mark Rizk | Licensing | Value for Money Council | Regulatory Services | Regulatory & Community Support | 56
Margaret Woolley | VFM52 | Ensure Robust Licensing Policies | Complete a Review of the Licensing Act Policy | 2020-03-31 | Policy reviewed awaiting revised CIZ from Police and updated appendix from TS |  | On Track to be Achieved | Awaiting document from police analyst | Due to be reported to CMT in October 2019 |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Mark Rizk | Licensing | Value for Money Council | Regulatory Services | Regulatory & Community Support | 57
Rachel Liddle | VFM53 | Ensure an Effective Selective Licensing Scheme | Complete an Evaluation of the Selective Licensing Scheme and consider its future expansion | 2019-11-30 | Scoping exercise started for future expansion |  | On Track to be Achieved | Update to be provided to DL on selective licensing criteria | Report completed for CMT in October |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q3 | Mark Rizk | Environmental Health | Value for Money Council | Regulatory Services | Regulatory & Community Support | 58
Rachel Liddle | VFM54 | Ensure an Effective Disabled Facilities Grant Service | Complete a Review of the Disabled Facilities Grant Service | 2019-12-31 | Ongoing monthly reviews undertaken and improvements made to increase service delivery |  | On Track to be Achieved |  | Process Mapping being undertaken and CMT report being drafted for November CMT |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q3 | Mark Rizk | Environmental Health | Value for Money Council | Regulatory Services | Regulatory & Community Support | 59
Michael Hovers | VFM55 | Develop the use of technology to improve service delivery | Complete a Review of Parking Services and the related use of technology | 2019-10-31 | Research has commenced into the varying forms of technology now being employed on car parks. A long list of options are being presented to the Deputy Leader on July 9th with a view to creating a preferential short list. |  | On Track to be Achieved |  | Report completed for CMT in October. Cabinet agreed introduction of app based parking payments |  |  | Fully Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q3 | Mark Rizk | Communities & Open Spaces | Value for Money Council | Regulatory Services | Regulatory & Community Support | 60
Michael Hovers & Margaret Woolley | VFM56 | Ensure an Effective Civil and Community Enforcement Service | Review Public Space Protection Orders for Dog Fouling and Alcohol consumption | 2019-10-31 | Parish Councils have been contacted and the existing PSPO have been confirmed. Notices are to be erected in Q2 regarding consultation on any additions or amendments |  | On Track to be Achieved |  | Consultation period closed in quarter 2 and final report completed with recommendations made on amendments to the existing PSPO's. |  |  | Fully Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q3 | Mark Rizk | Communities & Open Spaces, & Licensing | Value for Money Council | Regulatory Services | Regulatory & Community Support | 61
Simon Humble | VFM57 | Achieve further investment for our town centres and large settlements | Finalise agreement with SCC to fund the implementation of the co-designed Station Street new public realm project | 2019-06-30 | The report relating to this target was ready to be presented at the Full Council meeting in June 2019. However, as the Conservative Group membership has changed and there is a new Cabinet, a decision has been made to delay the report going forward for the time being, to allow the new Members to consider the financial implications of the project. |  | Off Target | This report will now be taken to the Full Council meeting scheduled to take place in September 2019. | As previously reported, the report was ready to be presented at the Full Council meeting in June 2019 but following the change in the make-up of Cabinet, a decision was taken to delay the report so that members could review progress made to that point. The report was presented at the Full Council meeting in September 2019. All of the recommendations of the report were approved and the agreement to fund the public realm project has been finalised. |  |  | Completed Behind Schedule |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q1 | Andy O'Brien | Corporate & Commercial | Value for Money Council | Regeneration | Regeneration & Planning Policy | 62
Thomas Deery | VFM58 | Achieve further investment for our town centres and large settlements | Consider the outcome of the Council’s expression of interest to the Future High Street Fund | 2019-06-30 | There has not yet been an announcement from Government on the outcome of the Council's FHSF bid. Members have been updated on the latest available information. |  | Fully Achieved | Members will be updated on progress in due course, as and when information is made available |  |  |  | Fully Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q1 | Andy O'Brien | Enterprise | Value for Money Council | Regeneration | Regeneration & Planning Policy | 63
Thomas Deery | VFM59 | Achieve optimum working in economic partnership | Consider the outcome of the national LEP review findings and implication on the Washlands LEP monies | 2019-06-30 | Members have been updated on the latest position of the national LEP review, which has not yet issued its findings. There is currently no known impact on Washlands LEP monies. |  | Fully Achieved | Members will be updated on progress in due course, as and when information is made available |  |  |  | Fully Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q1 | Andy O'Brien | Enterprise | Value for Money Council | Regeneration | Regeneration & Planning Policy | 64
Thomas Deery | VFM60 | Progress the commutation of s106 sums to deliver key brownfield development opportunities | Review progress on working in partnership with Burton Rugby Club (Peelcroft) and Molson Coors (Cross Street) | 2019-10-31 | The Council continues to engage both Burton Rugby Club and Molson Coors regarding the development of their respective sites and the potential for collaborative working. |  | On Track to be Achieved |  | The Council has engaged both Burton Rugby Club and Molson Coors regarding the potential development of their respective sites. |  |  | On Track to be Achieved | A proposal for commuting s106 sums will be considered by Cabinet on 7th October 2019. |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q3 | Andy O'Brien | Enterprise | Value for Money Council | Regeneration | Regeneration & Planning Policy | 65
Catherine Grimley | CR01 | Market Hall Development Initiatives | Hold at least 25 commercial events in the Market Hall | 2020-03-31 | 10 | 25 | On Track to be Achieved | A diverse number of events have been held in quarter 1 with more scheduled across the year. | 5 commercial events held during Quarter 2 | 15 |  | On Track to be Achieved | The Market Hall and place continues to host some exciting events with more planned throughout the Autumn/Winter programme. |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Mark Rizk | Markets | Community Regeneration | Cultural Services | Leisure, Culture & Tourism | 66
Catherine Grimley | CR02 | Market Hall Development Initiatives | Utilising previous procurement experience and the APSE Benchmarking Membership an Evaluation of future options for the Market offering will be completed | 2020-03-31 | Research has commenced on best practice and trends around market halls and this will continue in quarters 2 and 3 in preparation for a final report |  | Not Yet Due |  |  |  |  | Not Yet Due |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Mark Rizk | Markets | Community Regeneration | Cultural Services | Leisure, Culture & Tourism | 67
Planning Manager | CR03 | Major Planning Applications Determined Within 13 Weeks | Top Quartile as measured against relevant MHCLG figures |  | 11 applications all within time - 100% |  | On Track to be Achieved |  | 8 Applications - 7 within time = 88% | 95% |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Sal Khan | Planning | Community Regeneration | Planning | Regeneration & Planning Policy | 68
Planning Manager | CR04 | Minor Planning Applications Determined Within 8 Weeks | Top Quartile as measured against relevant MHCLG figures |  | 74 applications, 73 within time - 99% |  | On Track to be Achieved |  | 62 Applications - 55 within time = 89% | 94% |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Sal Khan | Planning | Community Regeneration | Planning | Regeneration & Planning Policy | 69
Planning Manager | CR05 | Other Planning Applications Determined in 8 Weeks | Top Quartile as measured against relevant MHCLG figures |  | 135 applications, 133 within time - 99% |  | On Track to be Achieved |  | 145 Applications - 143 within time = 99% | 99% |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Sal Khan | Planning | Community Regeneration | Planning | Regeneration & Planning Policy | 70
Planning Manager | CR06 | Improve Planning Guidance | Endorse Development Guidance for Station Street Southern Brewery Site | 2019-12-31 | Work underway |  | On Track to be Achieved |  | Work underway |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q1 | Sal Khan | Planning | Community Regeneration | Planning | Regeneration & Planning Policy | 71
Planning Manager | CR07 | Improve Planning Guidance | Revise and adopt Housing Choice SPD | 2019-12-31 | Report drafted |  | On Track to be Achieved |  | Consultation closes Friday 18th October |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q3 | Sal Khan | Planning | Community Regeneration | Planning | Regeneration & Planning Policy | 72
Planning Manager | CR08 | Raise Design Quality within the Borough | Adopt Shopfronts Design Guide SPD | 2019-10-31 | Out for consultation |  | On Track to be Achieved |  | To be adopted by EDR in October |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q3 | Sal Khan | Planning | Community Regeneration | Planning | Regeneration & Planning Policy | 73
Planning Manager | CR09 | Raise Design Quality within the Borough | Adopt addendum to ESBC Design Guide SPD | 2019-10-31 | Out for consultation |  | On Track to be Achieved |  | To be adopted by EDR in October |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q3 | Sal Khan | Planning | Community Regeneration | Planning | Regeneration & Planning Policy | 74
Planning Manager | CR10 | Raise Design Quality within the Borough | Brewery Building Conversion Design Guidance SPD | 2020-03-31 | Early work on this report is underway |  | On Track to be Achieved |  | Work underway |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Sal Khan | Planning | Community Regeneration | Planning | Regeneration & Planning Policy | 75
Planning Manager | CR11 | Delivering Improvements to the Washlands | Contribute to the ongoing partnership working relating to the Washlands | 2020-03-31 | There is ingoing work on this project |  | On Track to be Achieved |  | Ongoing contribution provided to project |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Sal Khan | Planning | Community Regeneration | Planning | Regeneration & Planning Policy | 76
Thomas Deery | CR12 | Improve wayfinding on Worthington Way, High Street and Washlands area: easy in and out of Burton | Establish clearer routes in and out of the town | 2019-10-31 | Existing wayfinding arrangements are currently being reviewed. |  | On Track to be Achieved |  | Proposals for new wayfinding routes are being developed using both the Public Realm Improvement Plan and the Burton Regeneration Strategy as guidance. |  |  | On Track to be Achieved | Proposals will be considered by the Deputy Leader in October. |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q3 | Andy O'Brien | Enterprise | Community Regeneration | Regeneration | Regeneration & Planning Policy | 77
Mark Rizk | CR13 | Introduce new public realm civic space | Working with new Street traders forum, introduce a food hall concept into the Market Hall | 2019-12-31 |  |  | Not Yet Due |  | Plans in place for a trial food hall offer in December |  |  | Not Yet Due |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q3 | Mark Rizk | Markets | Community Regeneration | Regeneration | Regeneration & Planning Policy | 78
Thomas Deery | CR14 | Look to roll out learning from improvements made in Burton to Uttoxeter and other large settlements | Consider learnings from regeneration that can be applied elsewhere in the borough with a view to applying for funds from phase 2 of the Future High Street Funds | 2020-03-31 |  |  | Not Yet Due |  |  |  |  | Not Yet Due |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Andy O'Brien | Enterprise | Community Regeneration | Regeneration | Regeneration & Planning Policy | 79
Thomas Deery | CR15 | Consider a Business Improvement District (BID) in Burton Town Centre to stimulate private sector investment in the Town Centre | Seek a BID ‘memorandum of understanding’ with the Burton Chamber of Commerce and Burton Small Business Federation | 2019-10-31 | Work is progressing to finalise a MoU. |  | On Track to be Achieved |  | A draft MOU has been sent to the Chamber of Commerce for their comment and consideration. |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q3 | Andy O'Brien | Enterprise | Community Regeneration | Regeneration | Regeneration & Planning Policy | 80
Thomas Deery | CR16 | Promote local employment opportunities | Support the delivery of three job fairs | 2020-03-31 | A jobs fair was delivered in June 2019. | 3 or 4 | On Track to be Achieved | The next jobs fair is planned for 10th September 2019, however there may be an interim event to address a more pressing employment issue in Burton. | The jobs fair on 10th September 2019 was successful. | 2 | 3 | On Track to be Achieved | A further event will be delivered during Q4. |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Andy O'Brien | Enterprise | Community Regeneration | Regeneration | Regeneration & Planning Policy | 81
Thomas Deery | CR17 | Consider business activity and economic performance in East Staffordshire | Report on local business activity during 2019 | 2020-03-31 | A procurement exercise is currently underway to appoint a consultant who will conduct a quantitative survey of businesses in East Staffordshire. This will provide information for the report. |  | On Track to be Achieved | The survey work will take place over the Summer and likely complete in October/November 2019. | The survey work is in progress and will be completing in November 2019. |  |  | On Track to be Achieved | The report will be delivered to Cabinet in March 2020. |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Andy O'Brien | Enterprise | Community Regeneration | Regeneration | Regeneration & Planning Policy | 82
Sara Botham | CR18 | Neighbourhood Fund implementation | 7 existing projects and 5 new projects brought to completion | 2020-03-31 | 2 existing projects brought to completion and 2 new projects brought to completion |  | On Track to be Achieved |  | To date 2 new projects brought to completion and 3 existing projects brought to completion. | 3 existing 2 new |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Mark Rizk | Neighbourhood Working | Community Regeneration | Regeneration | Regulatory & Community Support | 83
Sara Botham | CR19 | Neighbourhood Fund implementation | All Neighbourhood Fund projects to be identified with funding allocated | 2019-09-30 | Progress to be reviewed in Q2, funding panel meetings commenced end of May 2019 |  | On Track to be Achieved |  | All projects identified by end of September with in-principle funding awards made (funding allocated but not necessarily paid out). Total of £298,693.90 committed over 3 years to support 30 projects. Work will continue to bring all projects to completion. |  |  | Fully Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q2 | Mark Rizk | Neighbourhood Working | Community Regeneration | Regeneration | Regulatory & Community Support | 84
Sara Botham | CR20 | Neighbourhood Fund implementation | Review the Neighbourhood Fund project | 2020-03-31 | Will start end of Q3 |  | Not Yet Due |  | Review will be able to start now all funds have been committed |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Mark Rizk | Neighbourhood Working | Community Regeneration | Regeneration | Regulatory & Community Support | 85
Michael Hovers | EHW01 | Develop a Town Centre planting strategy | Develop a Borough wide Planting Strategy | 2019-10-31 | Site visits and potential costs relating to a potential planting scheme have taken place. Draft report with images and costs to be presented to the Deputy Leader in Qtr2 |  | On Track to be Achieved |  | Meeting held with Head of Service and Deputy Leader to explain the design ethos behind the proposed planting strategy and how this will shape up in future years. EDR prepared and ready for signing in October |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q3 | Mark Rizk | Communities & Open Spaces | Environment and Health & Wellbeing | Cultural Services | Leisure, Culture & Tourism | 86
Michael Hovers | EHW02 | In Bloom/Green Flag | Deliver a minimum of two Golds at the regional “In Bloom awards” and support Winshill In Bloom at the National RHS Awards | 2019-09-30 | Judging taking place in July with results expected in September |  | Not Yet Due |  | 3 golds achieved along with a number of special recognition awards |  |  | Fully Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q2 | Mark Rizk | Communities & Open Spaces | Environment and Health & Wellbeing | Cultural Services | Leisure, Culture & Tourism | 87
Michael Hovers | EHW03 | In Bloom/Green Flag | Achieve 2 Green Flag Awards at Bramshall Park and Stapenhill Gardens | 2019-11-30 | Judging took place in May. Results are expected to be announced in July and September |  | Not Yet Due |  | Judging results received in Q2 and Green Flag status reached for Bramshall. However, the combined Stapenhill Gardens and Washlands entry did not reach Green Flag standard. This was because the ambitions of the Washlands project have yet to come into fruition. Judges identified that Stapenhill Gardens was worthy of Green Flag status if entered as a separate entry without the Washlands |  |  | Off Target |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q3 | Mark Rizk | Communities & Open Spaces | Environment and Health & Wellbeing | Cultural Services | Leisure, Culture & Tourism | 88
Paul Farrer | EHW04 | Street Cleansing - Litter | Maintain Top Quartile Performance |  | Surveys run April - July. These results due in Q2 |  | Not Yet Due |  | April - July 0% |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Sal Khan | Environment | Environment and Health & Wellbeing | Environment | Environment & Housing | 89
Paul Farrer | EHW05 | Street Cleansing - Detritus | Maintain Top Quartile Performance |  | Surveys run April - July. These results due in Q2 |  | Not Yet Due |  | April - July 0% |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Sal Khan | Environment | Environment and Health & Wellbeing | Environment | Environment & Housing | 90
Paul Farrer | EHW06 | Street Cleansing - Graffiti | Maintain Top Quartile Performance |  | Surveys run April - July. These results due in Q2 |  | Not Yet Due |  | April - July 0% |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Sal Khan | Environment | Environment and Health & Wellbeing | Environment | Environment & Housing | 91
Paul Farrer | EHW07 | Street Cleansing – Fly-Posting | Maintain Top Quartile Performance |  | Surveys run April - July. These results due in Q2 |  | Not Yet Due |  | April - July 0% |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Sal Khan | Environment | Environment and Health & Wellbeing | Environment | Environment & Housing | 92
Paul Farrer | EHW08 | Recycling | Household Waste Recycled and Composted: Maintain Top Quartile Performance |  | 50.6% estimated as not all tonnage data received |  | On Track to be Achieved |  | 51% - estimated as not all tonnages received | 50.9% - estimated as not all Q2 data received |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Sal Khan | Environment | Environment and Health & Wellbeing | Environment | Environment & Housing | 93
Paul Farrer | EHW09 | Waste Reduction | Residual Household Waste Per Household: Maintain Top Quartile Performance |  | 117.16kg - estimated as not all tonnage data received |  | On Track to be Achieved |  | 119.12kg - estimated as not all tonnage data received | 240kg - estimated as not all Q2 data received |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Sal Khan | Environment | Environment and Health & Wellbeing | Environment | Environment & Housing | 94
Brett Atkinson | EHW10 | Delivering Better Services to Support Homelessness | Average time from appointment to initial decision for homeless applicants of 10 days |  | 58 Initial Decisions were taken this quarter with the majority of these decisions having been made the same day. | 2 days | On Track to be Achieved | It is noticeable that there were fewer contentious decisions than normal in Q1, and therefore the end of year forecast needs to take account of this. | 71 initial decisions were taken in Q2 with an average time of 3 days. | 2.5 days | 2.5 days | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Sal Khan | Housing Options | Environment and Health & Wellbeing | Housing & Homelessness | Environment & Housing | 95
Brett Atkinson | EHW11 | Continue to Maximise Utilisation of Self Contained Temporary Accommodation for Homeless Applicants | Reduce ‘Key to Key’ Void Turnaround to an average of 6 working days |  | The current average of 12 days is behind target, however there is confidence the target can be met across the 12 months. | 6 days | In Danger of Falling Behind Target | There have been anomalies in Q1 which are unlikely to be repeated, and the overall process has been sharpened to drive significant improvements in Q2. One property has been removed from the figures as it was in need of serious maintenance, (VERY) deep cleaning, redecorating etc. as the property was soiled and in a squalid state due to the occupant’s long term hoarding behaviours. | The average for Q2 across 6 key to key occurrences is 4.8 days. | 8.4 days | 6 days | On Track to be Achieved | The Q1 figure of 12 days has meant that the average remains above target, but the Q2 performance gives me confidence that that target will be achieved by year end. |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Qtrly | Sal Khan | Housing Options | Environment and Health & Wellbeing | Housing & Homelessness | Environment & Housing | 96
Brett Atkinson | EHW12 | Review options for continuing outreach services to Rough Sleepers | Report completed | 2019-07-31 | A report reviewing the options for continuing the Rough Sleepers Outreach Service is on the agenda for Cabinet on 15 July 2019. |  | On Track to be Achieved |  | Recommendation to continue the service approved at Cabinet on 15 July 2019. |  |  | Fully Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q2 | Sal Khan | Housing Options | Environment and Health & Wellbeing | Housing & Homelessness | Environment & Housing | 97
Brett Atkinson | EHW13 | Delivering Better Services to Support Homelessness | Launch Campaign to raise awareness of rough sleeping, street living and street begging | 2019-06-30 | The campaign was launched by the forming of 'Burton & East Staffordshire Homelessness Partnership' on 19 June 2019. |  | Fully Achieved | This partnership with the third sector homelessness service providers will be an effective means of raising awareness. |  |  |  | Fully Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q1 | Sal Khan | Housing Options | Environment and Health & Wellbeing | Housing & Homelessness | Environment & Housing | 98
Brett Atkinson | EHW14 | Produce a Business Plan to tackle selected empty homes | Business Plan Produced | 2019-04-30 | A Business Plan was produced, and a decision was made by EDR no 1010/19 dated 11 April 2019 to appoint Grafton (UK) Ltd to deliver an empty homes service on behalf of the Council. |  | Fully Achieved | The contract mobilised on 1 May 2019 for a 5 year period. |  |  |  | Fully Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q1 | Sal Khan | Housing Options | Environment and Health & Wellbeing | Housing & Homelessness | Environment & Housing | 99
Margaret Woolley | EHW15 | Deliver Focussed Environmental Health Initiatives | Provide a six monthly report on Regulatory Services activity including initiatives covering licensed gambling premises, Civil Enforcement, Scrap metal compliance etc. | 2019-10-31 | Initiatives are arranged, report to be pulled together |  | On Track to be Achieved | Pull together report detailing the initiatives that have been undertaken so far. | Items collated and ready for report |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q3 | Mark Rizk | Licensing | Environment and Health & Wellbeing | Regulatory Services | Regulatory & Community Support | 100
Rachel Liddle | EHW16 | Deliver Focussed Environmental Health Initiatives | Undertake a targeted initiative to identify Unlicensed Houses in Multiple Occupation | 2020-03-31 | Application for and execution of a warrant in an unlicensed HMO. Enforcement action currently being taken. |  | On Track to be Achieved | Further large scale initiative to begin in August 2019 | 200 potential unlicensed HMOs have been identified using information currently held. This has been prioritised on a case by case basis which are being written to using data from Council Tax and Land Registry. |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Mark Rizk | Environmental Health | Environment and Health & Wellbeing | Regulatory Services | Regulatory & Community Support | 101
Rachel Liddle | EHW17 | Deliver Focussed Environmental Health Initiatives | Complete an evaluation of all Licensable Animal Activities and report to DEFRA | 2020-03-31 | Animal Licensing has been completed for all renewals. Performing animals are currently being reviewed and will feed in to the annual return to DEFRA |  | On Track to be Achieved | Dynamics to be updated for reporting | Draft reporting template is being created for Dynamics |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Mark Rizk | Environmental Health | Environment and Health & Wellbeing | Regulatory Services | Regulatory & Community Support | 102
Thomas Deery | EHW18 | Improve active links: easy in and easy out of Burton | Working with SCC, audit the existing walking and cycling network and propose the upgrade and improvement of the network to ensure Burton is well connected to and from its town centre | 2019-12-31 | Initial audit work is underway, looking at the existing walking and cycling network in Burton town centre and the Washlands. |  | On Track to be Achieved |  | SCC will be launching a consultation on the Local Cycling and Walking Infrastructure plan by the end of November 2019. |  |  | On Track to be Achieved | A full consultation response will be compiled in December 2019 to feed into the final version of the infrastructure plan. |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q3 | Andy O'Brien | Enterprise | Environment and Health & Wellbeing | Regeneration | Regeneration & Planning Policy | 103
Thomas Deery | EHW19 | Improve active and green links: easy in and easy out of Burton | Begin scoping works for a bus interchange and active travel hubs in the Burton Place area | 2019-12-31 | Initial discussions with Staffordshire County Council have taken place, looking at understanding the scope of technical reports that will be required. |  | On Track to be Achieved |  | Engagement with SCC is ongoing and plans to begin scoping works are in motion. |  |  | On Track to be Achieved | Scoping works to begin by December 2019. |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q3 | Andy O'Brien | Enterprise | Environment and Health & Wellbeing | Regeneration | Regeneration & Planning Policy | 104
Thomas Deery | EHW20 | Upgrade Burton Railway Station in terms of functionality and aesthetics | Continue to work with the relevant rail authorities and partners to invest in and improve the fabric of Burton Railway Station building | 2020-03-31 | The Council continues to work with a number of partners towards supporting the improvement of the Burton Railway Station building. |  | On Track to be Achieved |  | The Council's involvement in the local network group is ongoing. |  |  | On Track to be Achieved |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Andy O'Brien | Enterprise | Environment and Health & Wellbeing | Regeneration | Regeneration & Planning Policy | 105
Thomas Deery | EHW21 | Upgrade Burton Railway Station in terms of functionality and aesthetics | Work with partners to lobby for the opening of the Burton to Lichfield and Ivanhoe rail links | 2020-03-31 |  |  | Not Yet Due |  | The Council has agreed to contribute £5,000 towards a study that has been jointly funded by the Local Authorities affected by the Ivanhoe rail line. |  |  | On Track to be Achieved | The Council will be writing to Midlands Engine in conjunction with Lichfield DC and Staffordshire CC in order to promote the need for a Burton-Lichfield rail line. |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Andy O'Brien | Enterprise | Environment and Health & Wellbeing | Regeneration | Regeneration & Planning Policy | 106
Michael Hovers | EHW22 | Achieve optimum working in economic partnership | Continue to work with strategic tourism partners to facilitate the promotion of tourism | 2020-03-31 | Officers remain engaged with strategic partners and are working with the Deputy Leader to agree a pathway for promoting tourism |  | Not Yet Due |  |  |  |  | Not Yet Due |  |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Mark Rizk | Communities & Open Spaces | Environment and Health & Wellbeing | Regeneration | Leisure, Culture & Tourism | 107
Thomas Deery | EHW23 | Achieve optimum working in economic partnership | Support partners such as the National Forest and Transforming The Trent Valley in delivering environmental enhancement projects, such as the Brook Hollows project | 2020-03-31 | The Council continues to work with strategic tourism partners on enhancing local regeneration projects such as the Washlands and Brook Hollows. |  | On Track to be Achieved |  | Engagement with partners on regeneration projects is ongoing. |  |  | On Track to be Achieved | As the TTTV partnership is delivering a range of projects in the region, we will be reviewing how best to effectively support the delivery of those projects. |  |  |  | Update Not Provided |  |  |  | Update not provided |  | Q4 | Andy O'Brien | Enterprise | Environment and Health & Wellbeing | Regeneration | Regeneration & Planning Policy | 108
Update not provided
Fully Achieved
Numerical Outturn Within 5% Tolerance
Numerical Outturn Within 10% Tolerance
Target Partially Met
Off Target
Completed Significantly After Target Deadline
Completion Date Within Reasonable Tolerance
Deferred
Deleted
Fully Achieved
On Track to be Achieved
In Danger of Falling Behind Target
Off Target
Completed Behind Schedule
Deleted
Not Yet Due
Update Not Provided
Deferred
Note on D29: …"to showcase the Council and raise the profile of its services". (p26)
Note on D30: …"to showcase the Council and raise the profile of its services". (p26)
Note on D37: in relation to waste management p.27

## Q1 Summary
Click here to return to index page
Quarter One (2019/20) | Green |  | Amber |  | Red
| Number of Indicators | Percentage | Number of Indicators | Percentage | Number of Indicators | Percentage
Overall Performance
All due targets | 80 | 96.39% | 2 | 2.41% | 1 | 1.205%
Corporate Priority
Value for Money Council | 50 | 96.15% | 1 | 1.923% | 1 | 1.923%
Environment and Health & Well Being | 14 | 93.33% | 1 | 6.667% | 0 | 0%
Community Regeneration | 16 | 100% | 0 | 0% | 0 | 0%

## Q2 Summary
Click here to return to index page
Quarter Two (2019/20) | Green |  | Amber |  | Red
| Number of Indicators | Percentage | Number of Indicators | Percentage | Number of Indicators | Percentage
Overall Performance
All due targets | 95 | 95.96% | 2 | 2.02% | 2 | 2.02%
Corporate Priority
Value for Money Council | 57 | 95% | 2 | 3.333% | 1 | 1.667%
Environment and Health & Well Being | 21 | 95.45% | 0 | 0% | 1 | 4.545%
Community Regeneration | 17 | 100% | 0 | 0% | 0 | 0%

## 2a. % By Priority
QUARTER ONE (April - June 2019) | [5 empty] | QUARTER TWO (July - Sept 2019) | [5 empty] | QUARTER THREE (Oct - Dec 2019) | [5 empty] | QUARTER FOUR (Jan - Mar 2020)
ALL TARGETS | [5 empty] | ALL TARGETS | [5 empty] | ALL TARGETS | [5 empty] | ALL TARGETS
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | 8 | 7.339% | 73.39% | 9.639% | 96.39% | Target Fully Achieved | 23 | 21.1% | 87.16% | 23.23% | 95.96% | Target Fully Achieved | 0 | 0% | 0% | #DIV/0! | #DIV/0! | Target Fully Achieved |  |  |  |  | 0%
On Track to be Achieved | 72 | 66.06% |  | 86.75% |  | On Track to be Achieved | 72 | 66.06% |  | 72.73% |  | On Track to be Achieved | 0 | 0% |  | #DIV/0! |  | On Track to be Achieved
In Danger of Falling Behind Target | 2 | 1.835% | 1.835% | 2.41% | 2.41% | In Danger of Falling Behind Target | 2 | 1.835% | 1.835% | 2.02% | 2.02% | In Danger of Falling Behind Target | 0 | 0% | 0% | #DIV/0! | #DIV/0! | Numerical Outturn Within 10% Tolerance |  |  |  |  | 0%
Target Partially Met
Completion Date Within Reasonable Tolerance
Completed Behind Schedule | 0 | 0% | 0.9174% | 0% | 1.205% | Completed Behind Schedule | 1 | 0.9174% | 1.835% | 1.01% | 2.02% | Completed Behind Schedule | 0 | 0% | 0% | #DIV/0! | #DIV/0! | Completed Significantly After Target Deadline |  |  |  |  | 0%
Off Target | 1 | 0.9174% |  | 1.205% |  | Off Target | 1 | 0.9174% |  | 1.01% |  | Off Target | 0 | 0% |  | #DIV/0! |  | Off Target
Not yet due to be reported | 26 | 23.85% | 23.85% |  |  | Not yet due to be reported | 10 | 9.174% | 9.174% |  |  | Not yet due to be reported | 0 | 0% | 0% |  |  | Not yet due to be reported
Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | 0% | 0% |  |  | Update not provided | 109 | 100% | 100% |  |  | Update not provided
Deferred | 0 | 0% | 0% |  |  | Deferred | 0 | 0% | 0% |  |  | Deferred | 0 | 0% | 0% |  |  | Deferred
Deleted | 0 | 0% | 0% |  | Back to index | Deleted | 0 | 0% | 0% |  | Back to index | Deleted | 0 | 0% | 0% |  | Back to index | Deleted |  |  |  |  | Back to index
Totals | 109 |  |  |  |  | Totals | 109 |  |  |  |  | Totals | 109 |  |  |  |  | Totals
Due to be Reported | 83 |  |  |  |  | Due to be Reported | 99 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported
VALUE FOR MONEY COUNCIL | [5 empty] | VALUE FOR MONEY COUNCIL | [5 empty] | VALUE FOR MONEY COUNCIL | [5 empty] | VALUE FOR MONEY COUNCIL SERVICES
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | 6 | 9.091% | 75.76% | 11.54% | 96.15% | Target Fully Achieved | 18 | 27.27% | 86.36% | 30% | 95% | Target Fully Achieved | 0 | 0% | 0% | #DIV/0! | #DIV/0! | Target Fully Achieved |  |  |  |  | 0%
On Track to be Achieved | 44 | 66.67% |  | 84.62% |  | On Track to be Achieved | 39 | 59.09% |  | 65% |  | On Track to be Achieved | 0 | 0% |  | #DIV/0! |  | On Track to be Achieved
In Danger of Falling Behind Target | 1 | 1.515% | 1.515% | 1.923% | 1.923% | In Danger of Falling Behind Target | 2 | 3.03% | 3.03% | 3.333% | 3.333% | In Danger of Falling Behind Target | 0 | 0% | 0% | #DIV/0! | #DIV/0! | Numerical Outturn Within 10% Tolerance |  |  |  |  | 0%
Target Partially Met
Completion Date Within Reasonable Tolerance
Completed Behind Schedule | 0 | 0% | 1.515% | 0% | 1.923% | Completed Behind Schedule | 1 | 1.515% | 1.515% | 1.667% | 1.667% | Completed Behind Schedule | 0 | 0% | 0% | #DIV/0! | #DIV/0! | Completed Significantly After Target Deadline |  |  |  |  | 0%
Off Target | 1 | 1.515% |  | 1.923% |  | Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | 0% |  | #DIV/0! |  | Off Target
Not yet due to be reported | 14 | 21.21% | 21.21% |  |  | Not yet due to be reported | 6 | 9.091% | 9.091% |  |  | Not yet due to be reported | 0 | 0% | 0% |  |  | Not yet due to be reported
Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | 0% | 0% |  |  | Update not provided | 66 | 100% | 100% |  |  | Update not provided
Deferred | 0 | 0% | 0% |  |  | Deferred | 0 | 0% | 0% |  |  | Deferred | 0 | 0% | 0% |  |  | Deferred
Deleted | 0 | 0% | 0% |  | Back to index | Deleted | 0 | 0% | 0% |  | Back to index | Deleted | 0 | 0% | 0% |  | Back to index | Deleted |  |  |  |  | Back to index
Totals | 66 |  |  |  |  | Totals | 66 |  |  |  |  | Totals | 66 |  |  |  |  | Totals
Due to be Reported | 52 |  |  |  |  | Due to be Reported | 60 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported
ENVIRONMENT AND HEALTH & WELL BEING | [5 empty] | ENVIRONMENT AND HEALTH & WELL BEING | [5 empty] | ENVIRONMENT AND HEALTH & WELL BEING | [5 empty] | PROMOTING LOCAL ECONOMIC GROWTH
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | 2 | 8.696% | 60.87% | 13.33% | 93.33% | Target Fully Achieved | 4 | 17.39% | 91.3% | 18.18% | 95.45% | Target Fully Achieved | 0 | 0% | 0% | #DIV/0! | #DIV/0! | Target Fully Achieved |  |  |  |  | 0%
On Track to be Achieved | 12 | 52.17% |  | 80% |  | On Track to be Achieved | 17 | 73.91% |  | 77.27% |  | On Track to be Achieved | 0 | 0% |  | #DIV/0! |  | On Track to be Achieved
In Danger of Falling Behind Target | 1 | 4.348% | 4.348% | 6.667% | 6.667% | In Danger of Falling Behind Target | 0 | 0% | 0% | 0% | 0% | In Danger of Falling Behind Target | 0 | 0% | 0% | #DIV/0! | #DIV/0! | Numerical Outturn Within 10% Tolerance |  |  |  |  | 0%
Target Partially Met
Completion Date Within Reasonable Tolerance
Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | 0% | 4.348% | 0% | 4.545% | Completed Behind Schedule | 0 | 0% | 0% | #DIV/0! | #DIV/0! | Completed Significantly After Target Deadline |  |  |  |  | 0%
Off Target | 0 | 0% |  | 0% |  | Off Target | 1 | 4.348% |  | 4.545% |  | Off Target | 0 | 0% |  | #DIV/0! |  | Off Target
Not yet due to be reported | 8 | 34.78% | 34.78% |  |  | Not yet due to be reported | 1 | 4.348% | 4.348% |  |  | Not yet due to be reported | 0 | 0% | 0% |  |  | Not yet due to be reported
Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | 0% | 0% |  |  | Update not provided | 23 | 100% | 100% |  |  | Update not provided
Deferred | 0 | 0% | 0% |  |  | Deferred | 0 | 0% | 0% |  |  | Deferred | 0 | 0% | 0% |  |  | Deferred
Deleted | 0 | 0% | 0% |  | Back to index | Deleted | 0 | 0% | 0% |  | Back to index | Deleted | 0 | 0% | 0% |  | Back to index | Deleted |  |  |  |  | Back to index
Totals | 23 |  |  |  |  | Totals | 23 |  |  |  |  | Totals | 23 |  |  |  |  | Totals
Due to be Reported | 15 |  |  |  |  | Due to be Reported | 22 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported
COMMUNITY REGENERATION | [5 empty] | COMMUNITY REGENERATION | [5 empty] | COMMUNITY REGENERATION | [5 empty] | PROTECTING AND STRENGTHENING COMMUNITIES
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | Total % of due indicators
Target Fully Achieved | 0 | 0% | 80% | 0% | 100% | Target Fully Achieved | 1 | 5% | 85% | 5.882% | 100% | Target Fully Achieved | 0 | 0% | 0% | #DIV/0! | #DIV/0! | Target Fully Achieved |  |  |  |  | 0%
On Track to be Achieved | 16 | 80% |  | 100% |  | On Track to be Achieved | 16 | 80% |  | 94.12% |  | On Track to be Achieved | 0 | 0% |  | #DIV/0! |  | On Track to be Achieved
In Danger of Falling Behind Target | 0 | 0% | 0% | 0% | 0% | In Danger of Falling Behind Target | 0 | 0% | 0% | 0% | 0% | In Danger of Falling Behind Target | 0 | 0% | 0% | #DIV/0! | #DIV/0! | Numerical Outturn Within 10% Tolerance |  |  |  |  | 0%
Target Partially Met
Completion Date Within Reasonable Tolerance
Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | 0% | 0% | 0% | 0% | Completed Behind Schedule | 0 | 0% | 0% | #DIV/0! | #DIV/0! | Completed Significantly After Target Deadline |  |  |  |  | 0%
Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | 0% |  | 0% |  | Off Target | 0 | 0% |  | #DIV/0! |  | Off Target
Not yet due to be reported | 4 | 20% | 20% |  |  | Not yet due to be reported | 3 | 15% | 15% |  |  | Not yet due to be reported | 0 | 0% | 0% |  |  | Not yet due to be reported
Update not provided | 0 | 0% | 0% |  |  | Update not provided | 0 | 0% | 0% |  |  | Update not provided | 20 | 100% | 100% |  |  | Update not provided
Deferred | 0 | 0% | 0% |  |  | Deferred | 0 | 0% | 0% |  |  | Deferred | 0 | 0% | 0% |  |  | Deferred
Deleted | 0 | 0% | 0% |  | Back to index | Deleted | 0 | 0% | 0% |  | Back to index | Deleted | 0 | 0% | 0% |  | Back to index | Deleted |  |  |  |  | Back to index
Totals | 20 |  |  |  |  | Totals | 20 |  |  |  |  | Totals | 20 |  |  |  |  | Totals
Due to be Reported | 16 |  |  |  |  | Due to be Reported | 17 |  |  |  |  | Due to be Reported | 0 |  |  |  |  | Due to be Reported
Note on W9: Jennifer Norman: Only Red and Green statuses for Year End??
Note on W31: Jennifer Norman: Only Red and Green statuses for Year End??
Note on W53: Jennifer Norman: Only Red and Green statuses for Year End??
Note on W75: Jennifer Norman: Only Red and Green statuses for Year End??

## 2b. Charts by Priority
Charts by Corporate Priority | Please note that all charts shown below can be amended to be displayed in alternative styles. Please right click on the relevant chart, select "change chart type" and choose your preferred chart option.
Back to index
|  | Back to index | Back to index | Back to index | Back to index
OVERALL PERFORMANCE
[8 empty] | Q1 | Q2 | Q3 | Q4
[7 empty] | Green | 96.39% | 95.96% | #DIV/0! | 0%
[7 empty] | Amber | 2.41% | 2.02% | #DIV/0! | 0%
[7 empty] | Red | 1.205% | 2.02% | #DIV/0! | 0%
|  | Back to index | Back to index | Back to index | Back to index
VALUE FOR MONEY COUNCIL
[8 empty] | Q1 | Q2 | Q3 | Q4
[7 empty] | Green | 96.15% | 95% | #DIV/0! | 0%
[7 empty] | Amber | 1.923% | 3.333% | #DIV/0! | 0%
[7 empty] | Red | 1.923% | 1.667% | #DIV/0! | 0%
|  | Back to index | Back to index | Back to index | Back to index
ENVIRONMENT AND HEALTH & WELL BEING
[8 empty] | Q1 | Q2 | Q3 | Q4
[7 empty] | Green | 93.33% | 95.45% | #DIV/0! | 0%
[7 empty] | Amber | 6.667% | 0% | #DIV/0! | 0%
[7 empty] | Red | 0% | 4.545% | #DIV/0! | 0%
|  | Back to index | Back to index | Back to index |  | Back to index
COMMUNITY REGENERATION
[8 empty] | Q1 | Q2 | Q3 | Q4
[7 empty] | Green | 100% | 100% | #DIV/0! | 0%
[7 empty] | Amber | 0% | 0% | #DIV/0! | 0%
[7 empty] | Red | 0% | 0% | #DIV/0! | 0%

## 4. Status Tracking
Back to index
CP Ref | Measures | Target 2019/20 | Quarter 1 On track? (R/A/G) | Direction of Travel From Q1 to Q2 | Quarter 2 On track? (R/A/G) | Direction of Travel From Q2 to Q3 | Quarter 3 On track? (R/A/G) | Direction of Travel From Q3 to Q4 | Quarter 4 Achieved? (R/A/G)
VFM01 | Set the MTFS for 2020/21 onwards | Set Budget for Council Approval | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided | Ü
VFM02 | Savings targets for 2019/20 | Achieve Savings Targets as Stated in the Medium Term Financial Strategy | Not Yet Due |  | Not Yet Due |  | Update Not Provided |  | Update not provided | Ý |  | è
VFM03 | Having an approved Statement of Accounts | Submit Statement of Accounts by New Statutory Deadline | On Track to be Achieved |  | Fully Achieved |  | Update Not Provided |  | Update not provided | Þ |  | ê
VFM04 | Responding to Significant Local Government Finance Changes and Assessing the Impact on the Council’s Financial Position | Activities Throughout the Year Reported in Line with the Timed Responses | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided | n/a | ê
VFM05 | Internal Audit Service Procurement | Procurement concluded and new contract awarded | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided |  | é
VFM06 | Working towards the Government’s new HMRC VAT Digitalisation Compliance requirements | Compliance Report completed | Not Yet Due |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided |  | è
VFM07 | Continuing to digitise SMARTER services | Secure Integrated Service Request and Payment mechanism developed and implemented | On Track to be Achieved |  | In Danger of Falling Behind Target |  | Update Not Provided |  | Update not provided
VFM08 | Continuing to digitise SMARTER services | Audio recording of Council meetings added to Corporate Website | On Track to be Achieved |  | Fully Achieved |  | Update Not Provided |  | Update not provided
VFM09 | Continuing to digitise SMARTER services | 80% of 2019/20 Milestones in New Digital Strategy Achieved | Not Yet Due |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM10 | Providing a more secure ICT working environment | Security Arrangements to Meet Requirements of PSN (or Replacement) | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM11 | Providing a more secure ICT working environment | Preferred biometric approach to password replacement identified and commenced | On Track to be Achieved |  | Fully Achieved |  | Update Not Provided |  | Update not provided
VFM12 | Successfully deliver local elections | Local elections delivered | Fully Achieved |  | Fully Achieved |  | Update Not Provided |  | Update not provided
VFM13 | Carry out detailed Procurement / Contractor Consolidation / Spend Analysis | Report and way forward approved | Not Yet Due |  | Not Yet Due |  | Update Not Provided |  | Update not provided
VFM14 | Increasing Staffing Availability Through Reduced Sickness | Short Term Sickness Days Average: 2.75 days | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM15 | Improve On The Average Time To Pay Creditors | Average Time To Pay Creditors: 12 days | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM16 | Legal and Assets | Carry out works to Canal Street industrial units, as identified in the condition survey | Not Yet Due |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM17 | Legal and Assets | Condition Survey commissioned for miscellaneous Council properties | Not Yet Due |  | Fully Achieved |  | Update Not Provided |  | Update not provided
VFM18 | Maintain Robust Mechanisms for Contract Managing the New Leisure Service Arrangements | Report on the performance of the Leisure Services contractor on a quarterly basis | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM19 | Review Strategic Sport and Leisure Approach in Line with New Leisure Service Arrangements | Undertake a benchmarking exercise to support the delivery of the leisure management contract | Not Yet Due |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM20 | Review Strategic Sport and Leisure Approach in Line with New Leisure Service Arrangements | Conduct a review of the relevant Sport and Leisure Strategy and Policy Documents and create a plan for their delivery | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM21 | Open Spaces Service Development Initiatives | Review the Open Spaces/Grounds Maintenance Contract in preparation for retendering in 2020/21 | On Track to be Achieved |  | Not Yet Due |  | Update Not Provided |  | Update not provided
VFM22 | Open Spaces Service Development Initiatives | Commission a consultant to assess the potential practical and capital requirements for the expansion of Stapenhill Cemetery | On Track to be Achieved |  | Fully Achieved |  | Update Not Provided |  | Update not provided
VFM23 | Open Spaces Service Development Initiatives | Review the options for improving the energy efficiency of lighting stock on Council land across the Borough | On Track to be Achieved |  | Fully Achieved |  | Update Not Provided |  | Update not provided
VFM24 | Open Spaces Service Development Initiatives | Review the first years performance of the Alertcom lone working system | Fully Achieved |  | Fully Achieved |  | Update Not Provided |  | Update not provided
VFM25 | Brewhouse, Arts and Town Hall Developments | Investigate new models of delivery for the Brewhouse Arts Facilities, Civic Function Suite and Arts Development | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM26 | Improve Awareness of ESBC Venues and Initiatives | Produce Marketing and Development Plans for key services and provide quarterly updates on performance | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM27 | Improve Awareness of ESBC Venues and Initiatives | Deliver a minimum of 2 Town Centre initiatives in Conjunction with local partners | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM28 | Improve Awareness of ESBC Venues and Initiatives | Organise a minimum of 4 “Outreach” Days (1 Per Quarter) to raise the profile of the Council’s services | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM29 | Further Development of SMARTER working (Waste Collection) | Conduct review of Waste Service Two Findings / Update Reports with next steps | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM30 | Further Development of SMARTER working (Street Cleaning) | Implement the SMARTER Street Cleaning Programme Two update reports | Not Yet Due |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM31 | Further Development of SMARTER working (Street Cleaning) | Produce Strategy for engaging with Highways England to improve cleanliness around A38 and associated access roads | Fully Achieved |  | Fully Achieved |  | Update Not Provided |  | Update not provided
VFM32 | Further Development of SMARTER Working (Building Control) | Implement ISO Quality Management System for Building Control | Not Yet Due |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM33 | Minimise The Number Of Missed Bin Collections | Number Of Missed Bin Collections: 2 missed bins per 10,000 collections | In Danger of Falling Behind Target |  | In Danger of Falling Behind Target |  | Update Not Provided |  | Update not provided
VFM34 | Carry out SMARTER Digital Communications | Refreshed Web / Social Media Waste Management and Street Cleaning Section launched | On Track to be Achieved |  | Fully Achieved |  | Update Not Provided |  | Update not provided
VFM35 | Respond to Government Policy Announcements | Complete responses to Government consultations in line with consultation deadlines | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM36a | Continue to Maximise Income Through Effective Collection Processes (Previously BV9) | Council Tax Collection Rates: 98% | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM36b | Continue to Maximise Income Through Effective Collection Processes (Previously BV10) | NNDR Collection Rates: 99% | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM37a | Continue to Maximise Income Through Effective Collection Processes: Reduce Former Years Arrears for Council Tax; NNDR; Sundry Debts | Former Years Arrears for Council Tax; £1,900,000 (net) | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM37b | Continue to Maximise Income Through Effective Collection Processes: Reduce Former Years Arrears for Council Tax; NNDR; Sundry Debts | Former Years Arrears for NNDR; £500,000 (net) | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM37c | Continue to Maximise Income Through Effective Collection Processes: Reduce Former Years Arrears for Council Tax; NNDR; Sundry Debts | Current Years Arrears for Sundry debts; £40,000 (older than 90 days) | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM38a | Maintaining excellent customer access to services with face-to-face and telephony enquiries | 99% of CSC and Telephony Team Enquiries Resolved at First Point of Contact | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM38b | Maintaining excellent customer access to services with face-to-face and telephony enquiries | Minimum 75% Telephony Team Calls Answered Within 10 Seconds | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM39a | Maximise Tax Bases through continued reviews of discounts, exemptions and reliefs | Empty Properties – October 2019 | Not Yet Due |  | Fully Achieved |  | Update Not Provided |  | Update not provided
VFM40 | Continue to Improve the Ways We Provide Benefits to Those Most in Need: Time Taken to Process Benefit New Claims and Change Events (Previously NI 181) | 5 days | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM41a | Working Towards the Reduction of Claimant Error Housing Benefit Overpayments (HBOPs) | 80% of HBOPs Overpayments Recovered During the Year | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM41b | Working Towards the Reduction of Claimant Error Housing Benefit Overpayments (HBOPs) | 85% of HBOPS Processed and on Payment Arrangement | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM42 | Review Council Tax Reduction scheme | Carry Out Review of the Council Tax Reduction Scheme | Not Yet Due |  | Fully Achieved |  | Update Not Provided |  | Update not provided
VFM43 | Review Business Rates Rate Relief policy | Policy reviewed (for next year’s implementation) | Not Yet Due |  | Not Yet Due |  | Update Not Provided |  | Update not provided
VFM44 | Prepare for Universal Credit Managed Migration | Work with DWP and partners, prepare 2 in year progress reports and 1 Member briefing | Not Yet Due |  | Not Yet Due |  | Update Not Provided |  | Update not provided
VFM45 | Continuing to inform and improve Planning awareness with Members | At least 2 briefings delivered to elected members during the year | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM46 | Continuing to inform and improve Planning awareness with Members | Strategic Sites Progress Report delivered | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM47 | Monitor Local Plan Performance | Annual Monitoring Report Prepared | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM48 | Continue to develop SMARTER working practices for Planning | Invalid Applications Review and Report | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM49 | Continue to develop SMARTER working practices for Planning | Adoption of SMARTER Developer Contributions SPD | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM50 | Ensure Robust Licensing Policies | Complete a Review of the Scrap Metal Dealers Policy | Fully Achieved |  | Fully Achieved |  | Update Not Provided |  | Update not provided
VFM51 | Ensure Robust Licensing Policies | Complete a Review of the Charitable Collection Policy | On Track to be Achieved |  | Fully Achieved |  | Update Not Provided |  | Update not provided
VFM52 | Ensure Robust Licensing Policies | Complete a Review of the Licensing Act Policy | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM53 | Ensure an Effective Selective Licensing Scheme | Complete an Evaluation of the Selective Licensing Scheme and consider its future expansion | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM54 | Ensure an Effective Disabled Facilities Grant Service | Complete a Review of the Disabled Facilities Grant Service | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
VFM55 | Develop the use of technology to improve service delivery | Complete a Review of Parking Services and the related use of technology | On Track to be Achieved |  | Fully Achieved |  | Update Not Provided |  | Update not provided
VFM56 | Ensure an Effective Civil and Community Enforcement Service | Review Public Space Protection Orders for Dog Fouling and Alcohol consumption | On Track to be Achieved |  | Fully Achieved |  | Update Not Provided |  | Update not provided
VFM57 | Achieve further investment for our town centres and large settlements | Finalise agreement with SCC to fund the implementation of the co-designed Station Street new public realm project | Off Target |  | Completed Behind Schedule |  | Update Not Provided |  | Update not provided
VFM58 | Achieve further investment for our town centres and large settlements | Consider the outcome of the Council’s expression of interest to the Future High Street Fund | Fully Achieved |  | Fully Achieved |  | Update Not Provided |  | Update not provided
VFM59 | Achieve optimum working in economic partnership | Consider the outcome of the national LEP review findings and implication on the Washlands LEP monies | Fully Achieved |  | Fully Achieved |  | Update Not Provided |  | Update not provided
VFM60 | Progress the commutation of s106 sums to deliver key brownfield development opportunities | Review progress on working in partnership with Burton Rugby Club (Peelcroft) and Molson Coors (Cross Street) | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
CR01 | Market Hall Development Initiatives | Hold at least 25 commercial events in the Market Hall | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
CR02 | Market Hall Development Initiatives | Utilising previous procurement experience and the APSE Benchmarking Membership an Evaluation of future options for the Market offering will be completed | Not Yet Due |  | Not Yet Due |  | Update Not Provided |  | Update not provided
CR03 | Major Planning Applications Determined Within 13 Weeks | Top Quartile as measured against relevant MHCLG figures | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
CR04 | Minor Planning Applications Determined Within 8 Weeks | Top Quartile as measured against relevant MHCLG figures | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
CR05 | Other Planning Applications Determined in 8 Weeks | Top Quartile as measured against relevant MHCLG figures | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
CR06 | Improve Planning Guidance | Endorse Development Guidance for Station Street Southern Brewery Site | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
CR07 | Improve Planning Guidance | Revise and adopt Housing Choice SPD | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
CR08 | Raise Design Quality within the Borough | Adopt Shopfronts Design Guide SPD | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
CR09 | Raise Design Quality within the Borough | Adopt addendum to ESBC Design Guide SPD | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
CR10 | Raise Design Quality within the Borough | Brewery Building Conversion Design Guidance SPD | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
CR11 | Delivering Improvements to the Washlands | Contribute to the ongoing partnership working relating to the Washlands | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
CR12 | Improve wayfinding on Worthington Way, High Street and Washlands area: easy in and out of Burton | Establish clearer routes in and out of the town | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
CR13 | Introduce new public realm civic space | Working with new Street traders forum, introduce a food hall concept into the Market Hall | Not Yet Due |  | Not Yet Due |  | Update Not Provided |  | Update not provided
CR14 | Look to roll out learning from improvements made in Burton to Uttoxeter and other large settlements | Consider learnings from regeneration that can be applied elsewhere in the borough with a view to applying for funds from phase 2 of the Future High Street Funds | Not Yet Due |  | Not Yet Due |  | Update Not Provided |  | Update not provided
CR15 | Consider a Business Improvement District (BID) in Burton Town Centre to stimulate private sector investment in the Town Centre | Seek a BID ‘memorandum of understanding’ with the Burton Chamber of Commerce and Burton Small Business Federation | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
CR16 | Promote local employment opportunities | Support the delivery of three job fairs | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
CR17 | Consider business activity and economic performance in East Staffordshire | Report on local business activity during 2019 | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
CR18 | Neighbourhood Fund implementation | 7 existing projects and 5 new projects brought to completion | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
CR19 | Neighbourhood Fund implementation | All Neighbourhood Fund projects to be identified with funding allocated | On Track to be Achieved |  | Fully Achieved |  | Update Not Provided |  | Update not provided
CR20 | Neighbourhood Fund implementation | Review the Neighbourhood Fund project | Not Yet Due |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
EHW01 | Develop a Town Centre planting strategy | Develop a Borough wide Planting Strategy | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
EHW02 | In Bloom/Green Flag | Deliver a minimum of two Golds at the regional “In Bloom awards” and support Winshill In Bloom at the National RHS Awards | Not Yet Due |  | Fully Achieved |  | Update Not Provided |  | Update not provided
EHW03 | In Bloom/Green Flag | Achieve 2 Green Flag Awards at Bramshall Park and Stapenhill Gardens | Not Yet Due |  | Off Target |  | Update Not Provided |  | Update not provided
EHW04 | Street Cleansing - Litter | Maintain Top Quartile Performance | Not Yet Due |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
EHW05 | Street Cleansing - Detritus | Maintain Top Quartile Performance | Not Yet Due |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
EHW06 | Street Cleansing - Graffiti | Maintain Top Quartile Performance | Not Yet Due |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
EHW07 | Street Cleansing – Fly-Posting | Maintain Top Quartile Performance | Not Yet Due |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
EHW08 | Recycling | Household Waste Recycled and Composted: Maintain Top Quartile Performance | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
EHW09 | Waste Reduction | Residual Household Waste Per Household: Maintain Top Quartile Performance | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
EHW10 | Delivering Better Services to Support Homelessness | Average time from appointment to initial decision for homeless applicants of 10 days | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
EHW11 | Continue to Maximise Utilisation of Self Contained Temporary Accommodation for Homeless Applicants | Reduce ‘Key to Key’ Void Turnaround to an average of 6 working days | In Danger of Falling Behind Target |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
EHW12 | Review options for continuing outreach services to Rough Sleepers | Report completed | On Track to be Achieved |  | Fully Achieved |  | Update Not Provided |  | Update not provided
EHW13 | Delivering Better Services to Support Homelessness | Launch Campaign to raise awareness of rough sleeping, street living and street begging | Fully Achieved |  | Fully Achieved |  | Update Not Provided |  | Update not provided
EHW14 | Produce a Business Plan to tackle selected empty homes | Business Plan Produced | Fully Achieved |  | Fully Achieved |  | Update Not Provided |  | Update not provided
EHW15 | Deliver Focussed Environmental Health Initiatives | Provide a six monthly report on Regulatory Services activity including initiatives covering licensed gambling premises, Civil Enforcement, Scrap metal compliance etc. | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
EHW16 | Deliver Focussed Environmental Health Initiatives | Undertake a targeted initiative to identify Unlicensed Houses in Multiple Occupation | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
EHW17 | Deliver Focussed Environmental Health Initiatives | Complete an evaluation of all Licensable Animal Activities and report to DEFRA | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
EHW18 | Improve active links: easy in and easy out of Burton | Working with SCC, audit the existing walking and cycling network and propose the upgrade and improvement of the network to ensure Burton is well connected to and from its town centre | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
EHW19 | Improve active and green links: easy in and easy out of Burton | Begin scoping works for a bus interchange and active travel hubs in the Burton Place area | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
EHW20 | Upgrade Burton Railway Station in terms of functionality and aesthetics | Continue to work with the relevant rail authorities and partners to invest in and improve the fabric of Burton Railway Station building | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
EHW21 | Upgrade Burton Railway Station in terms of functionality and aesthetics | Work with partners to lobby for the opening of the Burton to Lichfield and Ivanhoe rail links | Not Yet Due |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided
EHW22 | Achieve optimum working in economic partnership | Continue to work with strategic tourism partners to facilitate the promotion of tourism | Not Yet Due |  | Not Yet Due |  | Update Not Provided |  | Update not provided
EHW23 | Achieve optimum working in economic partnership | Support partners such as the National Forest and Transforming The Trent Valley in delivering environmental enhancement projects, such as the Brook Hollows project | On Track to be Achieved |  | On Track to be Achieved |  | Update Not Provided |  | Update not provided

## Custom Pivot
Angela Wakefield
Update Not Provided
Brett Atkinson
Update Not Provided
Fully Achieved
Catherine Grimley
Update Not Provided
Chloe Brown
Update Not Provided
Chris Ebberley
Update Not Provided
Fully Achieved
Guy Thornhill
Update Not Provided
James Abbott
Update Not Provided
Linda McDonald
Update Not Provided
Lisa Turner
Update Not Provided
Margaret Woolley
Update Not Provided
Fully Achieved
Michael Hovers
Update Not Provided
Michael Hovers & Margaret Woolley
Update Not Provided
Nathan Gallagher
Update Not Provided
Paul Farrer
Update Not Provided
Fully Achieved
Paul Nephin
Fully Achieved
Rachel Liddle
Update Not Provided
Sara Botham
Update Not Provided
Sarah Richardson
Update Not Provided
Thomas Deery
Update Not Provided
Fully Achieved
Daniel Arnold
Update Not Provided
Planning Manager
Update Not Provided
Simon Humble
Update Not Provided
Mark Rizk
Update Not Provided
Grand Total